## Sheet1
Tendring Approved Schemes - Prioritised for 2018/19 Deliverable Programme
|  | Schemes key | Complete | Cancelled | Update
Ref | Cost Code | Scheme | Parish | Application Received Date | Completion Date | Scheme Category | Scheme Stage | Works Description | Allocation Budget | Comments
Approved Schemes - Prioritised for delivery in 2018/19
1 | LTEN158002 | Footpath 45 & 48 Lawford - Surface upgrade | Lawford | 2015-06-10 | Q3 | Public Rights of Way | Total Scheme | Provision of a firm, levelled surfaced path sufficient for all year use. | 24000 | Completed 05/09/2018.
2 | LTEN153003 | Ramsey Road, Dovercourt - Footpath links | Ramsey | 2015-01-11 | Q3 | Walking | Design | Design of two small sections of footway to link Gipsey Lane and Ramsey Service Road. | 5000 | Design complete 02/10/2018.
3 | LTEN165024 | Thorpe Road, Weeley - Stop infrastructure - eastbound | Weeley | 2018-11-28 | Q2 | Passenger Transport | Total Scheme | Additional bus stop infrastructure required due to ECC retendered route | 2200 | Completed May 2018.
4 | LTEN165023 | Thorpe Road, Weeley - Stop infrastructure - westbound | Weeley | 2018-11-28 | Q2 | Passenger Transport | Total Scheme | Additional bus stop infrastructure required due to ECC retendered route | 2200 | Completed May 2018.
5 | LTEN165039 | Point Clear to St. Osyth - Bus stop infrastructure upgrade | St. Osyth | 2016-11-29 | Q3 | Passenger Transport | Total Scheme | From Point Clear to St. Osyth the bus route infrastructure needs upgrading. Poles, flags, cages and timetables. | 15500 | Completed July 2018.
6 | LTEN165042 | Kirby Le Soken to Kirby Cross, Tendring - Bus stop infrastructure upgrade | Various | 2016 | Q3 | Passenger Transport | Total Scheme | Kirby-le-Soken to Kirby Cross, the bus route infrastructure needs upgrading. Poles, flags, cages and timetables. | 7500 | Completed July 2018.
7 | LTEN172002 | Brickmans Hill, Bradfield - TMI | Bradfield | 2016-06-26 | Q3 | Safer Roads | Total Scheme | Design and implementation of signing and lining improvements, edge of carriageway markers and vehicle activated signage. | 18000 | Signing, lining and edge of carriageway markings completed in October. Awaiting bend ahead VAS installation.
8 | LTEN152015 | B1027, Alresford | Alresford | 2016-11-22 | Q3 | Traffic Management | Total Scheme | Design and implementation of a Vehicle Activated Sign. | 6000 | Design and vegetation clearance investigation underway. Estimated to be completed mid December.
9 | LTEN165044 | Walton-on-the-Naze to Kirby Cross, Tendring - Bus stop infrastructure upgrade | Various | 2015 | Q4 | Passenger Transport | Total Scheme | Walton-on-the-Naze to Kirby Cross, the bus route infrastructure needs upgrading. Poles, flags, cages and timetables. | 15000
10 | LTEN165046 | Naze to Walton, Tendring - Bus stop infrastructure upgrade | Various | 2016 | Q4 | Passenger Transport | Total Scheme | Naze to Walton, the bus route infrastructure needs upgrading. Poles, flags, cages and timetables. | 9500
11 | LTEN181001 | Lower Park Road jw Station Road, Brightlingsea | Brightlingsea | 2017-11-23 | Q4 | Safer Roads | Total Scheme | Design and installation of a pedestrian island, signing and lining improvements, tree canopy adjustments. | 22790 | Design complete. This will be issued through Direct Delivery.
12 | LTEN142068 | A137 Lawford Manningtree - Shuttle signals | Lawford | 2014-09-09 | Q4 | Traffic Management | Design | Detailed design to follow completion of trial holes in 2018/19. | 10000 | Trial holes complete. Now progressing detailed design with ITS.
13 | LTEN003003 | Steam Mill Road, Bradfield - New footway | Bradfield | Before LHP | Q4 | Walking | Total Scheme | Re-profiled from 2018/19. Delivery of footway. | 215000 | Resident letter drop from the completion of the trial holes was undertaken 16/10/2018. Trial hole data sent to UKPN. UKPN work due in December 2018. Footway expected start date anticipated for January 2019.
14 | LTEN163002 | Thorrington Road, Great Bentley - New footway | Great Bentley | 2013-07-23 | Q4 | Walking | Feasibility | Feasibility Study into new footway link for Brook Farm to Great Bentley. | 5000
15 | LTEN165027 | The Street, Little Clacton, outside No 157 - Replacement shelter | Little Clacton | 2016-09-04 | Q4 | Passenger Transport | Total Scheme | Replacement metal bus shelter. | 10500 | On hold - Shelter supplier issues.
16 | LTEN162003 | B1035 Clacton Road, Mistley - Weight restriction | Mistley | 2015-01-13 | Q4 | Traffic Management |  | Signage review of existing weight limit prohibitions and any remedial works associated with it including additional surveys. | 5000
17 | LTEN152082 | Ramsey Village - HGV Route | Ramsey | 2015 | Q4 | Traffic Management | Implementation | Feasibility Study looking at the safest route for HGVs and the signage that would be required. | 7500 | Feasibility Study progressed into detailed design. Could be delivered by direct delivery within this financial year.
18 | LTEN162002 | The Street, Crow Lane, Crown Lane, Tendring Village - TMI | Tendring | 2014-10-28 | Q4 | Traffic Management | Design | Design and consideration into improvement options - Single chevrons, verge marker posts at the bends and a bend warning sign. | 4000
19 | LTEN162010 | Valley Road, Clacton-on-Sea - Junction modifications | Clacton-on-Sea | 2016-11-28 | Q4 | Traffic Management | Feasibility Study | Feasibility Study into traffic management improvements at the junction. | 3000
20 | LTEN162009 | Various locations around Manningtree - Signage review | Lawford | 2018-05-08 | Q4 | Traffic Management | Feasibility Study | Signage review to look into the untidy/unnecessary and outdated signage around the town of Manningtree. | 4000
21 | LTEN162007 | Marine Parade East, Clacton-on-Sea - Zebra crossing | Non parished | 2015-09-10 | Q4 | Traffic Management | Design | Detailed design and TRO for a zebra crossing, degree of pedestrian conflict score criteria met (1.65 x 10^8) | 6000
22 | LTEN163009 | Grange Road, Lawford - New footway | Lawford | 2016 | Q4 | Walking | Design | Detailed design of footway. | 5000
23 | LTEN142079 | Bridge over Holland Brook, Church Road, Little Bentley - Priority working signage | Little Bentley | 2014-10-28 | Q4 | Traffic Management | Design | Design of priority working signs with advanced warning signs. | 6000
24 | LTEN172034 | Harwich Road jw Frating Road, Great Bromley | Great Bromley | 2016-10-13 | Q4 | Traffic Management | Total Scheme | Panel consideration for funding of points 1, 3, 5a, 5b and 6 highlighted with the completed Casualty Reduction report. | 18000 | This has been earmarked for delivery by the Direct Delivery team.