## Uttlesford
|  |  | Key: | COMPLETED | CANCELLED | UPDATE
Ref | Cost Code | Scheme name | Parish | Estimated Finish | Scheme Category | Scheme stage | Works Description | Allocated Budget | Comments
Approved Schemes - For Delivery in 2018/19
1 | LUTT168010 | Bridleway 36 Clavering | Clavering | COMPLETED | Public Rights of Way | Total scheme | Further surface improvements following on from works undertaken in 2014 | 30000
2 | LUTT162045 | Crix Green Felsted - Signage | Felsted | Quarter 4 | Traffic Management | Design | Warning signage for the bends | 4000 | This scheme was installed by the direct delivery gang.
3 | LUTT162042 | B1053 / B1054 section between Radwinter and Hempstead - Deer warning signage | Radwinter | COMPLETED | Traffic Management | Total Scheme | Request to look into deer warning signage | 6500
4 | LUTT162064 | Manuden Road, Manuden and Berden - Chevron signs | Manuden | COMPLETED | Traffic Management | Total Scheme | Request for chevron signs to increase awareness of the s-bend | 8000
5 | LUTT162065 | Ashdon primary - Advisory 20mph outside the school | Ashdon | Quarter 4 | Traffic Management | Total Scheme | The Parish have reported concerns over speeding. Implementation of measures outside the school | 17000 | The signage has been installed, awaiting the installation of the wig wags.
6 | LUTT162066 | Walden Road, Little Walden - Speed limit amendments | Little Walden | Quarter 4 | Traffic Management | Design | Initial design and TRO for reducing the existing 40mph limit to 30mph and also to introduce a new 40mph buffer limit | 4000 | The design and TRO will be progressed towards the end of the financial year.
7 | LUTT162072 | Elizabeth Way j/w Lavender Fields, Saffron Walden - Keep clear markings | Saffron Walden | COMPLETED | Traffic Management | Total Scheme | Request for keep clear markings to enable vehicles to get out of the car park | 4000
8 | LUTT172011 | Cambridge Road, Quendon outside Waterbutt Cottages | Quendon | Quarter 4 | Traffic Management | Feasibility | Feasibility study to look at ways of improving the parking situation outside the Cottages | 4000
9 | LUTT172003 | Bumpstead Road, Hempstead - 40mph buffer speed limit | Hempstead | Quarter 4 | Traffic Management | Design | TRO and design works associated with a 40mph buffer and gateway feature | 4000 | The design and TRO will be progressed towards the end of the financial year.
10 | LUTT172004 | Rookery Lane, Wendens Ambo - Signage amendments | Wendens | COMPLETED | Traffic Management | Total Scheme | Implementation of signage recommendations following on from the feasibility study undertaken in 2016 | 5000
11 | LUTT172005 | Ross Close, Saffron Walden - Pram crossings | Saffron Walden | COMPLETED | Walking | Total Scheme | Installation of 1 pair of pram crossings outside the access to the Junior School | 8000
12 | LUTT172016 | Hollow Road, Widdington - Advanced height restriction signage | Widdington | Quarter 4 | Traffic Management | Total Scheme | Detailed design and installation of improved signage on the approach to the low bridge as identified in the feasibility study | 8000 | The need for a Basic Asset Protection Agreement (BAPA) with Network Rail means it will not be possible to install this signage in this financial year.
13 | LUTT172017 | North Hall Bridge, Quendon - Advanced height restriction signage | Quendon | Quarter 4 | Traffic Management | Total Scheme | Detailed design and installation of improved signage on the approach to the low bridge as identified in the feasibility study | 8000 | The need for a Basic Asset Protection Agreement (BAPA) with Network Rail means it will not be possible to install this signage in this financial year.
14 | LUTT172019 | B1051 Stansted Road, Stansted - Advanced weight limit signage | Stansted | Quarter 4 | Traffic Management | Total Scheme | Detailed design and installation of improved signage on the approach to the weight limit as identified in the feasibility study | 21000 | It will not be possible to install the signage in this financial year, so consideration will need to be given from the 2019-20 budget.
15 | LUTT172020 | Ugley Road, Ugley - Width restriction | Ugley | Quarter 4 | Traffic Management | Total Scheme | Detailed design and installation of improved signage on the approach to the width restriction as identified in the feasibility study | 8000
16 | LUTT172023 | Wenden Road, Arkesden - Traffic improvement measures | Wenden | Quarter 4 | Traffic Management | Total Scheme | Measures to look at protecting a listed building on a narrow lane from being struck | 6000 | This scheme has been earmarked for installation by the direct delivery gang.
17 | LUTT172024 | Steventon End, Ashdon - Junction improvements | Ashdon | COMPLETED | Traffic Management | Total Scheme | Request to look at the Walden Road junction with Steventon End | 4500
18 | LUTT172025 | Chelmsford Road, Barnston - Deer warning signs | Barnston | COMPLETED | Traffic Management | Total Scheme | Deer warning signs on Chelmsford Road Barnston at either end of the village | 6500
19 | LUTT173001 | The Endway, Great Easton - Installation of footway, phase 1 | Great Easton | Quarter 4 | Walking | Total scheme | Installation of footway between Rebecca Mead and the B184 | 50000 | The installation is scheduled to commence on the 25th March.
20 | LUTT162036 | Duck Street, Little Easton - 40mph buffer speed limit | Little Easton | Quarter 4 | Traffic Management | Total scheme | Implementation of a 40mph buffer speed limit as designed and advertised in 2017-18 | 8000
21 | LUTT162016 | The Street, High Easter - 40mph buffer speed limit | High Easter | Quarter 4 | Traffic Management | Total scheme | Implementation of a 40mph buffer speed limit as designed and advertised in 2017-18 | 8000 | Objections had been received which has meant that it is not now possible to install the works in the 2018-19 financial year. Consideration will now need to be given to funding from the 2019-20 budget.
22 | LUTT162067 | High Easter Road, Barnston - Mini roundabout improvements | Barnston | Quarter 4 | Traffic Management | Total scheme | Installation of works recommended in the feasibility study undertaken in 2017/18 | 26000 | At the January meeting the members agreed to the additional £13,500 required to be able to progress the installation of the works. Physical works are scheduled for the week commencing 11th March.
23 | LUTT162060 | Willow Road, Great Dunmow - No through road sign | Great Dunmow | Quarter 4 | Traffic Management | Total scheme | Installation of a no through road sign | 4500 | This was agreed as an additional scheme for Direct Delivery at the September panel meeting
24 | LUTT162060 | Bullocks Lane, Hope End - No through road | Great Canfield | Quarter 4 | Traffic Management | Total scheme | Installation of a no through road sign | 4500 | This was agreed as an additional scheme for Direct Delivery at the September panel meeting
25 | LUTT162044 | Hatfield Forest approach - Advanced warning low bridge signage | Takeley | Quarter 4 | Traffic Management | Total scheme | Installation of improved signage as identified in feasibility study undertaken in 2017-18 | 21000 | This was agreed as an additional scheme for Direct Delivery at the September panel meeting
Provisionally Approved Schemes - For Delivery in 2019/20
26 | LUTT182020 | Chelmsford Road, Barnston - Road widening design | Barnston | 2019-20 | Traffic Management | Design | Detailed design for possible road widening following on from feasibility study undertaken in 2015-16 | 9500 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
27 | LUTT173002 | Church Street, Saffron Walden - Footway widening and junction study | Saffron Walden | 2019-20 | Walking | Feasibility | Feasibility to look at the possibility of widening the footway close to the junction with Museum Street | 5500 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
28 | LUTT172016 | Hollow Road, Widdington - Advanced height restriction signage | Widdington | 2019-20 | Traffic Management | Implementation | Detailed design and installation of improved signage on the approach to the low bridge as identified in the feasibility study | 8000 | This was a reprofiled scheme from 2018-19 which Members provisionally approved as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
29 | LUTT172017 | North Hall Bridge, Quendon - Advanced height restriction signage | Quendon and Rickling | 2019-20 | Traffic Management | Implementation | Detailed design and installation of improved signage on the approach to the low bridge as identified in the feasibility study | 8000 | This was a reprofiled scheme from 2018-19 which Members provisionally approved as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
30 | LUTT173004 | The Endway, Great Easton - footway phase 2 | Great Easton | 2019-20 | Walking | Total scheme | Installation of footway between Rebecca Mead and the B184 | 80000 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
31 | LUTT172030 | Dunmow Road Leaden Roding - Signage improvements | Leaden Roding | 2019-20 | Traffic Management | Design | Request to look at a VAS or traffic calming on the approach to the Primary School | 6000 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
32 | LUTT172031 | Bolford Street, Thaxted - 40mph buffer speed limit | Thaxted | 2019-20 | Traffic Management | Design | Request to consider installing a 40mph buffer and gateway signage | 4500 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
33 | LUTT172037 | Walden Road, Hadstock - Signage amendments | Hadstock | 2019-20 | Traffic Management | Total scheme | Request to look at measures to slow traffic on the approach to the village | 6000 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
34 | LUTT172034 | Audley End Road, Audley End, Saffron Walden - Pedestrian crossing improvements | Saffron Walden | 2019-20 | Traffic Management | Feasibility | Request to look at a speed limit reduction or pedestrian improvements on the approach to Audley End House | 4500 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
35 | LUTT162043 | Manuden Road / The Street Manuden - Legal works associated with the kerbing | Manuden | 2019-20 | Traffic Management | Design | Installation of kerbing as identified in feasibility study undertaken in 2017-18 | 2000 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
36 | LUTT162052 | Rosemary Lane junction with North Street, Great Dunmow - Mini roundabout realignment | Great Dunmow | 2019-20 | Traffic Management | Feasibility | Installation of works recommended in the feasibility study undertaken in 2017/18 | 4000 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
37 | LUTT182006 | Ashdon Road, Saffron Walden - Traffic flow improvements | Saffron Walden | 2019-20 | Traffic Management | Feasibility | Request to look at improving traffic flow through Ashdon Road | 4000 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
38 | LUTT182013 | Cambridge Road, Quendon - 40mph buffer | Quendon and Rickling | 2019-20 | Traffic Management | Design | Design and TRO for a 40mph buffer | 8000 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
39 | LUTT182015 | Stortford Road, Leaden Roding - Speed limit extension | Leaden Roding | 2019-20 | Traffic Management | Feasibility | Extension to the existing 30mph limit on the Stortford Road as looked at originally in 2016 | 8000 | Members provisionally approved this as a P1 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
40 | LUTT182014 | Cambridge Road, Newport - speed limit request | Newport | 2019-20 | Traffic Management | Feasibility | Request to consider extending the existing 30mph limit or introducing a 40mph buffer for the new development | 10000 | Members provisionally approved this as a P2 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
41 | LUTT172047 | Hawkins Hill Little Sampford - speed limit | Little Sampford | 2019-20 | Traffic Management | Feasibility | Request for a 40mph speed limit on Hawkins Hill | TBC | Members provisionally approved this as a P2 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
42 | LUTT172048 | Main Road, Felsted - on the approach to Milch Lane - Safety improvements | Felsted | 2019-20 | Traffic Management | Feasibility | Request to improve the signage on the approach to the Milch Lane junction for southbound traffic | 10000 | Members provisionally approved this as a P2 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
43 | LUTT182024 | Rands Road, High Roding - 30mph speed limit extension | High Roding | 2019-20 | Traffic Management | Feasibility | Request to extend the existing 30mph speed limit | 10000 | Members provisionally approved this as a P2 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
44 | LUTT182012 | Old Mead Road - Chevrons | Henham | 2019-20 | Traffic Management | total scheme | Request for a chevron on the bend outside The White House | 4500 | Members provisionally approved this as a P2 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
45 | LUTT186001 | Braintree Road, Felsted - Bus cages | Felsted | 2019-20 | School Crossing Patrols | Total scheme | Request to install 2 x bus cages outside the Primary school | 4000 | Members provisionally approved this as a P2 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
46 | LUTT198001 | Byway 63 Clavering / Byway 3 Berden | Clavering | 2019-20 | Public Rights of Way | Total scheme | Refurbishments works to byway | 40000 | Members provisionally approved this as a P2 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
47 | LUTT172003 | Bumpstead Road, Hempstead - Implementation of 40mph buffer | Hempstead | 2019-20 | Traffic Management | Total scheme | Implementation of speed limit advertised in 2018-19 | 4000 | Members provisionally approved this as a P2 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval
48 | LUTT162066 | Little Walden - Implementation of amendments to existing speed limit | Little Walden | 2019-20 | Traffic Management | Total scheme | Implementation of speed limit advertised in 2018-19 | 11000 | Members provisionally approved this as a P2 project for inclusion in the 2019-20 programme, subject to Cabinet Member approval

## Issues (hidden)
RAG * | Design Reference Number | Task Name | Parish | Finish | CMA approved | Cost Code | Works Description | Allocated Budget | Comments | Luke Comments