## Sheet1
Basildon Potential Schemes List - 22 November 2018
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
B148 Westmayne / Ford Access / Lower Dunton Rd, Langdon Hills | Installation of tactile paving, dropped kerbs and cyclist give way markings and possible upgrade of the uncontrolled crossing points with cyclists in mind. | Signals were recently upgraded in this location (not an LHP funded scheme). The stage 2 safety audit found a number of improvements that could be made for the benefit of pedestrians and cyclists. | Road Safety |  | Walking | TBC | LBAS183001 | TBC | In discussion with Kris Radley (Essex Cycling Strategy Leader) to find suitable recommendations.
Radwinter Avenue, Wickford - Speeding | Request to investigate excessive speeds on bend along Radwinter Avenue, Wickford | Concerns relating to excessive speeds and alleged unrecorded accidents on bend. | Cllr Ball |  | Traffic Management | TBC | LBAS182017 | TBC | Site visited with Cllr Ball and subsequently with the validating engineer. Scheme still in validation, but measures discussed on site include highlighting the junction on the bend (with warning signs) and the installation of SLOW markings.
Kathleen Ferrier Crescent, Laindon | Request for bollards on grass verge | Parking on verges. | Cllr Davies |  | Traffic Management | TBC | LBAS182022 | TBC | Information obtained on verge schemes undertaken in other District/Boroughs as requested. To be discussed at meeting.
Lee Chapel Primary School, Basildon | Request for 20's Plenty |  | Cllr Smith |  | Traffic Management | TBC | LBAS182025 | TBC | It is recommended that the Panel first assess the benefits of the 20's Plenty sites being installed this year before seeking to install elsewhere.
5 Bells slip road to Southend Road southbound | Request for reduction in lanes on roundabout approach | The problem is unclear. | Cllr Smith |  | Traffic Management | TBC | LBAS182026 | TBC | No history of accidents in this location, and no obvious reason to reduce the number of lanes from 3 to 2. Further info as to the rationale behind this request would be required to proceed any further.
High Road, Laindon (bridge section above Mandeville Way and Laindon train station) | Request for crossing upgrade to signalised crossing | Existing crossing not visible enough, and well used. | Cllr Smith |  | Walking | TBC | LBAS183007 | TBC | Site visited with validating engineer. Initial signs indicate that this could be a worthwhile location for a crossing upgrade. Awaiting full validation.
Nightingales junction with Aylesbury Drive, Basildon | Request for bus shelter |  | Cllr Smith |  | Passenger Transport | Total scheme | LBAS185002 | 11000
Highview Avenue junction with Amersham Avenue, Langdon Hills | Request for bus shelter |  | Cllr Smith |  | Passenger Transport | Total scheme | LBAS185003 | 11000 | A shelter would be viable here, but would heavily obstruct a residents window. We would therefore not recommend installation. Consultation with resident would be required to proceed with this request.
Highview Avenue junction with Derby Close | Request for bus shelter |  | Cllr Smith |  | Passenger Transport | Total scheme | LBAS185004 | 11000
Station Road, Wickford | Request for zebra crossing close to Aldi supermarket |  | Cllr Buckley |  | Walking | TBC | LBAS183008 | - | It would not be possible to install a zebra crossing at the existing crossing point due to the proximity to the busy junction and the lack of visibility. Any further away from the junction though and the crossing is unlikely to be on the desire line for pedestrians and therefore highly unlikely to meet the PV² criteria.
Outside Basildon hospital, Nethermayne | Request for new bus shelter |  | Passenger Transport |  | Passenger Transport | Total scheme | LBAS185006 | 11000
Pitsea Broadway East bus stop | Request to extend bus stop markings |  | Passenger Transport |  | Passenger Transport | TBC | LBAS185007 | TBC
Salcott Cresc and Cranfield Park Rd Bus Shelters | Request to install 7 new stops including 2 shelters, in a westbound direction to allow full provision of the 94 bus service |  | Passenger Transport |  | Passenger Transport | TBC | LBAS185009 | TBC
Dry Street, Basildon | Request to move the existing speed cushions |  | Cllr Smith |  | Traffic Management | TBC | LBAS182027 | TBC | Site visited with validating engineer. There is nowhere that the cushions could be moved without being outside a property. If Members would like the cushions removed then consultation would need to be undertaken first with evidence of support from the majority of residents.
Bridleway 239 near Fern Walk, Langdon Hills | Request for improvements to the surface of the bridleway |  | Cllr Smith |  | Public Rights of Way | TBC | LBAS188001 | TBC | Scheme in validation.
66-80 Gernons, Basildon | Request for the installation of a ramp |  | Cllr Smith |  | Walking | TBC | LBAS183010 | TBC | Site visited with the validating engineer. The verge (if adopted highway - as yet unconfirmed) is too steep to install a simple ramp. The ramp would need to be long and gradual and would cover a long distance. Would be disproportionately costly considering the number of residents benefiting.
Close to 69 Codenham Green, Basildon | Request for the installation of measures to prevent driving/parking on the footway |  | Cllr Smith |  | Walking | TBC | LBAS183011 | TBC
Norsey Road, Billericay | Request for a zebra crossing |  | Cllr Moore |  | Walking | TBC | LBAS183012 | TBC | Site visited with the validating engineer. Site extremely unlikely to meet the required PV² criteria. We would therefore recommend to not proceed with this request.
Wickford Junior School, Wickford | Request for Keep Clear Markings |  | Cllr Buckley |  | Traffic Management | TBC | LBAS182028 | TBC | Scheme in validation.
GP Surgery to Lee Chapel South Community Centre | Request for pedestrian guard railing | Pedestrians are struggling when walking between the GP Surgery and Lee Chapel South Community Centre due to the incline of the footway | Cllr Smith |  | Walking | TBC | LBAS183013 | TBC | Scheme in validation.
Hawthorn Path | Request for signage to indicate the cycle lane on the shared footway / cycleway | Cyclists are knocking pedestrians when they cycle along Hawthorn Path | Cllr Smith |  | Walking | TBC | LBAS183014 | TBC | Scheme in validation.
Outside 49 Ingaway, Basildon | Request for grasscrete/ concrete | Vehicles are driving over a section of verge causing rutting | Cllr Smith |  | Traffic Management | TBC | LBAS182031 | TBC | Scheme in validation.
Dry street j/w Dixon Road, Basildon | Request to install a chevron sign | A new housing development is being built and on the approach there is a sharp corner | Cllr Smith |  | Traffic Management | TBC | LBAS182030 | TBC | Scheme in validation.
B1007 Laindon Link / Gt Knightleys | A request has been received to look at the junction layout | There is currently a dedicated right and left turn into a car park that is no longer used | Intelligent Traffic signals |  | Traffic Management | TBC | LBRA182036 | TBC | Scheme in validation.
Staneway jw High Road | Request to change the current 50mph speed limit to a 40mph speed limit | It has been mentioned that vehicles are driving too fast past the junction of High Road | Cllr Smith |  | Traffic Management | TBC | LBAS182037 | TBC | Awaiting speed survey data
Stanbridge Path | Request for a salt bin | There is a steep slope along Stanbridge Path which gets icy in the winter | Cllr Smith |  | Traffic Management | TBC | LBAS182038 | TBC | Scheme in validation.
Florence Way | Request for a zebra crossing | Pedestrians are having difficulty crossing the road in this location | Cllr Smith |  | Walking | TBC | LBAS183016 | TBC | Awaiting speed survey data
Junction of Mill Road to Southend Road, Billericay | Request to look at junction improvements at the junction of Mill Road and Southend Road | There are concerns over the visibility of this junction | Cllr Moore |  | Traffic Management | TBC | LBAS182039 | TBC | Scheme in validation.
Roberts Road, Laindon | Request to look into the speeds of traffic along Roberts Road | Vehicles are using Roberts Road as a cut through and residents are concerned about vehicles speeds | Cllr Henry |  | Traffic Management | TBC | LBAS182040 | TBC | Awaiting speed survey data
Bells Hill Road, Basildon | Request for a salt bin | When the weather conditions get icy pedestrians struggle to walk along Bells Hill Road | Cllr Smith |  | Traffic Management | TBC | LBAS182041 | TBC | Scheme in validation.
33-49 The Slade, Basildon | Request to look at the possibility of installing grasscrete or wooden bollards | Vehicles are driving over a section of verge causing rutting | Cllr Smith |  | Traffic Management | TBC | LBAS182042 | TBC | Scheme in validation.
Latchetts Shaw, Basildon | Request for grasscrete | Vehicles are parking on the verge | Cllr Smith |  | Traffic Management | TBC | LBAS182045 | TBC | Scheme in validation.
Spains Hall Place, Basildon | Request for a layby | Vehicle are parking inappropriately | Cllr Smith |  | Traffic Management | TBC | LBAS182046 | TBC | Following site meeting with Cllr Smith and residents of Spains Hall Place it was noted that SEPP were going to be looking into double yellow lines in this location. LHP scheme to be looked at following SEPP scheme.
Entrance to Woodlands School Woodlands Approach | Request for a salt bin | Children have difficulty walking to school in icy conditions | Cllr Smith |  | Traffic Management | TBC | LBAS182047 | TBC | Scheme in validation.
Clay Hill Lane jw Sparrow Herne | Request to improve the current drop kerbs at the junction | There is currently no tactile paving at the drop kerbs | Cllr Smith |  | Walking | TBC | LBAS183016 | TBC | Scheme in validation.