## Sheet1
Braintree Potential Schemes List - 22nd November 2018
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
Kelvedon Road, Coggeshall | Install a VAS for southbound traffic | Speeding along this road is reported as a major concern as vehicles enter the village | Coggeshall Parish Council | Coggeshall | Traffic Management | Total scheme | LBRA162017 | 11000 | A new speed survey has been undertaken and it still meets the guidance for a VAS to be installed travelling southbound. However there are still concerns regarding signage clutter.
Byway 3, Pentlow - PROW improvements | Blade the byway level, implement a sub-base and drainage and cap with a suitable all-weather surface |  | PROW Officer | Pentlow | Public Rights of Way | Total scheme | LBRA168001 | 39000
Byway 43 Steeple Bumpstead - PROW improvements | 1. Remove all loose materials on top of the firm base. 2. Black top using existing foundations and build surface back up in level with ditches. 3. Install drainage ditch and piping for 75m. |  | PROW Officer | Steeple Bumpstead | Public Rights of Way | Total scheme | LBRA168003 | 45500
Finchingfield Road, Steeple Bumpstead - Feasibility for layby | Feasibility for installation of a layby | The verge is frequently used by hearses and those attending funerals which is rutting the verge | Cllr Westrope and Cllr Finch | Steeple Bumpstead | Traffic Management | Feasibility | LBRA162020 | 6500 | There are a number of issues with installing a parking bay here. The level difference from the edge of carriageway to the back of the verge is quite large and to install a parking bay would mean excavating a large amount of the verge, this could affect the brick wall that is there. There is also a BT chamber which would need to be moved, this could add significantly to the delivery costs of the scheme. There is a bench in-situ as well and this would likely need to be removed to allow the bay to be installed.
Cressing Road, Braintree south of Stubbs Lane | Request for a detailed design | Pedestrians and school children are having problems crossing the road | Cllr Lady Newton | Braintree and Bocking | Walking | Design | LBRA173006 | 26000 | A video survey was undertaken as requested by the panel in July 2017 and it has shown that most pedestrians cross within the location that the signalised crossing is being suggested.
Boars Tye Road, Silver End - Footway | Complete sections 2&3 of the footway (Ralph's Farm to Brettons 400m) | Currently no footpath | Historical scheme | Silver End | Walking | Implementation | LBRA163006 | 97500
Colne Road, Coggeshall - Footway | Detailed design for Option 2 - Install a footway on the western side of Colne Road including a retaining wall. | There is no footway from Brick Kiln Close to the Fire Station | Cllr Lady Newton | Coggeshall | Walking | Design | LBRA163001 | 71500
Hill Lane j/w the A1017, Sturmer | Improve the current footway and install dropped crossing with tactile paving | A lack of footway at the junction of Hill Lane and the A1017 | Sturmer Parish Council | Sturmer | Walking | Total scheme | LBRA173003 | 69000 | The feasibility has been returned with several options ranging from £19,500 to £69,000 after speaking with Sturmer Parish Council they have decided that option 4 £69,000 would be the most suitable option.
Colne Road to the Colchester bound carriageway of the A120 | Dedicated left hand lane from Colne Road to the A120. | Congestion along Colne Road | Cllr Lady Newton | Coggeshall | Traffic Management | Feasibility Only | LBRA172010 | 6500 | Feasibility study has been returned but needs to be checked by Highway England to determine if these works are suitable.
Mitchells Avenue, Halstead | Request for some signage to indicate to vehicles which way to drive around the informal traffic island | Vehicles are travelling in both directions around the informal traffic island | Halstead Town Council | Halstead | Traffic Management | Feasibility | LBRA172016 | 2000 | Land is not highway maintainable need to determine the land owner and contact them in the first instance.
Old Challis Rise – Salt Bin | Request for a salt bin and land negotiations | The footway is used by school children walking to Rayne Primary School and with the recent weather the footways have been slippery | Rayne Parish Council | Rayne | Traffic Management | Feasibility | LBRA172036 | 2000 | Validation has proposed installing a salt bin however the land is not highway maintainable so we would need to negotiate the land in the first instance.
Mill Park Drive | Request for traffic calming | When the development was installed only a small section of the road got traffic calming features and then it stops | Cllr Schmitt | Unparished | Traffic Management | Total scheme | LBRA182008 | - | Speed and volume survey results, 30mph speed limit: Mill Park Drive (N), Braintree Southbound mean av: 15.6mph Northbound mean av: 15.8mph Mill Park Drive (S), Braintree Southbound mean av: 18.1mph Northbound mean av: 18mph Against the Essex Speed Management Strategy to install traffic calming features as vehicle speeds show excellent compliance to the current 30mph speed limit.
B1018 Maldon Road, Witham | Request for a change in speed limit | Residents would like the current 40mph speed limit to be reduced to a 30mph limit | Cllr Louis | Witham | Traffic Management | Total scheme | LBRA182009 | TBC | In validation.
Pointwell Lane, Coggeshall - Salt Bin | Request for a Salt Bin | There are concerns that the carriageway is slippery and in the winter conditions vehicles struggle to exit Pointwell Lane | Coggeshall Parish Council | Coggeshall | Traffic Management | Total scheme | LBRA182011 | TBC | In validation.
Bridge Street, Coggeshall | Request to look into measures to protect the Grade II listed building | The property is situated close to the carriageway and there is no footway or measures to protect the property and large vehicles sometimes hit the property | Coggeshall Parish Council | Coggeshall | Traffic Management | Total scheme | LBRA182012 | TBC | In validation.
B1024 Coggeshall Road jw Upper Holt Street, Earls Colne | Request for Grasscrete | Vehicles are currently over-running the verges at both the entrance and exits to the junction and cutting up the grass verges | Earls Colne Parish Council | Earls Colne | Traffic Management | Total scheme | LBRA182014 | TBC | In validation.
Bakers Lane, Black Notley - VAS | Request for a VAS | There are concerns of vehicle speeds as they are driving along Bakers Lane | Black Notley Parish Council | Black Notley | Traffic Management | Total scheme | LBRA182013 | TBC | In validation.
Dog Chase, Wethersfield | Request to stop up the road | Vehicles are still travelling the wrong way along a one way system | Wethersfield Parish Council | Wethersfield | Traffic Management | Total scheme | LBRA182015 | TBC | In validation.
Kenworthy Road, Braintree | Request for 'no through road' signage | Vehicles are trying to gain access to London Road through Kenworthy Road and it is actually a no through road | Cllr Cunningham | Braintree and Bocking | Traffic Management | Total scheme | LBRA182016 | TBC | In validation.
Rowley Hill, Sturmer - 30mph roundel | Request for 30mph roundels | There are concerns over the speeds of vehicles through the village | Sturmer Parish Council | Sturmer | Traffic Management | Total scheme | LBRA182017 | TBC | In validation.
Caurtauld Close, Halstead | Request for drop kerbs with tactile paving | It is currently hard for the mobility impaired to cross the road at this location | Cllr Jo Beavis | Halstead | Walking | Total scheme | LBRA183002 | TBC | In validation.
B1018 Braintree Road Cressing - Carriageway and footway works | Carriageway widening, install a footpath and new kerbing. | It is difficult for two HGV's to pass on this bend due to the width of the road. | Cllr Lady Newton | Cressing | Traffic Management | Implementation | LBRA142006 | 237000
School Road, Silver End - Pedestrian Guard Rails / Layby | A Request to remove the existing layby and install more pedestrian guard railing and look at features to preserve the grass verges | Thee layby is not used and could be extended into a footway, the layout of the pedestrian guard railing and road markings was not looked at previously and vehicles are parking on the grass verge. | Cllr Abbott | Silver End | Traffic Management | Total scheme | LBRA182021 | TBC | In validation.
Vauxhall Drive and Maple Avenue, Braintree | Request for traffic calming features | The whole of Clare Road has traffic calming features and they do not cover Vauxhall Drive and Maple Avenue so there are concerns over the speeds of vehicles | Cllr Schmitt | Braintree and Bocking | Traffic Management | Total scheme | LBRA182022 | - | Speed and volume survey results, 30mph speed limit: Vauxhall Drive, Braintree Eastbound mean av: 17.3mph Westbound mean av: 17.7mph Maple Avenue, Braintree Eastbound mean av: 17.2mph Westbound mean av: 17.8mph Against the Essex Speed Management Strategy to install traffic calming features as vehicle speeds show excellent compliance to the current 30mph speed limit.
Audley End, Gestingthorpe | Request for a VAS | There are concerns over vehicles speeds | Gestingthorpe Parish Council | Gestingthorpe | Traffic Management | Total scheme | LBRA182023 | TBC | In validation.
Vicarage Road, Finchingfield | Request for 20's Plenty | There are concerns over speeds outside of the school | Finchingfield Parish Council | Finchingfield | Traffic Management | Total scheme | LBRA182024 | TBC | In validation.
A1017 Rowley Hill, Entrance and Exit to village | Request to amend the current gateway signage to indicate that it’s a speedwatch village | There are concerns of speeding through the village | Sturmer Parish Council | Sturmer | Traffic Management | Total scheme | LBRA182025 | TBC | In validation.
Pebmarsh Road, Pebmarsh | Request for 20's Plenty | There are concerns over speeds outside of the school | Pebmarsh Parish Council | Pebmarsh | Traffic Management | Total scheme | LBRA182026 | TBC | In validation.