## Sheet1
Schemes Awaiting Funding - July 2019
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
Fambridge Road (Limebrook Way RAB to Royal Oak Public House), Maldon | Walkable verge/footway | Lack of footway between small hamlet/public house and Maldon Town | Councillor | Maldon | Traffic Management | Implementation | LMAL162099 | TBC | Liaison ongoing regarding nearby development and footways planned within the development
Cedar Grove, Burnham on Crouch | Footway improvements | Accessibility issues on footways | Councillor | Burnham on Crouch | Traffic Management | Total scheme | LMAL182031 | NA | Validation - Parking on footway issues need to be addressed by Police/SEPP
Church Road (Holt Drive to Blacksmiths Lane) and Arbour Lane (Blacksmiths Lane to Grange Road), Wickham Bishops | Footways | Lack of pedestrian access to the Village Library | Parish Council | Wickham Bishops | Walking | Feasibility | LMAL153002 | 4000 | Validation - recommendation is for Feasibility Study to cover obtaining any land necessary for footway construction and also pedestrian/vehicle counts to assess potential usage and any conflict. Construction costs could be significant. Dec 17 Panel decision to remove scheme from Approved Works Programme and return to Potential Scheme List
Burnham Road, Latchingdon | Wooden bus shelter | Stop ID 1500LATCHG2 - metal shelter needs replacing (Parish Council owned Shelter) | Parish Council/Passenger Transport Team | Latchingdon | Passenger Transport | Total scheme | LMAL155016 | TBC | Validated by Passenger Transport team
Mill Lane j/w Buckingham Street, Tolleshunt Major | HGV Signage improvements | Road not suitable for HGV's | Parish Council | Tolleshunt Major | Traffic Management | Feasibility | LMAL162091 | 13000 | Validation - Existing 7.5 tonne weight limit signage in place and "Unsuitable for HGV" sign. Recommendation is for signage review of HGV directional signage to ensure vehicles use preferred route via School Road. Dec 17 Panel decision to remove scheme from Approved Works Programme and return to Potential Scheme List
Byway 32 Purleigh (Roundbush Road to Howe Green Road) | Improve drainage, rebuild surface, install heavy duty removable bollards | Southern end of byway badly rutted and is often impassable. There is also a seasonal TRO in place to restrict access. | Public Rights of Way | Purleigh | Public Rights of Way | Total scheme | LMAL168007 | 36000 | Validated by Public Rights of Way team - Dec 17 - Panel decision to return scheme from Approved Works Programme back to Potential Schemes List
B1018 Langford Road, Wickham Bishops | Carriageway improvements | Width of road when two vehicles try to pass | Resident | Wickham Bishops | Traffic Management | Feasibility Study | LMAL172008 | 10000 | Validation - "B" road and PR2, width restriction contrary to policy as its main function is movement of traffic. Suggestion is to review warning signs and road markings indicating hazards and narrow sections of road
Fambridge Road, Maldon | New bus stop poles/flags/timetables | Nine bus stops need clearly identifying, some flags on lamp columns | Passenger Transport | Maldon | Passenger Transport | Total scheme | LMAL175001 | 10000 | Validated by Passenger Transport team
Plains Road, Great to Little Totham | Speed reduction | Speed of traffic | Parish Council | Little Totham | Traffic Management | Total scheme | LMAL182008 | TBC | In validation - ATC data - 60mph speed limit - West - Eastbound 41.1mph & Westbound 40.5mph - East - Eastbound 37.7mph & Westbound 35.5mph
Church Lane, Honeypot Lane & Crows Lane, Stow Maries | 7.5 tonne environmental weight limit | Goods vehicle use of rural lane | Parish Council | Stow Maries | Traffic Management | Total scheme | LMAL182009 | NA | Validation - traffic survey data does not show an issue with HGV usage along the route, with 0.5% of vehicles being classed as HGVs
Blackhouse Farm Cottages, Steeple Road, St Lawrence | Traffic management improvements | Speeding traffic/vehicle damage to buildings | Councillor | St Lawrence | Traffic Management | Total scheme | LMAL182005 | TBC | In validation - ATC data - 60mph speed limit - NE bound 42.7mph & SW bound 42.7mph
Woodrolfe Road, Tollesbury | Surfacing in front of seawall | Loose/unbound material spreading onto carriageway | Parish Council | Tollesbury | Traffic Management | Design | LMAL182010 | 6500 | Validation - Recommends design of surfacing scheme and any necessary drainage. Design will also produce accurate costing, at this stage it would be expected to be approximately £22,000
B1018 Southminster Road near Dairy Farm Road, Althorne/Mayland | New bus stop | Changes to existing bus service | Councillor | Althorne | Passenger Transport | Total scheme | LMAL185001 | TBC | Validation - possible to implement two bus stops with kerbing. Feasibility of scheme would depend on bus service
School Road & The Street, Little Totham | Routing of HGV vehicles | Volume of traffic | Councillor | Little Totham | Traffic Management | Total scheme | LMAL182023 | TBC | Validation recommends not to proceed any further with this request. Implementation of signage would move the problem to a route which may be considered worse for HGVs.
Witham Road/Little Braxted Road, Little Braxted | Measures to stop HGV's using roads unnecessarily | HGV usage of rural roads | Parish Council | Little Braxted | Traffic Management | Total scheme | LMAL182011 | TBC | Validation recommends not to proceed any further with this request. The current signage has been reviewed and is considered sufficient.
Southminster Road (Old Heath Road to Mangaps Manor) Burnham on Crouch | Walkable verge/footway | Lack of footway/walkable verge for pedestrians | Councillor | Burnham on Crouch | Traffic Management | Implementation | LMAL142037 | NA | Feasibility Study does not recommend creating walkable verge
B1010 Fambridge Road (The Wash to Roundbush Public House), Purleigh | Speed reduction measures | Narrow road with passing places, speed of traffic | Parish Council | Purleigh | Traffic Management | Implementation | LMAL142031 | TBC | Feasibility study does not recommend to proceed due to high anticipated costs.
Hoe Mill Road/The Causeway, Ulting | Parking improvements | Bridge is a weak structure with vehicles routinely parking on it | Structures Team | Ulting | Traffic Management | Total scheme | LMAL182029 | 6500 | Validation - Recommends the design and implementation of parking restrictions to deter vehicles from parking on the weak bridge.
Wantz Road, Maldon | 2x Speed and volume surveys required. | Speeding and vehicles travelling in the wrong direction. | Cllr Channer | Maldon | Surveys | Surveys |  | 400
West Street, Tollesbury | Speed and volume survey required. | Speeding vehicles | Parish Council | Tollesbury | Surveys | Surveys |  | 200
Western Road, Burnham-on-Crouch | Speed and volume survey required. | Speeding vehicles | Cllr Pratt | Burnham on Crouch | Surveys | Surveys |  | 200
Burnham Road, Southminster | Speed and volume survey required. | Speeding vehicles | Cllr Pratt | Southminster | Surveys | Surveys |  | 200
Wickham Bishops SID Rotations | SID Rotations | SID rotations for Wickham Bishops | N/A | Wickham Bishops | VAS | Surveys |  | 1480
Chimney Pot Lane, Hazeleigh | Investigation into the possibility of placing restrictions to prevent HGVs from using the route | HGVs getting stuck at the brook | Cllr Channer | Hazeleigh | Traffic Management | Total scheme | LMAL192001 | TBC | In validation
Witham Road, Wickham Bishops | Investigation into the possibility of undertaking a review of the signing and lining along the route | Safety along the route | Parish Council | Wickham Bishops | Traffic Management | Total scheme | LMAL192002 | TBC | In validation
B1021 Burnham Road, Southminster | Residents have raised concerns in relation to speeding vehicles | Speeding vehicles | Cllr Pratt | Southminster | Traffic Management | Total scheme | LMAL182035 | TBC | Speed and volume survey results: Eastbound 41.6mph. Westbound 41.2mph. Good compliance within the posted speed limit, therefore not recommended to proceed with this request. Information shared with Cllr Pratt
West Street, Tollesbury | Percieved speeding issues | Speeding vehicles | Tollesbury Parish Council | Tollesbury | Traffic Management | Total scheme | LMAL182033 | TBC | Awaiting speed and volume survey information
Elysian Gardens, Tollesbury | Parish Council have reported obsructive parking. | Parking issues | Tollesbury Parish Council | Tollesbury | Traffic Management | Total scheme | LMAL192003 | TBC | In validation