## Sheet1
Colchester Potential Schemes List - January 2019
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
Millers Lane, Stanway - Footway | Request to investigate missing section of footway. | Pedestrians have to walk in the road. | Cllr Scott-Boutell | Stanway | Walking |  | LCOL152150 | TBC | Following the meeting with the Parish Council, Borough Councillors and County Member. Parish to liaise with residents, awaiting results. 02/11/2018 - Sonia has contact Cllr Scott-Boutell who agrees this can be removed for the time being.
Shrub End Road, Colchester - Pedestrain crossing | Pedestrian safety has been raised as a concern as there are no crossing points by the Co Op/Texaco garage on Shrub End Road. | Due to speeds and volumes of traffic elderly and disabled finding it difficult to cross road safely. | Cllr Lissimore | Prettygate | Walking |  | LCOL153006 | TBC | In validation - Degree of pedestrian, vehicle conflict survey = 0.261 x10^8.
The Commons, Colchester - Pedestrian crossing | Long, straight road which should have School Crossing Patrol however the position is vacant. | Pedestrians have expressed difficulty crossing the road. | Cllr Lissimore | Prettygate | Walking |  | LCOL163004 | TBC | In validation - Degree of pedestrian , vehicle conflict survey = 0.515 x10^8.
Halstead Road, Stanway | Speeding complaints raised through Stanway Parish Council and County Member. Residents concerns regarding safety of pedestrians. | Speeding concerns along Halstead Road, Stanway. | Cllr Scott-Boutell | Lexden | Traffic Management |  | LCOL162019 | N/A | 125m east of jw Dale Cl & Halstead Rd. Speed limit = 30mph. Eastbound av: 31.8mph Westbound av: 32.4mph Results do not warrant further investigation at this time.
Mersea Road jw The Willows, Colchester | Congestion has been identified at the junction of Mersea Road with The Willows. Vehicles exiting The Willows are experiencing lengthy delays trying to exit onto the PR1 route, Mersea Road. | Congestion, Parking, difficulty crossing the road. | Cllr Harris | Colchester | Traffic Management |  | LCOL162029 | TBC | In validation.
Holt Drive, Colchester | Local residents are experiencing difficulty crossing the road. | Difficulty crossing the road. | Cllr Bentley/Cllr Harris | Colchester | Traffic Management |  | LCOL162031 | N/A | Request for NEPP to investigate. Contact information passed to County Member.
Dedham Road, Dedham - Entrance signage | A request for gateway signs has been requested. To formally mark the boundaries of Dedham. | Perceived speeding identified. | Cllr Brown | Dedham | Traffic Management | Feasibility | LCOL162035 | 4000 | Validation recommends to do a feasibility in the first instance
Flagstaff Road, Circular Road East, Colchester | The shared pathway with cyclists is causing problems for children walking from St. Johns Green School being forced into the road by speeding cyclists. | Children forced into the road by cyclists. |  | Colchester | Traffic Management |  | LCOL162043 | TBC | In validation.
Whitehall Road, Colchester - Ped Crossing | Local residents are feeling very vulnerable and intimidated by large vehicles whilst trying to cross Whitehall Road by the junction of Grange Farm Road. | Residents feel intimidated and vulnerable in the middle of the traffic island. | Cllr Scordis | Colchester | Traffic Management |  | LCOL162046 | TBC | In validation - Pedestrian, vehicle conflict survey results = 0.213 x10>8. Data to feed into validation request. Possible Section 106 funding.
Blackheath, Colchester | Speeding issues have been reported along the stretch of Blackheath. With the surrounding schools, investigation into traffic calming has been requested. | Speeding issues reported. | Cllr Harris | Colchester | Traffic Management |  | LCOL162062 | TBC | Speed survey results do not meet the police intervention level. Southbound: 34.5mph Northbound: 33.4mph Panel instruction to progress via CMA. Validation report has suggested possible locations to site VAS. CMA report to be presented to Cabinet Member for decision once validation report has been finalised.
London Road jw Coach Road, Nayland Road, Little Horkesley - Cross road warning signs | Highway Surgery Action - Sightline issues raised. Road Safety confirmed heavy cutting of vegetation on private land would not resolve the issue. Suggested advanced cross road warning signs to be installed. | Sightline issue, route confirmed as a at run. | Cllr Brown | Little Horkesley | Traffic Management | N/A | LCOL162064 | N/A | Validation has not identified any viable engineering solutions - Sonia to speak to Road Safety further and report back.
Crown Street jw Manningtree Road, Dedham | Lack of footway, residents in the road, vehicle conflict has become an issue. | Lack of footway identified. | Dedham Parish Council | Dedham | Traffic Management |  | LCOL172002 | N/A | Validation recommends - Minimum footway not achievable due to lack of available highway land and nearby water course.
Stratford Road, Dedham | Many roads around Dedham are narrow, operational alternatives are required when needed. | Existing TRO prevents buses accessing the road. | Colchester bus project | Dedham | Passenger Transport | N/A | LCOL175003 | N/A | County Member has confirmed that this request was only relating to during road closures on surrounding roads. Sonia to pass to the Capital Suracing Team and NRSWA.
Trinity Street, Colchester | A signage review has been requested to further instruct vehicles. | Outdated signage. | Cllr Fisher | Non parished | Traffic Management |  | LCOL172005 | TBC | In validation.
Villa Road, Stanway | Local residents have raised that there are a lack of crossing points to aid elderly residents cross Villa Road. | Lack of crossing point identified. | Cllr L Scott-Boutell | Stanway | Walking |  | LCOL173002 | N/A | Awaiting County member approval
Tuffnell Way, Colchester | The surrounding estates are 20mph limits but the entrance to Tuffnell Way remains a 30mph limit. | Possible 20mph limit omitted. | Cllr Goss | Mile End & Highwoods | Traffic Management | Design | LCOL172007 | 6500 | Validation recommends undertaking the design and TRO in first year.
Hall Road, Tiptree | Conflict between vehicles and pedestrians has been reported along thin narrow lane. | Vehicle, pedestrian conflict. | Tiptree Parish Council | Tiptree | Traffic Management |  | LCOL172008 | TBC | In validation.
Axial Way, Colchester | Request for a formal crossing point to aid pedestrians to cross a busy road safely. | Lack of pedestrian crossing point identified. | Cllr Goss | Mile End & Highwoods | Walking |  | LCOL172011 | TBC | 40mph speed limit. Pedestrian, vehicle conflict score = 1.065 x 10^8. Survey score to allow for further investigation into a crossing point.
Church Road, Moat Road, Plummers Road, Fordham | The local Parish have received several complaints of speeding throughout the village. | Speeding issues reported. | Fordham Parish Council | Fordham | Traffic Management |  | LCOL172012 | N/A | Clean all existing repeater signage and request cutting back of any vegetation surrounding signage through the village.
London Road, Great Horkesley | Increase of vehicles through the village has caused issues with rural route. | Volume of traffic. | Cllr Brown | Great Horkesley | Traffic Management |  | LCOL172014 | N/A | Validation recommends - Vehicles are entitled to use an alternative route as it is public highway. No reported accidents, speeds are not above intervention levels. Scheme to not progress further at this time.
Priory Street, Colchester | Complaints received from residents on speed of vehicles. | Speeding issues reported. | Cllr Scordis | Non parished | Traffic Management |  | LCOL172017 | TBC | Awaiting informal residents consultation from County Member on physical traffic calming.
Mersea Road, Colchester - Dropped kerbs | Local residents with pushchairs and mobility scooters struggle to travel between 173 Mersea Road and Abbots Road due to narrowness of the footway and lack of dropped kerbs. | Lack of dropped kerbs identified. | Cllr Scordis | Non parished | Walking |  | LCOL173006 | TBC | In validation.
Bowes Road, Wivenhoe - Pedestrian Guard Rail | Parents and Teachers of Millfields are concerned with the lack of metal barriers and crossing points outside the School. | Lack of barriers and crossing point. | Cllr Young | Wivenhoe | Walking |  | LCOL172023 | TBC | In validation. - Pedestrian, vehicle conflict survey = 0.022 x 10^8. Survey score does not meet the intervention level for further investigation.. Pedestrian guardrail being investigated.
Victoria Road, Colchester | Resident complaints of vehicle speeds along road. | Speed of vehicles reported. | Cllr Lissimore | Non parished | Traffic Management |  | LCOL172024 | N/A | Speed limit: 30mph South eastbound: 17.3mph North westbound: 18.4mph Survey results do not meet the police intervention limit.
A134 Nayland Road, Great Horkesley | 1) Speeding issues reported at the southern entry point to village 2) Double mini roundabout signing and lining issues | Speeding, difficulty crossing the road, signage and lining. | Cllr Brown | Great Horkesley | Traffic Management |  | LCOL172025 | TBC | In validation. Speed limit: 30mph Southbound av: 38.7mph Northbound: 38.1mph Results to feed into validation request.
The Causeway, Great Horkesley | Residents with the Parish Council have reported: 1) Collisions and near misses reported at junction 2) Residents experiencing difficulties exiting their properties safely | Speeding, visibility issues. | Cllr Brown | Great Horkesley | Traffic Management |  | LCOL172026 | TBC | 140m s of jw Tog Lane / Boxted Church Lane, speed limit = 40mph. Southbound av: 40.4mph Northbound av: 41.4mph County Member has requested that a validation is still undertaken to ascertain if any recommendations can be made.
West Quay, Wivenhoe | Residents have raised safety concerns in relation to cyclists speeding along footpath, many near misses reported. | Conflict with cyclists and pedestrians on footpath. | Cllr Young | Wivenhoe | Traffic Management |  | LCOL174002 | TBC | In validation.
Chapel Road, West Bergholt | Resident complaints of perceived speeding, request to lower limit to 20mph. | Speeding issues reported. | Cllr Brown | West Bergholt | Traffic Management |  | LCOL172032 | TBC | Speed and volume survey results, 30mph speed limit: Av 22.9 mph Chapel Road, Colchester South Westbound mean av: 23.8mph North Eastbound mean av: 21.9 mph Results passed to the validation engineer
Beverley Road, Colchester | Complaints regarding speed of vehicles and lack of crossing points for pedestrians following recent accident. | Speeding issues reported, request for pedestrian crossing. | Cllr Lissimore | Non parished | Traffic Management |  | LCOL172033 | N/A | Degree of pedestrian, vehicle conflict study = 0.146 x10>8. Speed and volume survey results, 30mph speed limit: Beverley Road, Colchester Southbound mean av: 23.8mph Northbound mean av: 25.5mph Survey results do not meet the intervention level for further investigation at this time.
Langham Road, Colchester | Request for change in speed limit to 30mph | Speeding issues reported. | Cllr Brown | Boxted Parish Council | Traffic Management |  | LCOL172034 | TBC | Speed survey results. 40mph limit 65m NW of 40mph limit Southeast bound av: 38.2mph Northwest bound av: 37.0mph As this location is rural it would not meet the criteria for a 30mph speed limit.
Berechurch Hall Road, Colchester - Crossing signage | The Military have requested signage to alert vehicles that troops may be crossing in the area for training purposes. | Lack of warning signs. | Cllr Harris | Non parished | Traffic Management |  | LCOL172035 | TBC | In validation.
Normandy Avenue, Colchester | Local residents have requested dropped kerbing amendments are made to connect the footways at the western point junctions of Normandy Avenue. | Lack of drop kerbing identified. | Cllr Scordis | Non parished | Walking | Design | LCOL173009 | 4000 | Scheme to only progress to design and costing due to the statutory undertakers equipment at this location.
Phillip Road jw High Street, Wivenhoe | Request to look into moving or adjusting the current signage at this location. | The sign is seen as a visibility issue of vehicles exiting Phillip Road. | Cllr Young | Wivenhoe | Traffic Management | Total scheme | LCOL172036 | 7500 | Validation recommends - Remove blue sign and improve arrangement. Priority working sign to Diag 615 has its illumination unit missing leaving the wires exposed. Blue sign was mounted incorrectly above it.
Prettygate Road, The Commons, Parsons Hill and Church Lane, Colchester | Resident complaints of perceived speeding, request for drop in limit. | Speeding issues reported. | Cllr Lissimore | Non parished | Traffic Management |  | LCOL172038 | N/A | Validation recommends that this is an enforcement issue. Church Lane has existing VAS signs and physical traffic calming would not be recommended. Church Lane speeds were 37mph and 35mph averages. All other roads has average speeds under 30mph.
Winstree Road, Stanway | County Member has raised issues with speeding and congestion at peak times. School area with plenty of pedestrian and vehicle movement. | Speeding, congestion at peak times, pedestrian/vehicle conflict. | Cllr Bentley | Stanway | Traffic Management |  | LCOL172040 | TBC | Sonia to discuss with Councillor Bentley and the School Project Sponsor.
Footpath 185, Artillery Barracks Folley | Resurface footpath with blacktop and investigate existing cycle status | Uneven surface with loose bricks. | PROW team | Non parished | Public Rights of Way |  | LCOL178001 | TBC | PROW team gathering target cost for implementation of upgrade. Validation will be required for cycle element.
Posford Court, Colchester - Entrance gradient | Complaints have been received from residents of Posford Court regarding the gradient of the entrance. | Vehicles bottoming out of entrance to Court. | Cllr Turrell | Mile End & Highwoods & Highwoods | Traffic Management |  | LCOL172041 | TBC | In validation.
High Street, Dedham - Church footway | The chestnut tree outside of the Church is causing damage to the boundary wall and highway footway. | Chestnut tree roots damaging wall and footway. | Cllr Brown | Dedham | Walking |  | LCOL173011 | TBC | County Member supports the footway works as required but Church need to first arrange the moving of the wall.
Maypole Road, Tiptree - Crossing point | School Crossing Patrol no longer operates outside turntable School. The Parish have requested investigation into a formal crossing point. | Lack of crossing point. | Cllr Jowers | Tiptree | Walking |  | LCOL173012 | TBC | 30mph speed limit. Pedestrian, vehicle conflict score = 0.028 x 10^8. Survey score does not allow for further investigation into a crossing point.
Newbridge Road, Tiptree - TMI | Tiptree Parish Council have requested a speed and volume survey to be undertaken after the 30mph limit. | Speeding issues reported. | Cllr Jowers | Tiptree | Traffic Management |  | LCOL172042 | N/A | 250m e of jw Grove Rd. Speed limit = 30mph. Northeast bound av: 35.2mph Southwest bound av: 33.9mph Contrary to the guidance given in DFT circular 01/13.
Maldon Road, Tiptree - TMI | Tiptree Parish Council have requested a speed and volume survey to be undertaken by the obsolete VAS. Request for the implementation of a new VAS. | Speeding issues reported. | Cllr Jowers | Tiptree | Traffic Management |  | LCOL172043 | N/A | Speed limit = 30mph. 290m SW of jw West End Road / The Ship PH Southwest bound av: 34.9mph Northeast bound av: 33.9mph Contrary to the guidance given in DFT circular 01/13.
Straight Road, Colchester | A request has been received to look at speeds along Straight Road, Colchester. | There is a Pre School along Straight Road and there are concerns for pedestrians. | Cllr Lissimore | Non parished | Traffic Management |  | LCOL172055 | N/A | Speed limit - 30mph. 30m SW of jw Stoneleigh Park. Southbound av: 28.3mph Northbound av: 29.0mph Contrary to the guidance given in DFT circular 01/13.
Berechurch Hall Road jw Berechurch Road, Colchester - Footway link | Residents have requested investigation of a missing footway link between the footway entrance to Maypole Green Road and the footway to the south east on Berechurch Road. | Missing footway link identified. | Cllr Harris | Non parished | Walking |  | LCOL163014 | TBC | This overlaps with the feasibility study which is being completed at the moment - A
Cherry Tree Lane, Colchester | Residents experiencing difficulty using footway due to the lack of dropped kerbing. | Lack of dropped kerb identified. | Cllr Harris | Non parished | Walking |  | LCOL173013 | TBC | In validation.
Stanway Green Lodge, Stanway - Directional signage | Stanway Green Lodge have requested directional signage by Fiveways Fruit Farm to direct emergency services to the Lodge as sat navs do not pick up the address. | Lack of directional signage. | Cllr Bentley | Stanway | Traffic Management |  | LCOL172053 | TBC | In validation.
High Street, Wivenhoe - Zebra crossing | Request for a zebra crossing. | Pedestrians are struggling to cross High Street, Wivenhoe. | Cllr Young |  |  |  | LCOL173018 |  | Degree of pedestrian vs vehicle conflict study = 0.057 x10>8. It is against criteria to install a zebra crossing in this location.
Langham Road, Runkins Corner, Boxted | Local residents have concerns over the corner as vehicles are reported to regularly leave the carriageway and enter the ditch. The road falls away at the exit of the corner. | Vehicle accidents reported. | Langham/Boxted Parish Council | Boxted Parish Council | Traffic Management | Total scheme | LCOL172054 | 7500 | De-restricted limit. 1m NW of jw Severalls Lane. Southeast bound av: 35.2mph Northwest bound: 35.6mph Recommendation to improve existing signage in the first instance. No S106 money.
Norman Way, Colchester | The shape of the layby does not allow for buses to enter and exit the layby safely. | Buses unable to stop safely. | Passenger Transport | Non parished | Passenger Transport | Total scheme | LCOL175013 | TBC | In validation.
East Road, East Mersea | Resident complaints of vehicle speeds along road. | Speeding issues reported. | Cllr Bentley | East Mersea | Traffic Management | N/A | LCOL172030 | N/A | Speed limit = 40mph Eastbound av: 37.3mph Westbound av: 36.1mph Validation recommendation - The recorded average speeds are lower than 40mph. A Cabinet Member Action will be required to progress the request.
Scheregate Steps, Colchester | Request to amend the layout of the steps to cater for a disabled access. | Pedestrians using mobility scooters or in wheel chairs have to take a long route to Sir Isaacs Walk | Cllr Sue Lissimore | Non parished | Walking |  | LCOL183001 | TBC | Validation - Lack of available space, desired fall would be exceeded by a substantial amount which would be extremely unsafe.
Crown Street, Dedham | Large number of elderly residents that are experiencing difficulties accessing the bus due to the lack of even standard kerbing. | Lack of raised kerbing. | Chris Seamen | Dedham | Passenger Transport | Total scheme | LCOL185001 | TBC | In validation.
Glen Avenue, Colchester | Requests to reduce the current speed limit. | There are concerns over the current speed limit | Cllr Lissimore | Non parished | Traffic Management |  | LCOL182002 | TBC | 85m N of jw Eleanor Ave Speed limit = 30mph Southbound av: 28.6mph Northbound: 30.8mph Survey results do meet the police interception levels. 20mph limit policy not met. PV2: 0.012 X 108 Therefore doesn’t not meet the requirements for a zebra
Head Street, Rowhedge | Raised kerbing requires extension or reposition to allow for less abled bodies to enter/exit the bus. | Lack of raised kerbing. | Cllr Bentley | East Donyland | Passenger Transport | Total scheme | LCOL185002 | TBC | In validation
Villa Road, Stanway | A safety barrier has been requested outside the school between the entrance and the carriageway. | Request for barrier. | Cllr Bentley | Stanway Parish Council | Traffic Management | Total scheme | LCOL182004 | 5500 | 2 x 2m guardrail could be installed at this location if the County Member supports it. Sonia to check this with Cllr Bentley.
Tollgate Road, Stanway | Local residents have reported speeding issues. Request to consider lowering the limit. Also they would like a safe crossing point linking the two public right always. | Speeding vehicles and lack of safe crossing point. | Cllr Bentley | Stanway Parish Council | Traffic Management |  | LCOL182005 | TBC | 160m S of Homebase Roundabout 30mph speed limit. Number of vehicles 83,243 average of 35.5MPH Southbound av: 36.5 Mph Northbound av: 34.6 Mph
B1022 Maldon Road, Colchester | Request for a 20mph speed limit or possible traffic calming features. | Speeding vehicles. | Cllr Lissimore | Non parished | Traffic Management |  | LCOL182006 | TBC | Previous speed and volume survey results, 30mph speed limit. Eastbound av: 37.3mph Westbound av: 36.1mph
Bracken, Broom & Meadow Way, Abberton | Request from the County Member to investigate a 20mph limit or zone. | Speeding issues reported. | Cllr Bentley | Abberton | Traffic Management |  | LCOL182007 | TBC | 40 m S of j/w Broom way Speed limit = 30mph Southbound: 14.2 mph Northbound: 12.0 mph Total volume recorded 962. data showing 0% exceeded the speed limit on Bracken Way
St. Faith Road jw St. Monance Way, Colchester | Request for dropped kerbing by St. Fillings care centre. | Lack of dropped kerbing identified. | Cllr Baker | Non parished | Walking |  | LCOL183002 | TBC | In validation.
Peartree Road, Stanway | A request has been received for the investigation into a crossing point. | Lack of crossing point identified. | Cllr Scott-Boutell | Stanway | Walking |  | LCOL183003 | TBC | 40 m W of Co-op mini roundabout access Speed limit = 30mph Eastbound av: 24.3 mph Westbound: 25.8 mph. This shows that having a pedestrian crossing potential as v2 scored 0.458
D'arcy Road, Colchester | Request for a salt bin for the local residents. | Steep gradient road. Lack of grip in cold weather. | Cllr Scordis | Non parished | Walking |  | LCOL183004 | TBC | In validation.
Seaview Avenue jw Westwood Drive, West Mersea | Request for a salt bin for the local residents. | Steep gradient road. Lack of grip in cold weather. | Cllr Jowers | West Mersea | Walking |  | LCOL183005 | TBC | In validation.
London Road/Birch Road, Copford | The Parish Council are requesting clear Copford Boundary signage with gateway feature. | Lack of signage to identify Parish. | Cllr Bentley | Copford | Traffic Management |  | LCOL182008 | TBC | In validation.
Halstead Road, Stanway | Borough Councillor is requesting investigation into a safe crossing point for residents between Dale Close and Butterfly Trail. | Lack of formal crossing point. | Cllr Scott-Boutell | Stanway | Walking |  | LCOL183006 | TBC | Awaiting pedestrian, vehicle conflict survey results.
Spring Lane & Wood Lane, Eight Ash Green | The Parish Council have requested two speed and volumes surveys to be undertaken initially on the two routes. | Speeding issues have been identified. | Eight Ash Green Parish Council | Eight Ash Green | Traffic Management |  | LCOL182009 | TBC | Awaiting speed and volume information.
Churchfields Avenue, Stanway | A 20mph zone end/30mph signage is required as this was not implemented when a new development was built. | Current no 30mph signs exiting the estate | Cllr Scott-Boutell | Stanway | Traffic Management | Total scheme | LCOL182010 | TBC | In validation.
Lexden Road, West Bergholt | Local and school buses are often found parked at the top end of Lexden Road by the junction with Colchester Road causing congestion and visibility issues. | Reinstatement of yellow bus cages. | West Bergholt Parish Council | West Bergholt | Passenger Transport |  | LCOL185005 | TBC | In validation. This is likely to be just bus cages Passenger Transport team to investigate further with school bus companies
Western Bypass, Stanway | Stanway Parish Council require investigation into a crossing point on the Western Bypass | Lack of formal crossing point identified. | Stanway Parish Council | Stanway | Walking |  | LCOL183014 | TBC | 85m S of j/w Osprey Close Speed limit = 40mph Southbound av: 41.4 mph Northbound: 40.3 mph. This shows that having a pedestrian crossing potential as v2 scored 0.015 Does not meet criteria.
Station Road, Wivenhoe | Improvements to the bus stop area | Bus turning movement hinders alignment with the Kassel kerbs | Cllr Young | Wivenhoe | Passenger Transport | Total scheme | LCOL185006 | TBC | In validation.
Station Road, Wivenhoe | Improvements to rail station, with the installation of a passenger shelter | Lack of shelter | Cllr Young | Wivenhoe | Passenger Transport | Total scheme | LCOL185007 | TBC | Awaiting road improvement until shelter location
B1026 Colchester road, Tiptree | Wheelchair users unable to use public transport (buses) due to lack of accessibility | Lack of raised kerbing. | Parish Council | Tiptree | Passenger Transport | Total scheme | LCOL185008 | TBC | Awaiting further information from County Member. Request is from Parish Council but to cater for one disabled resident. Scheme could be costly.
Newcastle Avenue, Colchester | Speeding, causing difficulty to cross the road | Crossing the road. | Cllr Sue Lissimore | Non parished | Traffic Management |  | LCOL182011 | TBC | in validation
Grange Way, Colchester | Difficultly getting onto Whitehall Road . | Pulling into new road | Cllr lee Scordis | Non parished | Traffic Management |  | LCOL182012 | TBC | in validation
Cowdray way Avenue, Colchester | Wheelchair users unable to cross the road to access park or fire station. | Lack of dropped kerbing identified. | Cllr lee Scordis | Non parished | Walking |  | LCOL183008 | TBC | in validation
New Road/Brook Road and Ford Street, Constable | Problems with speeding vehicles | Speeding vehicles reported. | Cllr Anne Brown | Aldham | Traffic Management |  | LCOL182013 | TBC | Awaiting 5 residential properties supporting from Cllr Brown. Awaiting speed and volume survey locations.
West End Road, Tiptree | Dangerous parking on the junction of Maldon road | Dangerous parking causing poor visibility when turning into west end road. Danger for pedestrian crossing the road. | Cllr John Jowers | Tiptree | Traffic Management |  | LCOL182014 | N/A | Referred to NEPP as this is a parking issue.
Church Street, Abbey | Large vehicles hitting the buildings in narrow street. | Lack of signage to identify how narrow. | Cllr lee Scordis | Non parished | Traffic Management |  | LCOL182015 | N/A | Unable to complete the request, as signage can not be placed on the junction. In validation to see potential improvements
Reynolds Avenue, Drury | Wheelchair users unable to cross the road, near high school | Lack of dropped kerbs for access. | Cllr Sue Lissimore | Non parished | Walking |  | LCOL183009 | TBC | in validation
Lisle/Canterbury/Winchester Road, Colchester | Lorries using narrow estate to make shortcuts on journeys causing difficulty on bends. | No 'HGV' sign. | Cllr Lee Scordis | Non parished | Traffic Management |  | LCOL182016 | TBC | Awaiting approval from residents, and where the HGV's are going in and out of the estate.
St. Marks Drive, Fp105, Colchester | Footpath immediately north of St Mark's Drive, improve the surface | Large standing puddles on footway | Cllr John Baker | Non parished | Public Rights of Way |  | LCOL188001 | 6000 | In validation
Lilac Cottage, Colchester Road. Tiptree | Problems with speeding vehicles | Difficulty for car pulling out of their drives | Cllr John Jowers | Non parished | Traffic Management |  | LCOL182017 | TBC | Tiptree Parish Council are in consultation with local residents about proposed speeding issue. In order to gain 5 of more properties in agreement on the issue to proceed. Vegetation removal would improve the visibility.
Maldon Road, Tiptree | Problems with speeding vehicles | Speeding vehicles reported. | Cllr John Jowers | Tiptree | Traffic Management |  | LCOL182018 | N/A | 492 m NE of j/w Braxted Road Speed limit = 60mph Southwest: 37.8 mph Northeastbound: 43.3 mph. Showing good compliance to the speed limit.
Salcott Crossroads, Colchester road | Wheelchair users unable to use public transport (buses) due to lack of accessibility. | No raised kerbs | Cllr John Jowers |  | Traffic Management |  | LCOL182019 | TBC | In validation
Station Road, Wakes Colne | Increased traffic flow and speeding on a narrow road. | Difficulty for pedestrians walking on paths due to school access | Cllr Anne Brown | Wakes Colne | Traffic Management |  | LCOL182020 | TBC | In validation - The Engineer will look at the parishes proposals and revist the feasability.
Old Heath Road, Colchester | Difficult for pedestrians to cross the road. | Crossing the road safely | Cllr lee Scordis | Unparished | Walking |  | LCOL183010 | TBC | Awaiting Residents approval before proceeding with Pv2. Is must be noted that Distillery Lane is not a PROW.
Roman/ Castle Road, Colchester | Implementation of Salt bins. | Residents don’t have storage room to hold salt grit | Cllr lee Scordis | Unparished | Traffic Management |  | LCOL182021 | TBC | In validation.
Athelstan Road, Colchester | Implementation of 20 MPH zone. | vehicles speeding during school time | Cllr Sue Lissimore | Unparished | Traffic Management |  | LCOL182022 | TBC | In validation
Irvine Road, Colchester | Implementation of 20 MPH zone. | vehicles speeding during school time | Cllr Sue Lissimore | Unparished | Traffic Management |  | LCOL182023 | TBC | Average Speeds are below 21mph Now in validation
Rectory Hill, Wivenhoe | VAS reported as faulty. Investigation required. | VAS reported faulty. | Cllr Young | Wivenhoe | Traffic Management | Surveys | LCOL182001 | 337 | Battery replaced. VAS repaired.
Station Road, Wakes Colne | VAS reported as faulty. Investigation required. | VAS reported faulty. | Wakes Colne Parish Council | Wakes Colne | Traffic Management | Surveys | LCOL182001 | 1452 | Replaced control board. VAS repaired.
Dunnock Way, Colchester | Motor bike users using the footpath as a cut through point. | Inappropriate use of the footpath | Cllr John Baker | Unparished | Walking |  | LCOL183011 |  | In validation
Circular Road North, Colchester | Crossing the roads safety and investigation in existing build out. | Cars speeding | Cllr Sue Lissimore | Unparished | Traffic Management |  | LCOL182024 |  | Awaiting scheme request form from County Member
Blackberry Road, Colchester | Improvement requested to the existing crossing | Difficulty crossing the road | Cllr Scott-Boutell | Unparished | Walking |  | LCOL183012 |  | Awaiting Cllr Bentley's approval
Myland School Crossing, Mill Road | Drivers failing to stop at the crossing | Difficulty crossing the road | Cllr Goss | Unparished | Walking |  | LCOL183013 |  | in validation - There is no S106 within the area that can be used for any improvements.
Hall Road/London Road, Copford | Implementation of a no through road sign at the junction of hall road and London road | Sign removed when road was resurfaced | Easthorpe Parish Council | Copford | Traffic Management |  | LCOL182025 |  | Awaiting Cllr Bentley's approval
School road/London Road , Copford | Implementation of a 30mph sign repeater | Speed campaigns showing cars speeding | Easthorpe Parish Council | Copford | Traffic Management |  | LCOL182026 |  | Awaiting Cllr Bentley's approval
Mill Road j/w Bedford road, Colchester | Request for a mini roundabout | Perceived speeding problems | Cllr Goss/Turrell |  | Traffic Management |  | LCOL182027 |  | Received request and residential support - speeds surveys are being ordered.
Ransom Road, Tiptree | No entry and one way traffic' signs have been placed and cars are ignoring the signs | Enforcement issue | Cllr Wood | Tiptree | Traffic Management |  | LCOL182028 |  | This scheme has been assessed by the validation team and all signs that should be in place are correct. The Sat Nav companies have also been contact and google now shows this as a one way street.
Perry Lane/ Grove Hill, Colchester | Signage instructing eventually garage | Movement of signage | Cllr Brown |  | Traffic Management |  | LCOL182029 |  | In validation
Villa Road, Stanway | 20mph zone outside of Stanway primary school | Speeding | Cllr Scott-Boutell | Stanway | Traffic Management |  | LCOL182030 |  | Awaiting Cllr Bentley's approval
Maldon Road, Tiptree | Vehicles speeding | Speeding | Cllr John Jowers | Tiptree |  | Surveys | LCOL182018 | 200 | Previously rejected scheme, beginning to investigate a 40MPH buffer
Waterside Lane, Abbey | Salt bin installation | Ungritted Roads | Cllr Lee Scordis | Abbey | walking |  | LCOL183015 |  | In Validation
Causton Road, Abbey | No HGV' signage | Large vehicles using narrow roads | Cllr Lee Scordis | Abbey | Traffic Management |  | LCOL182031 |  | Sonia emailed Cllr Scordis with why we cannot proceed with this scheme. Cllr Scordis has still asked for a validation.
Park Lane, Langham - New footway | Feasibility Study to investigate approx. 126 metres of new footway from the A12 up to the village green. |  | Langham Parish Council | Langham |  | Surveys |  | 800
London Road and School Road, Copford | Would like to install 30mph repeater roundels along both London Road and School Road | Vehicles speeding | Copford and Easthorpe | Copford | Traffic Management |  | LCOL182032 |  | The area is street lit and cannot have repeater signs.
VAS Repairs. Boxted Road, Mile End near junction with United Way. SOL988 | Investigated and repairs upto £500 | VAS reported faulty. | Cllr Goss | Mile End |  | Surveys |  | 528 | Customer Non-Conformance Agreement sent to Solagen
VAS Repairs. Halstead Road, Stanway, SOL1886 | Investigated and repairs upto £500 | VAS reported faulty. |  | Stanway |  | Surveys |  |  | Customer Non-Conformance Agreement sent to Solagen
Mersea Road Bus Stop junction with Bourne Court with Mersea Road | Implementation of a bus shelter outside of the Mersea Road cemetery gates | No bus shelter facilities for users of the service | Cllr Harris | Maypole | Passenger Transport |  | LCOL185008 |  | Awaiting information before proceeding with the validation form
School Road, Monkwick | Traffic calming to protect children by the school | Students at high risk of highly dense traffic | Cllr Harris | Maypole | Traffic Management |  | LCOL182033 |  | Awaiting residents support to be provided by Cllr Harris
Colchester Road B1508, Mount Bures | Speed reduction and traffic calming to protect pedestrians on the junction of brook house lane/hall road | Speeding vehicles | Cllr Anne Brown | Constable | Traffic Management |  | LCOL182034
Bergholt Road, Mile End | Regular complaints of vehicles speeding, They would like a VAS to be implemented | Speeding vehicles | Cllr Goss | Mile End | Traffic Management |  | LCOL182035 |  | Awaiting speed and volume results
Bergholt Road, Mile End | Speed and Volume Survey | Speeding vehicles |  | Mile End |  | Surveys | LCOL182035 | 200
Bergholt Road, Mile End | Keep clear signage outside enterance of the vets parking area. Traffic queues on Bergholt Road to enter North Station junction | Causing traffic congestion | Cllr Turrell | Mile End | Traffic Management |  | LCOL182036
Weir Lane, Rowhedge | Road full of pot holes causing damage to vehicles | Poor road condictions |  | Rowhedge | Safer Roads |  | LCOL181003