## Sheet1
Chelmsford City Local Highway Panel - Potential Schemes List - November 2018
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
Highwood Road Edney Common to Loves Green, including St Pauls Church | Pedestrian footway - 1.2m walkable verge, crossing point at Highwood Road and removal of informal layby at St Paul's Church, estimated cost £105,000 next stage detailed design | Lack of footway/walkable verge | Parish Council | Highwood | Traffic Management | Design | LCHE142040 | 3500 | Technical Note (costing £4,000) previously shared with Panel March 2015
High Street, Stock | Route enhancement study | Speed of traffic | Parish Council | Stock | Traffic Management | Feasibility | LCHE132043 | 3000 | Validation - Feasibility Study suggested following request for 20mph speed limit/average speed camera
Essex Records Office, Chelmsford | Signage improvements to (1) vehicular access to ERO on Navigation Road and (2) outside pedestrian entrance to ERO | Lack of signage | Councillor | Chelmsford Non Parished | Traffic Management | Total scheme | LCHE142085 | 750 | Validation - Site (2) agreed and Site (1) not necessary as building visible from location. Section 106 monies to be considered if available
Brookmans Road j/w Back Lane, Stock | Bollards on verge to prevent verge damage | Vehicles damaging verge | Parish Council | Stock | Traffic Management | Total scheme | LCHE142089 | 36000 | Validation - Option 1 approach Parking Partnership for junction protection parking restrictions, Option 2 reduce width of verge, install HGV overrun to allow easier turning for larger vehicles
Sporhams Lane, Danbury | Width restriction on road, to prevent goods vehicles damaging verges | Vehicles damaging verges | Parish Council | Danbury | Traffic Management | Total scheme | LCHE142092 | TBC | In validation - Need to await results of request for Quite Lane status
Chelmer Park Cycle Route, Beehive Lane, Galleywood | Shared footway/cycleway on Beehive Lane between Skinners Lane and Chelmer Car Park | Lack of cycle network connectivity to Galleywood | Cycling team | Galleywood | Cycling | Design | LCHE154002 | 8000 | Priority Scheme for LHP in terms of Chelmsford Cycling Action Plan, estimated scheme cost £227,000
Longstomps Cycleway, Chelmsford | Create shared footway/cycleway | Improvements to National Cycle Route 13, along busy section of Longstomps | Cycling team | Chelmsford Non Parished | Cycling | Total scheme | LCHE154003 | 142000 | Not a priority scheme within Chelmsford Cycling Action Plan
Writtle Cycle Route, Writtle | Solar lights/studs at 10m intervals | Mainly rural unlit route | Cycling team | Writtle | Cycling | Total scheme | LCHE154005 | 21500 | Priority Scheme for LHP in terms of Chelmsford Cycling Action Plan
West Park, Chelmsford | Install a 3.5m replacement bridge on existing alignment | Design of replacement footbridge currently not part of Highways Network, which would need to be addressed | Cycling team | Chelmsford Non Parished | Cycling | Design | LCHE154006 | 8000 | Validated by Cycling team, estimated scheme cost £65,000
Sporhams Lane, Sandon | Suggestion to be classified as a Quiet Lane | Narrow lane, often used as a "rat run" or short cut | Parish Council | Sandon | Traffic Management | Total Scheme | LCHE152012 | TBC | In validation - Awaiting impact of five Quiet Lanes currently being implemented in County
School Road, Good Easter | 7.5T environmental weight limit | Goods vehicle using route as an alternative route damaging road | Parish Council | Good Easter | Traffic Management | Surveys | LCHE152017 | 3000 | Validation - Reintroduced to Panel - Speed/volume data shows HGV's usage very low. Unsuitable for HGV signage considered not recommended as this road is similar to others in the vicinity and could lead to excessive blue signs. Parish Council have asked for scheme to be considered by the Panel. Next stage would be for HGV Origin and Destination Survey using Automatic Number Plate Recognition cameras
Lordship Road j/w Fox Burrows Lane, Writtle | Feasibility Study into junction/carriageway improvement | Recommendation from Route Enhancement Study | Parish Council | Writtle | Traffic Management | Feasibility | LCHE152088 | 5000 | Recommendation from Route Enhancement Study, suggestion is to await results of any future development on Fox Burrows Lane
Writtle College Main Access, Lordship Road, Writtle | Feasibility Study into carriageway/footway /signing/lining/street lighting/verge improvements | Speed/volume of traffic | Parish Council | Writtle | Traffic Management | Feasibility | LCHE152089 | 5000 | Recommendation from Route Enhancement Study
Chignal Hall Lane j/w Mashbury Road, Chignal Smealy | Remove bennet junction | Existing verge being overrun dragging mud onto road | Parish Council | Chignal Smealy | Traffic Management | Feasibility | LCHE152093 | 3000 | Validation - Feasibility/design recommended into junction improvement options
29-59 North Avenue, Chelmsford | Improved parking | Lack of residents parking | Residents | Chelmsford Non Parished | Traffic Management | Feasibility | LCHE152095 | 5000 | Validation - Option to encourage residents to apply for dropped kerbs and park on their frontage and Feasibility Study/Design into creating parking within adjacent green area
Old Moulsham, Chelmsford | 7.5 tonne environmental weight limit | Delivery vehicles for Moulsham Street routinely driving through Old Moulsham | Residents | Chelmsford Non Parished | Traffic Management | Feasibility | LCHE152096 | 10000 | Validation - Recommends Feasibility Study into 7.5t environmental weight limit, to include HGV traffic surveys and details of any delivery vehicles using Old Moulsham to access Moulsham Street shops
Lawn Lane near junction with Orford Crescent, Springfield | Improved pedestrian crossing facilities | Pedestrians having difficulties crossing | Councillor | Springfield | Traffic Management | Total scheme | LCHE182055 | TBC | In validation - Degree of pedestrian conflict survey carried out results 0.482x10^8 feeding into validation process. Existing tree currently obscure sight line. New PV² at adjacent crossing point 60m north of this location value 0.672x10^8
S/o Vita Bella, The Tye, East Hanningfield | Footway widening works - kerbing/resurfacing to open up full width | Narrow footway for pedestrians | Parish Council | East Hanningfield | Traffic Management | Feasibility | LCHE152105 | 3000 | Validation - Feasibility Study into footway widening to consider extent of highway, statutory undertakers apparatus and fully cost any scheme proposal
Admirals Park Estate, North-West Chelmsford (Boarded Barns) | 20mph zone | Speed of vehicles | Councillor | Chelmsford Non Parished | Traffic Management | Total scheme | LCHE152115 | TBC | In validation - Four ATC carried out - Corporation Road - 30mph speed limit - East bound 26.7mph & West bound 27.4mph, Swiss Avenue - 30mph speed limit - East bound 25.5mph & West bound 27.4mph, Langton Avenue - 30mph speed limit - South bound 25.4mph & West bound 24.6mph, Kings Road - 30mph speed limit - Southwest bound 25.4mph & Northeast bound 26.1 mph. Good compliance with existing 30mph speed limit. Remaining 26 ATC will cost £6,500. Need to await impact of Old Moulsham 20 mph speed limit.
Bridleway 10, Mill Lane Ramsden Heath | Bridleway 10 South Hanningfield surface improvements | Boggy and uneven surface in sections makes bridleway a difficult route to follow for some users | PRoW team | South Hanningfield | Public Rights of Way | Total scheme | LCHE158003 | 21500 | Validated by Public Rights of Way team
Bridleway 11 Margaretting | To create a link between Bridleway 11 and Bridleway 44/54 | Bridleway 11 cut off by A12 | PRoW team | Margaretting | Public Rights of Way | Total scheme | LCHE158004 | 35000 | Validated by Public Rights of Way team
Great Leighs Footpath 41 (Part of The Essex Way) | Surfacing and Drainage improvements | Water meadow/natural springs affecting a well used PRoW | PRoW team | Great Leighs | Public Rights of Way | Total scheme | LCHE158006 | 40000 | Validated by Public Rights of Way team
Little Waltham Footpath 28 | Surfacing and Drainage improvements - 365m length and average 2m width | Path is routinely very muddy throughout the year | PRoW team | Little Waltham | Public Rights of Way | Total scheme | LCHE158007 | 30000 | Validated by Public Rights of Way team
Footpath 63, South Hanningfield | Footpath surface improvements with planings | Footpath surface in need of improvement | PRoW team | South Hanningfield | Public Rights of Way | Total scheme | LCHE158010 | 10000 | Validated by Public Rights of Way team
Main Road (at northern Broomfield Parish boundary), Broomfield | Village Gateway Treatment | Lack of Village Gateway feature to define entry to Broomfield | Parish Council | Broomfield | Traffic Management | Total scheme | LCHE142002 | 7500 | Parish Council has agreed for scheme to be considered once any changes at adjacent roundabout have been finalised
Penny Royal Road/Mayes Lane to Woodhill Road, Danbury | Implementation of footway to link two parts of Village | Lack of footway/walkable verge | Parish Council | Danbury | Walking | Total scheme | LCHE163005 | 90000 | Estimated costs, design under review
Stock Rd/Ship Rd, Holiday Hill/Blind Ln, Church Rd, Middlemead/ Broadmead, West Hanningfield | Road/Depth markers | Flooding sites | Parish Council | West Hanningfield | Traffic Management | Total scheme | LCHE162137 | 6000 | Validation - Feasible to install water depth markers though this would not address cause of flooding.
Stump Lane, Chelmsford | Footway improvements | Narrow footway for pedestrians over railway bridge | Councillor | Chelmsford Non Parished | Traffic Management | Feasibility | LCHE152126 | 5000 | Validation - Recommends Feasibility Study into priority working and to then consider footway widening
Hall Lane, West Hanningfield | Suggestion to be classified as a Quiet Lane | Speed of traffic | Parish Council | West Hanningfield | Traffic Management | Total scheme | LCHE152123 | TBC | In validation - Speed data in 40mph limit Northeast - 26.3mph/Average 82 vehicles a day and Southwest 25.7mph/Average 60 vehicles a day. Awaiting impact of five Quiet Lanes currently being implemented in County
Highwood Road, Edney Common to Loves Green | 50mph speed limit | Speed of traffic | Parish Council | Writtle | Traffic Management | Total scheme | LCHE152124 | 14500 | Validation - Speed data - 60mph speed limit - 150m SW of A414 - Northeast bound - 41.5mph & Southwest bound - 37.5mph, 930m SW of A414 - South bound - 46.4mph & 49.9mph, 560m Northeast of Nathans Lane - Northeast bound - 46.5mph & Southwest bound - 46.6mph. Based on speed data - 30mph limit near A414 not feasible as recorded speeds are too high, also environment of road would not assist a 30mph limit as properties not apparent to drivers. It could though be possible to consider a 50mph limit, which may reduce some of the higher speeds along the road
Springfield Green/Timsons Lane | Options to improve connection of existing routes | Lack of connectivity | Cycling team | Chelmsford non Parished | Cycling | Total scheme | LCHE164015 | 298000 | Priority Scheme for LHP in terms of Chelmsford Cycling Action Plan
The Tye (nr j/w Old Church Road/Main Road), East Hanningfield | Kerbing and verge reinstatement | Vehicles over running verge and causing damage | Parish Council | East Hanningfield | Traffic Management | Design | LCHE152113 | 3000 | Validation - Kerbing introduced previously on western side of road. Recommendation is for detailed design, obtaining statutory undertakers apparatus drawings and road safety audit. This will provide a feasible design and an accurate target cost
Hatchfields, Great Waltham | Parking lay-by | Lack of parking within Village | Parish Council | Great Waltham | Traffic Management | Feasibility Study | LCHE162148 | 3000 | Validation - Suggested area for parking is owned by Parish Council, who could create parking on this land subject to any necessary planning/highway agreements needed. Limited parking restrictions within Village. Could carry out Feasibility Study at £3,000 but scheme costs could be very high and would need any land dedicated as highway
Chelwater, Great Baddow | Traffic management improvements | Speed of vehicles on access road and existing street lighting | Councillor | Great Baddow | Traffic Management | Survey | LCHE162151 | 1500 | Validation - This is an access road to a small group of properties. In first instance any speeding issues should be raised through Police. A street lighting survey could be carried out to determine lux levels of existing lights to see if they are emitting enough light, if not it could be a maintenance issue to upgrade the lighting heads
Lordship Road, Writtle | Pair of bus stops, raised kerbs flags/poles | Lack of bus stops at Doctors Surgery | Passenger Transport team | Writtle | Passenger Transport | Feasibility | LCHE165032 | 4000 | Re-assessed by Design Team, recommendation is now for feasibility study and informal consultation
Heath Road, Ramsden Heath | Replacement bus shelter | Existing shelter is at the end of its life | Parish Council | Ramsden Heath | Passenger Transport | Total scheme | LCHE165033 | 14000 | Validated by Passenger Transport team - Scheme includes removal of existing shelter, new base and then new shelter
School Road (Crowsheath Lane to Village Hall), Downham | Traffic management improvements | Speed of traffic within 30mph speed limit | Parish Council | South Hanningfield | Traffic Management | Total scheme | LCHE162162 | 28000 | Validation - 30mph speed limit, Southeast bound 33.5mph and Northwest bound 33.5mph. Recommendation was to carry out Feasibility Study into traffic calming options. Further validation work now recommends three Village gateway treatments and size/frequency improvements to existing 30mph speed limit repeater signage
Chatham Green, Little Waltham | 30mph speed limit through Hamlet | Speed of traffic | Parish Council | Little Waltham | Traffic Management | Total scheme | LCHE172027 | 23000 | Validation - Speed data Chatham Green 60 mph South bound 21.1mph & North bound 19.8 mph - Feasible to implement a 30mph speed limit but there would need to be 30mph signs at either end of the new limit and repeater signs along the new limit, Change in speed limit would also require a formal consultation where objections may be made.
PROW Footpath 95 Chelmsford | Investigation on-going into installing drainage in existing surfaced city centre footpath | PROW improvement | PRoW team | Chelmsford Non Parished | Public Rights of Way | Total scheme | LCHE148002 | TBC | Awaiting results of 2018/19 Feasibility Study
A132 Burnham Road, Rettendon, O/s Hayes Country Park | Traffic management improvements | Lack of bus service to Residential Park and pedestrian crossing facilities | Residents | Rettendon | Traffic Management | Total scheme | LCHE172009 | TBC | In validation - Awaiting results of A131 Route Based Strategy
Court Road j/w Main Road, Broomfield | Traffic management improvements | Problems at peak times with egress of traffic from Court Road onto Main Road | Residents | Broomfield | Traffic Management | Total scheme | LCHE172010 | 6000 | Validation - Recommendation to install KEEP CLEAR road marking on Main Road to allow vehicles to turn out of Court Road onto Main Road
Church Lane j/w Lawn Lane, Springfield | Phase 2 - Cycle link/junction improvements - 3m shared cycleway across Park | Need for cycling improvements | Safer roads team | Springfield | Cycling | Total scheme | LCHE174002 | 119000 | Draft Design presented at June 2017 Panel meeting. Phase 1 implemented in 2018/19
Lodge Road/Bridge Street/The Green/St Johns Green, Writtle | Traffic management improvements | Concerns around junction | Parish Council | Writtle | Traffic Management | Total scheme | LCHE162178 | TBC | In validation - Three PV² surveys feeding into scheme validation
Bell Street, Great Baddow | Footway improvements | Lack of footway | Parish Council | Great Baddow | Traffic Management | Surveys | LCHE162179 | 500 | Validation - If Panel wish to consider a scheme first stage would be a camera survey to determine pedestrian usage, resulting scheme could be expensive and affect parking. Also alternative route along High Street/Pump Hill is only 50m longer.
Maldon Road, Great Baddow | Dropped kerb improvements | Improvements to existing crossing point | Parish Council | Great Baddow | Traffic Management | Total scheme | LCHE162181 | 5000 | Validation - Recommendation is for tactile paving
The Bringey, Great Baddow | Pedestrian guard railing at Baddow Hall Junior School | Pedestrians exiting school in possible conflict with vehicles | Councillor | Great Baddow | Traffic Management | Total scheme | LCHE162185 | TBC | In validation - School pedestrian entrance is off a Public Right of Way (Footpath 20) with agreement of land owner staggered barriers could be put in front of school entrance. School confirm land between footpath and school not theirs.
Vicarage Road, Skreens Park Road and Stonehill Road, Roxwell | Village Gateway treatments | Speed of traffic | Parish Council | Roxwell | Traffic Management | Total scheme | LCHE172045 | 26500 | Validation - Gateway treatments and speed limit signing improvements
The Green, Writtle | Pedestrian crossing improvements | Pedestrian safety | Councillor | Writtle | Traffic Management | Design | LCHE172041 | 7000 | Validation - PV^ 2 0.2x10^8. Site does not lend itself to installation of zebra crossing. As such suggestion is design only as scheme year 1 and then look at implementation in year 2, though scheme costs could be £71,500
Pratt's Farm Lane j/w Domsey Lane, Little Leighs | HGV signage improvements | Signage too low for HGV's | Parish Council | Little Leighs | Traffic Management | Total scheme | LCHE172042 | 2650 | Validation - Provide new Unsuitable for HGV sign on higher post, will also require some vegetation to be cut back
The Green nr j/w Ongar Road, Writtle | Measures to stop verge damage | Vehicles routinely over-running the verge | Parish Council | Writtle | Traffic Management | Total scheme | LCHE172044 | 6500 | Validation - Suggestion as to extend bus cage not favoured by Parish Council. Looking at other options
Church Green, Broomfield | Kerbing | Wooden sleepers need replacing | Parish Council | Broomfield | Traffic Management | Feasibility | LCHE172020 | 4000 | Validation - Study to consider options, needs to address land ownership as possible Village Green, also include consultation with Conservation Officers and Arboriculture Officers
The Square j/w High Street, Stock | Parking improvements | Lack of parking | Parish Council | Stock | Traffic Management | Design | LCHE172024 | 8000 | Validation - Resulting scheme could cost £62k and provide two additional parking spaces
O/s 19-33 Shelley Road, Chelmsford | Extension of parking bays | Insufficient parking for residents cars | Councillor | Springfield | Traffic Management | Total scheme | LCHE172031 | 85500 | Validation - Extending parking bays would provide two additional spaces
Well Lane to The Heights - Service Road, Danbury | One-way road | Vehicles routinely parking/blocking service road | Parish Council | Danbury | Traffic Management | Total scheme | LCHE152104 | 81500 | From Feasibility Study shared at June 2018 Panel Option 2 - Make one-way with carriageway and layby improvements
Chancellor Avenue j/w Chelmer Village Way, Springfield | Measures to prevent vehicles loosing control on roundabout and hitting adjacent wall | Vehicles loosing control on roundabout | Parish Council | Springfield | Traffic Management | Total scheme | LCHE152009 | TBC | Awaiting impact on traffic speeds of Toucan crossing on Chelmer Village Way
West-bound bus stop on Broughton Road, near junction with Inchbonnie Road. | New metal bus shelter | Request received by SWF Town Council for a new passenger shelter to be installed. | Town Council | South Woodham Ferrers | Passenger Transport | Total scheme | LCHE175002 | 7500 | Validated by Passenger Transport team
Bus stop on Hullbridge Rd, opposite The Railway public house. | New metal bus shelter | Request received by SWF Town Council for a new passenger shelter to be installed. | Town Council | South Woodham Ferrers | Passenger Transport | Total scheme | LCHE175003 | 7500 | Validated by Passenger Transport team
Bus Stop outside St. Peter's C of E Primary School | New wooden shelter | Request received by West Hanningfield Parish Council for a new passenger shelter to be installed. | Parish Council | West Hanningfield | Passenger Transport | Total scheme | LCHE175004 | 13000 | Validated by Passenger Transport team
A114 London Road nr Britvic RAB, Chelmsford | Pedestrian crossing improvements | Concerns around pedestrians crossing A114 | Councillor | Chelmsford Non Parished | Traffic Management | Total Scheme | LCHE172025 | NA | Signalised crossing not feasible and footbridge could cost in excess of £200,000
Ongar Road (Nr j/w East View) Writtle | New metal bus shelter | Existing shelter badly damaged and barriered off | Parish Council | Writtle | Passenger Transport | Total scheme | LCHE185002 | 9000 | Validated by Passenger Transport team
Savernake Road (Harewood Road to Writtle Road), Chelmsford | Parking improvements | Congestion caused by parked cars | Councillor | Chelmsford Non Parished | Traffic Management | Feasibility | LCHE182006 | 4000 | Validation - Carry out Feasibility Study into widen carriageway to allow for parking bays. Resulting scheme could cost £100,000 to implement and need land acquisition.
67-69 Downham Road, Ramsden Heath | Request to change VAS to SID unit | Speed of traffic | Parish Council | South Hanningfield | Traffic Management | Total scheme | LCHE182012 | TBC | In validation - ATC data - 30mph - Eastbound 35.6mph & Westbound 33.3mph
Chignal Corner Bus Stop (west bound), O/s 57/59 Roxwell Road, Chelmsford | Request for raised kerbs | Low kerbs at bus stop | Passenger Transport team | Chelmsford Non Parished | Passenger Transport | Total scheme | LCHE175005 | 16000 | Validation - Raised kerbs could be installed.
Ford End C of E Primary School, B1008, Ford End | Advisory 20mph speed limit with Wig-Wag flashing lights | Speed of traffic | Parish Council | Great Waltham | Traffic Management | Total scheme | LCHE182016 | 500 | Review of 2018/19 scheme following 1 year trial period
Near 83-89 Avon Road, Chelmsford | Verge improvements | Parking on verges damaging them | Councillor | Chelmsford Non Parished | Traffic Management | Total scheme | LCHE182018 | NA | Validation - Verge outside 83-89 does not appear to be within public highway
Near 65-71 Melbourne Avenue, Chelmsford | Traffic island improvements | Speed and vehicle damage | Councillor | Chelmsford Non Parished | Traffic Management | Total scheme | LCHE182019 | NA | Validation - ATC data - 30mph speed limit - Eastbound 25.2mph & Westbound 23.9mph. Good speed compliance.
Thames Avenue, Chelmsford | Verge improvements | Vehicles routinely parking on verges | Councillor | Chelmsford Non Parished | Traffic Management | Feasibility | LCHE182032 | 5500 | Validation - Recommends a feasibility study into creating parking areas and prevent parking in other areas. Any resulting scheme could be in the region of £85,000 based on costs from Avon Road scheme.
Cherwell Drive, Chelmsford | Verge/parking improvements | Vehicles routinely parking on verges | Councillor | Chelmsford Non Parished | Traffic Management | Design | LCHE182031 | 13000 | Validation - Would recommend design year one and implementation year two. Create hard standing to allow vehicles to park (but not on bend) and HGV overrun around bend
Hammonds Road/Church Road, Boreham | Flood warning sign improvements - To allow automatic operation | Manually operated flood warning signs | Councillor | Boreham | Traffic Management | Total scheme | LCHE152010 | NA | Sensors funded 2017/18, awaiting implementation date from suppliers/contractors
Old Moulsham, Chelmsford - 20mph zone/limit | 20 mph zone/limit - Moulsham Drive/Lady Lane/Hamlet Road/St Johns Road/Vicarage Road/Moulsham Street | Speed of traffic | Councillor | Chelmsford Non Parished | Traffic Management | Implementation | LCHE152057 | 160000 | 20mph Zone Signs/Road markings to be implemented in 2018/19. Could still require Traffic Calming features, depending on driver compliance
Highwood Road, Edney Common - Traffic management improvements | Implementation of traffic management improvements - Remove centre white line/renew SLOW road markings, build outs at play ground/public house with priority flow | Speed of traffic | Parish Council | Highwood | Traffic Management | Implementation | LCHE162039 | 17500 | From completed design
Highwood Road, Loves Green - Traffic management improvements | Implementation of traffic management improvements - Remove centre white line/renew SLOW road markings/build outs at school with priority flow | Speed of traffic | Parish Council | Highwood | Traffic Management | Implementation | LCHE162038 | 14000 | From completed design
Victoria Road nr Riverside Leisure Centre, Chelmsford - Drainage improvements | Drainage improvements at crossing point | Standing water causing problems for pedestrians crossing road | School Crossing Patrol team | Chelmsford Non Parished | School Crossing Patrols | Implementation | LCHE156006 | 15000 | From completed design - Possible S.106 monies available
O/s St Peters Primary School, Church Road, West Hanningfield | Advisory 20mph speed limit with Wig-Wag flashing lights | Speed of traffic | Parish Council | West Hanningfield | Traffic Management | Total scheme | LCHE172007 | 21000 | Validation - Implement 20mph when lights flash signage with Wig-Wag flashing lights
Railway Bridge, Pump Lane, Springfield | Footbridge/footway improvements | Narrow footway over railway bridge | Councillor | Springfield | Traffic Management | Total scheme | LCHE182021 | TBC | In Validation
Nr Belsteads School, Back Lane, Little Waltham | Pedestrians in road warning signs | School pedestrians routinely crossing road | Councillor | Little Waltham | Traffic Management | Total scheme | LCHE182005 | TBC | In Validation
Cherwell Drive, Chelmsford | Verge/parking improvements | Verges being damaged by parked vehicles | Councillor | Chelmsford Non Parished | Traffic Management | Feasibility | LCHE182031 | 4000 | Validation - Could carry out feasibility study into creating parking but resulting scheme could cost in excess of £50,000
Thames Avenue, Chelmsford | Verge/parking improvements | Verges being damaged by parked vehicles | Councillor | Chelmsford Non Parished | Traffic Management | Feasibility | LCHE182032 | 4000 | Validation - Could carry out feasibility study into creating parking but resulting scheme could cost in excess of £85,000
School Lane, Broomfield | Improvements to conspicuity of zebra crossing | Speed of traffic | Councillor | Broomfield | Traffic Management | Total scheme | LCHE182015 | 5000 | Validation - ATC 30mph speed limit - Eastbound 26.2mph & Westbound 28.2mph. Recommendation to replace beacons and shields, also cut back vegetation to improve visibility
Lordship Road, Writtle | Reduce existing 40mph speed limit to 30mph | Speed of traffic | Councillor | Writtle | Traffic Management | Total scheme | LCHE182029 | NA | Validation - 30mph limit southbound -32.9mph & north bound 34.9mph - 40mph limit south bound 28.1mph & north bound 30.0 mph. Excellent compliance with 40mph speed limit, 30mph limit not appropriate due to environment of road
Milburn Crescent Chelmsford | Parking | Lack of available parking | Councillor | Chelmsford Non Parished | Traffic Management | Total scheme | LCHE182053 | TBC | In Validation
Footpath 76 Galleywood - Markland Close to Rignals Lane | Flexible surfacing on much used urban PRoW - 290m | Existing surface uneven/cracked by tree roots | PRoW team | Galleywood | Public Rights of Way | Total scheme | LCHE188001 | 45500 | Validated by PRoW team - footpath provides off-road pedestrian access, linking several residential roads