## Sheet1
Maldon District Local Highway - Potential Schemes List - November 2018
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
Fambridge Road (Limebrook Way RAB to Royal Oak Public House), Maldon | Walkable verge/footway | Lack of footway between small hamlet/public house and Maldon Town | Councillor | Maldon | Traffic Management | Implementation | LMAL162099 | TBC | Liaison on-going regarding nearby development and footways planned with the development
Handley's Lane, between Kelvedon Road and Handley's Lane roadway, Wickham Bishops | Surface improvements to byway to allow all year round usage | Byway often inaccessible due to flooding /surface condition | Parish Council | Wickham Bishops | Public Rights of Way | Total scheme | LMAL158003 | 64500 | Validation - Estimated costs re-evaluated by PROW team - Surfacing to north-east section (not to adoptable standards) £14,500 and middle section levelled/finished with planings £50,000
Beckingham Street/Tolleshunt D'Arcy Road, Tolleshunt Major | Junction improvements | Existing bennett junction causing issues | Parish Council | Tolleshunt Major | Traffic Management | Total scheme | LMAL162077 | 64000 | From Feasibility Study Parish Council preferred Option 2, Standard T-junction with pedestrian island at estimated cost £125,000. Scheme would require acquisition of land. Following site meeting with Parish Council representatives in October 2017 Parish indicate Option 1 Standard T-junction estimated cost £45,000 could meet their needs subject to final design.
Market Hill j/w High Street, Maldon | Improved signage to Car Parks | No signage at top of hill to direct traffic to Car Parks | District Council | Maldon | Traffic Management | Total scheme | LMAL152072 | NA | Validation - Whilst there is no signage at the top of Market Hill directing traffic to car parks. There is parking in either direction along the High Street which is signed, so any visitor taking either direction will be able to find a car park. Also there are a lot of existing signs at the top of Market Hill and there is a current drive by DfT to reduce sign clutter.
B1021 Bradwell Road, Mill End Bradwell on Sea | Traffic management improvements | Speed of traffic in 30mph limit | Councillor | Bradwell on Sea | Traffic Management | Total scheme | LMAL162119 | 26000 | Validation - Posted speed limit 30mph, South bound 36.4mph & North bound 37.1mph. Recommendation - Vehicle Activated Sign and speed limit repeater signs
Cedar Grove, Burnham on Crouch | Footway improvements | Accessibility issues on footways | Councillor | Burnham on Crouch | Traffic Management | Total scheme | LMAL182031 | TBC | In validation
Old Heath Road, Southminster | Traffic management improvements and request for Quiet Lane status | Speed of traffic on narrow rural road | Councillor | Southminster | Traffic Management | Total scheme | LMAL162118 | NA | Validation - Policy states that vehicles speeds should be kept to appropriate for mixed road usage with 85th%ile below 35mph. Recorded 85th%ile speeds are above 35mph so it cannot be a Quiet Lane
Church Road (Holt Drive to Blacksmiths Lane) and Arbour Lane (Blacksmiths Lane to Grange Road), Wickham Bishops | Footways | Lack of pedestrian access to the Village Library | Parish Council | Wickham Bishops | Walking | Feasibility | LMAL153002 | 4000 | Validation - recommendation is for Feasibility Study to cover obtaining any land necessary for footway construction and also pedestrian/vehicle counts to assess potential usage and any conflict. Construction costs could be significant. Dec 17 Panel decision to remove scheme from Approved Works Programme and return to Potential Scheme List
B1010 Chelmsford Road (Spar Lane to Edgeware Veterinary Practice), Purleigh | Extension of existing footway | Lack of safe route for pedestrians | Parish Council | Purleigh | Walking | Feasibility | LMAL153001 | 8000 | Validation - recommendation for Feasibility Study into footway/walkable verge, with pedestrian video survey and road safety audit. Though implementation costs could be around £50k. Dec 17 - Panel decision to return scheme from Approved Works Programme back to Potential Schemes List
Fambridge Road, North Fambridge | Wooden bus shelter | Stop ID 1500IM2085 - North Fambridge Shelter - replacement needed | Passenger Transport Team | North Fambridge | Passenger Transport | Total scheme | LMAL155013 | 13000 | Validated by Passenger Transport team
The Avenue, North Fambridge | Wooden bus shelter | Stop ID 1500IM2536 - Ferry Corner Shelter - replacement needed | Passenger Transport Team | North Fambridge | Passenger Transport | Total scheme | LMAL155014 | 13000 | Validated by Passenger Transport team
Burnham Road, Latchingdon | Wooden bus shelter | Stop ID 1500LATCHG2 - metal shelter needs replacing (Parish Council owned Shelter) | Parish Council/Passenger Transport Team | Latchingdon | Passenger Transport | Total scheme | LMAL155016 | 13000 | Validated by Passenger Transport team
Mill Lane j/w Beckingham Street, Tolleshunt Major | HGV Signage improvements | Road not suitable for HGV's | Parish Council | Tolleshunt Major | Traffic Management | Feasibility | LMAL162091 | 13000 | Validation - Existing 7.5 tonne weight limit signage in place and "Unsuitable for HGV" sign. Recommendation is for signage review of HGV directional signage to ensure vehicles use preferred route via School Road. Dec 17 Panel decision to remove scheme from Approved Works Programme and return to Potential Scheme List
Byway 32 Purleigh (Roundbush Road to How Green Road) | Improve drainage, rebuild surface, install heavy duty removable bollards | Southern end of byway badly rutted and is often impassable. There is also a seasonal TRO in place to restrict access. | Public Rights of Way | Purleigh | Public Rights of Way | Total scheme | LMAL168007 | 36000 | Validated by Public Rights of Way team - Dec 17 - Panel decision to return scheme from Approved Works Programme back to Potential Schemes List
Maldon Road/Hall Road/Walden House Road/Prince of Wales Road, Great Totham | Parking improvements at junctions | Parking causing problems at junctions | Parish Council | Great Totham | Traffic Management | Total scheme | LMAL172005 | NA | Validation - Parking restrictions here should be considered through the Parking Partnership, SEPP advised.
B1018 Langford Road, Wickham Bishops | Carriageway improvements | Width of road when two vehicles try to pass | Resident | Wickham Bishops | Traffic Management | Feasibility Study | LMAL172008 | 10000 | Validation - "B" road and PR2, width restriction contrary to policy as its main function is movement of traffic. Suggestion is to review Warning Signs and Road Markings indicating hazards and narrow sections of road
Fambridge Road, Maldon | New bus stop poles/flags/timetables | Nine bus stops need clearly identifying, some flags on lamp columns | Passenger Transport | Maldon | Passenger Transport | Total scheme | LMAL175001 | 10000 | Validated by Passenger Transport team
Factory Hill/Brook Road/D'Arcy Road, Tolleshunt Knights - TMI | Mini-roundabout improvements | Concerns around operation of mini-roundabout | Parish Council | Tolleshunt Knights | Traffic Management | Feasibility | LMAL162055 | 4000 | Validation recommends feasibility study. Dec 17 Panel decision to remove scheme from Approved Works Programme and return to Potential Scheme List
Tiptree Road, Wickham Bishops | Footway to link new development to Witham Road | Lack of footway | Councillor | Wickham Bishops | Traffic Management | Total scheme | LMAL182022 | TBC | In validation
Church Hill/The Street, Purleigh | Kerbing of verge | Parked cars causing verge damage | Parish Council | Purleigh | Traffic Management | Total scheme | LMAL172023 | NA | Validation - Feasible to provide formal surface to allow parking and drainage. Parish Council had a quote form external contractor and considering funding scheme.
Main Road, Mundon | Traffic management improvements | Speed of traffic through Village | Parish Council | Mundon | Traffic Management | Feasibility | LMAL172013 | 4000 | Validation - Recommends a feasibility study into providing road narrowing's and/or priority working system within the 30mph speed limit (to include consultation) and provide costing for any feasible scheme
Eves Corner B1021 Southminster Road j/w Mill Road/Green Lane, Burnham on Crouch | Traffic management improvements | Vehicles losing control and causing property damage | Councillor | Burnham on Crouch | Traffic Management | Design | LMAL172022 | 4000 | Validation - Review of traffic signs/carriageway markings and design of kerb realignment (junction with Green Lane and Mill Road) with reflective road studs.
Woodham Road/The Street, Stow Maries | Traffic management improvements | Speed of traffic through Village | Parish Council | Stow Maries | Traffic Management | Feasibility | LMAL172026 | 4000 | Validation - Woodham Road - 30mph - East bound 35.4mph & West bound 37.4mph, The Street - 30mph - Southwest bound 39.5mph & Northeast bound 37.8mph. Recommendation to carry out feasibility study into viability of providing road narrowing's and/or priority working system within 30mph limit. To include consultation and road safety audit. As well as introducing new features need to consider removing/altering existing features/measures.
Tom Tit Lane near j/w A414 Maldon Road, Woodham Mortimer | Request for Unsuitable for HGV signage | HGV use of lane | Parish Council | Woodham Mortimer | Traffic Management | Total scheme | LMAL172025 | 2500 | Validation - Replace existing Weight Limit Sign and post with Unsuitable for HGV sign and relocate existing weight limit sign to Old London Road cross roads
Site 1 - Goldhanger Road, Site 2 - Broad Street Green, Site 4 - Heybridge Approach, Site 5 - Langford Road, Heybridge | Heybridge - Village gateway treatments (post/rail) | To highlight parish boundary to drivers | Parish Council | Heybridge | Traffic Management | Implementation | LMAL152049 | TBC | Awaiting findings from 2018/19 design
Southminster Road j/w Hall Road, Asheldham | Signage improvements | Signs at junction/visibility problems | Parish Council | Asheldham & Dengie | Traffic Management | Total scheme | LMAL182006 | TBC | In Validation
Asheldham Centre, Hall Road, Asheldham | Warning signs for pedestrians in road | Pedestrians routinely crossing road o/s Asheldham Centre | Parish Council | Asheldham & Dengie | Traffic Management | Total scheme | LMAL182007 | TBC | In Validation
Plains Road, Great to Little Totham | Speed reduction | Speed of traffic | Parish Council | Little Totham | Traffic Management | Total scheme | LMAL182008 | TBC | In Validation - ATC data - 60mph speed limit - West - Eastbound 41.1mph & Westbound 40.5mph - East - Eastbound 37.7mnph & Westbound 35.5mph
Church Lane, Honeypot Lane & Crows Lane, Stow Maries | 7.5 tonne environmental weight limit | Good vehicle use of rural lane | Parish Council | Stow Maries | Traffic Management | Total scheme | LMAL182009 | TBC | In Validation
Blackhouse Farm Cottages, Steeple Road, St Lawrence | Traffic management improvements | Speeding traffic/vehicle damage to buildings | Councillor | St Lawrence | Traffic Management | Total scheme | LMAL182005 | TBC | In validation - ATC data - 60mph speed limit - NE bound 42.7mph & SW bound 42.7mph
Church Road, Tolleshunt Major | HGV restrictions | HGV usage of road | Parish Council | Tolleshunt Major | Traffic Management | Total scheme | LMAL182001 | TBC | In validation - HGVs comprise 2-3% of total vehicle volume over 5 day period
Woodrolfe Road, Tollesbury | Surfacing in front of seawall | Loose/unbound material spreading onto carriageway | Parish Council | Tollesbury | Traffic Management | Total scheme | LMAL182010 | TBC | In validation - Seawall is a highway maintenance responsibility.
Fambridge Road, near j/w Granger Avenue, Maldon | Traffic management improvements | Speed/volume of traffic | Councillor | Maldon | Traffic Management | Total scheme | LMAL182012 | NA | Validation - 30mph speed limit - South bound 28.8mph & North bound 27.4mph. Good speed compliance.
A414, Maldon Road (Oak Corner to Post Office Road) Woodham Mortimer | Measures to help pedestrians cross the road to bus stops | Speed/volume of traffic | Parish Council | Woodham Mortimer | Traffic Management | Total scheme | LMAL182016 | TBC | In validation
B1018 Southminster Road near Dairy Farm Road, Althorne/Mayland | New bus stop | Changes to existing bus service | Councillor | Althorne | Passenger Transport | Total scheme | LMAL185001 | TBC | In validation
B1010 Maldon Road, Burnham on Crouch | 30mph carriageway roundels | Speed/volume of traffic | Councillor | Burnham on Crouch | Traffic Management | Total scheme | LMAL182018 | TBC | In validation - 30mph speed limit - East bound 34.5mph & West bound 34.0mph
School Road &The Street, Little Totham | Routing of HGV vehicles | Volume of traffic | Councillor | Little Totham | Traffic Management | Total scheme | LMAL182023 | TBC | In validation
Near 20 Coleridge Road, Maldon | Measures to stop vehicles parking on footway and adjust fall of footway away from the property | Vehicles parking on footway & fall of footway towards property | Councillor | Maldon | Traffic Management | Total scheme | LMAL182024 | TBC | In validation
Near 25 Wellands, Wickham Bishops | Bend Warning sign & SLOW road marking | Sharp bends and speed of traffic | Parish Council | Wickham Bishops | Traffic Management | Total scheme | LMAL182025 | TBC | In validation
Witham Road/Little Braxted Road, Little Braxted | Measures to stop HGV's using roads unnecessarily | HGV usage of rural roads | Parish Council | Little Braxted | Traffic Management | Total scheme | LMAL182011 | TBC | In validation
Ravello, Maypole Road, Wickham Bishops | Signage improvements to improve sight lines | Village sign blocking sight line of property | Resident | Wickham Bishops | Traffic Management | Total scheme | LMAL182013 | 2000 | Validation - Feasible to raise height of Village signs. Possible 3rd party funding for scheme
O/s 1-8 Ulting Road, Langford | Request for 40mph speed limit | Existing 60mph speed limit too high | Councillor | Langford | Traffic Management | Total scheme | LMAL182014 | TBC | In validation - Existing 60mph speed limit Average Speed data South bound 20.5mph & North bound 21.3mph
O/s Library Station Road Burnham on Crouch | Directional sign to St Cuthbert's Church | Lack of sign | Resident | Burnham on Crouch | Traffic Management | Total scheme | LMAL182026 | TBC | In validation - Possible 3rd party funding for scheme
Southend Road and B1010, Burnham Road, Hazeleigh | Speed limit reduction | Speeding traffic | Parish Council | Hazeleigh | Traffic Management | Total scheme | LMAL182028 | TBC | In validation - awaiting speed/volume survey data
Maypole Road, Langford | Horse & Rider Signage | Improvements to Horse & Rider signage at bridleway and Farm Ride crossings | Parish Council | Langford | Traffic Management | Total scheme | LMAL182040 | TBC | In validation
D'Arcy Way, Tolleshunt D'Arcy | Cul de Sac signage | Residential no through road | Parish Council | Tolleshunt D'Arcy | Traffic Management | Total scheme | LMAL182030 | TBC | In validation
Adjacent to White Lyons/Bradwell Church, High Street, Bradwell on Sea - TMI | Traffic management improvements | Narrow carriageway and parked vehicles causing congestion issues | Parish Council | Bradwell on Sea | Traffic Management | Implementation | LMAL162090 | TBC | Awaiting findings from 2018/19 design
Southminster Road (Old Heath Road to Mangaps Manor) Burnham on Crouch | Walkable verge/footway | Lack of footway/walkable verge for pedestrians | Councillor | Burnham on Crouch | Traffic Management | Implementation | LMAL142037 | TBC | Awaiting findings from 2018/19 feasibility
Fambridge Road, Maldon (Limebrook Way RAB to Royal Oak PH) - Footpath | Detailed design of footpath | Detailed design of footpath | Councillor | Maldon | Traffic Management | Implementation | LMAL142006 | TBC | Awaiting findings from 2018/19 design
Fambridge Road (Lower Burnham Road to Rectory Road), North Fambridge - Study into provision of footway | Feasibility Study to consider provision of new footway/walkable verge | Feasibility Study to consider provision of new footway/walkable verge | Parish Council | North Fambridge | Traffic Management | Implementation | LMAL152010 | TBC | Awaiting findings from 2018/19 feasibility
B1010 Fambridge Road (The Wash to Roundbush Public House), Purleigh | Speed reduction measures | Narrow road with passing places, speed of traffic | Parish Council | Purleigh | Traffic Management | Implementation | LMAL142031 | TBC | Awaiting findings from 2018/19 feasibility
Witham Road/Maypole Road/Kelvedon Road/The Street, Wickham Bishops - TMI | Wickham Bishops - Priority working/build outs/gateways | Speed/volume of traffic | Parish Council | Wickham Bishops | Traffic Management | Implementation | LMAL162039 | TBC | Awaiting findings from 2018/19 feasibility
B1026 Maldon Road Goldhanger | Check on effectiveness of changes to size/frequency of 30mph speed limit repeater signs | Speed of traffic | HLO | Goldhanger | Traffic Management | Total scheme | LMAL162048 | TBC | In validation - awaiting speed/volume survey data