## Sheet1
Maldon Local Highway Panel - Potential Schemes List - September 2019
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
Church Road (Holt Drive to Blacksmiths Lane) and Arbour Lane (Blacksmiths Lane to Grange Road), Wickham Bishops | Footways | Lack of pedestrian access to the Village Library | Parish Council | Wickham Bishops | Walking | Feasibility | LMAL153002 | 4000 | Validation - recommendation is for feasibility study to cover obtaining any land necessary for footway construction and also pedestrian/vehicle counts to assess potential usage and any conflict. Construction costs could be significant. Dec 17 Panel decision to remove scheme from Funded Schemes List and return to Schemes Awaitng Funding List.
Mill Lane j/w Buckingham Street, Tolleshunt Major | HGV signage improvements | Road not suitable for HGV's | Parish Council | Tolleshunt Major | Traffic Management | Design | LMAL162091 | 4500 | Validation - Existing 7.5 tonne weight limit signage in place and "Unsuitable for HGV" sign. Recommendation is for signage review of HGV directional signage to ensure vehicles use preferred route via School Road. Dec 17 Panel decision to remove scheme from Funded Schemes List and return to Schemes Awaiting Funding List.
Byway 32 Purleigh (Roundbush Road to Howe Green Road) | Improve drainage, rebuild surface, install heavy duty removable bollards | Southern end of byway badly rutted and is often impassable. There is also a seasonal TRO in place to restrict access. | Public Rights of Way | Purleigh | Public Rights of Way | Total scheme | LMAL168007 | 36000 | Validated by Public Rights of Way team in Dec 17 - Panel decision to return scheme from Funded Schemes List back to Schemes Awaiting Funding List
B1018 Langford Road, Wickham Bishops | Carriageway improvements | Width of road when two vehicles try to pass | Resident | Wickham Bishops | Traffic Management | Total scheme | LMAL172008 | 10000 | Validation - "B" road and PR2, width restriction contrary to policy as its main function is movement of traffic. Suggestion is to review warning signs and road markings indicating hazards and narrow sections of road.
Fambridge Road, Maldon | New bus stop poles/flags/timetables | Nine bus stops need clearly identifying, some flags on lamp columns | Passenger Transport | Maldon | Passenger Transport | Total scheme | LMAL175001 | 10000 | Validated by Passenger Transport team.
Plains Road, Great to Little Totham | Speed reduction | Speed of traffic | Parish Council | Little Totham | Traffic Management | Validation | LMAL182008 | TBC | In validation - ATC data - 60mph speed limit - West - Eastbound 41.1mph and Westbound 40.5mph - East - Eastbound 37.7mph and Westbound 35.5mph.
Blackhouse Farm Cottages, Steeple Road, St Lawrence | Traffic management improvements | Speeding traffic/vehicle damage to buildings | Councillor | St Lawrence | Traffic Management | Total scheme | LMAL182005 | N/A | Validation recommends not to proceed with this request due to the lack of space available to install a VRS at this location.
Woodrolfe Road, Tollesbury | Surfacing in front of seawall | Loose/unbound material spreading onto carriageway | Parish Council | Tollesbury | Traffic Management | Design | LMAL182010 | 6500 | Validation - Recommends design of surfacing scheme and any necessary drainage. Design will also produce accurate costing, at this stage it would be expected to be approximately £22,000.
B1018 Southminster Road near Dairy Farm Road, Althorne/Mayland | New bus stop | Changes to existing bus service | Councillor | Althorne | Passenger Transport | Total scheme | LMAL185001 | TBC | Validation - possible to implement two bus stops with kerbing. Feasibility of scheme would depend on bus service. HLO to now undertake an informal consultation prior to commissioning the scheme.
Wantz Road, Maldon | 2x Speed and volume surveys required. | Speeding and vehicles travelling in the wrong direction. | Cllr Channer | Maldon | Surveys | Surveys |  | 400
West Street, Tollesbury | Speed and volume survey required. | Speeding vehicles | Parish Council | Tollesbury | Surveys | Surveys |  | 200
Western Road, Burnham-on-Crouch | Speed and volume survey required. | Speeding vehicles | Cllr Pratt | Burnham on Crouch | Surveys | Surveys |  | 200
Burnham Road, Southminster | Speed and volume survey required. | Speeding vehicles | Cllr Pratt | Southminster | Surveys | Surveys |  | 200
Wickham Bishops SID Rotations | SID Rotations | SID rotations for Wickham Bishops | N/A | Wickham Bishops | VAS | Surveys |  | 1480
Chimney Pot Lane, Hazeleigh | Investigation into the possibility of placing restrictions to prevent HGVs from using the route | HGVs getting stuck at the brook | Cllr Channer | Hazeleigh | Traffic Management | Validation | LMAL192001 | TBC | In validation.
Witham Road, Wickham Bishops | Investigation into the possibility of undertaking a review of the signing and lining along the route | Safety along the route | Parish Council | Wickham Bishops | Traffic Management | Validation | LMAL192002 | TBC | In validation.
B1021 Burnham Road, Southminster | Residents have raised concerns in relation to speeding vehicles | Speeding vehicles | Cllr Pratt | Southminster | Traffic Management | Total scheme | LMAL182035 | N/A | Speed and volume survey results: Eastbound 41.6mph. Westbound 41.2mph. Good compliance within the posted speed limit, therefore not recommended to proceed with this request. Information shared with Cllr Pratt.
West Street, Tollesbury | Perceived speeding issues | Speeding vehicles | Tollesbury Parish Council | Tollesbury | Traffic Management | Total scheme | LMAL182033 | N/A | Speed and volume results: Westbound 34.4mph, Eastbound 32.0mph, and therefore does not meet intervention for traffic calming measures. Information fed back to Tollesbury Parish Council and County Member.
Elysian Gardens, Tollesbury | Parish Council have reported obstructive parking. | Parking issues | Tollesbury Parish Council | Tollesbury | Traffic Management | Validation | LMAL192003 | TBC | In validation.
East End Road, Bradwell-on-Sea | Parish Council have requested traffic calming measures and a 20mph limit. | Safety along the route | Bradwell Parish Council | Bradwell on Sea | Traffic Management | Validation | LMAL192004 | TBC | Awaiting speed and volume survey information.
Chimney Pot Lane, Hazeleigh | Speed and volume survey required. | HGV usage | HLO | Woodham Mortimer | Surveys | Surveys |  | 200
Witham Road, Little Braxted | Parish Council have requested additional signage to prevent vehicles from travelling along Witham Road. | HGV usage | Little Braxted Parish Council | Little Braxted | Traffic Management | Validation | LMAL192005 | TBC | In validation