## Sheet1
Potential Schemes List - March 2019
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
Honey Lane, Waltham Abbey - Crossing | To look at the land required to install a signalised crossing | No crossing point for pedestrians and horse riders along Honey Lane by the Woodbine | Cllr Gadsby | Waltham Abbey | Traffic Management | Feasibility | LEPP162004 | N/A | This does not meet policy to implement a signalised crossing. A substantial amount of non-highway land is required to install any kind of crossing point at this location. This land belongs to the City of London and they require a land swap at a ratio of 1:10 of adjacent land to the Forest. ECC and Essex Highways do not have the land required. This scheme is not viable to progress.
Watery Lane, Little Laver - Quiet Lane | Quiet Lane | Request for Quiet Lane | Cllr McEwen | Little Laver | Traffic Management | Total scheme | LEPP162025 | N/A | There is currently a trial underway for Quiet Lanes and there were 5 chosen sites. New sites may be considered after the conclusion of this trial in 2019.
Upland Road, Thornwood - Traffic calming | Reported speeding issue, request for traffic calming | Parish raised concerns that Upland Road is being used as a 'rat run' and vehicles are speeding | Parish Council | Thornwood | Traffic Management | Total scheme | LEPP172029 | TBC | In validation, speed survey indicates a speeding issue as the combined East & Westbound daily average speed is 35.6mph in a 30mph speed limit.
Thornwood Common on the B1393 - Pedestrian Refuge | Request for a pedestrian refuge | Reports of speeding vehicles makes it difficult for pedestrians to cross the road to the bus stop | Cllr Whitbread | Thornwood | Traffic Management | Feasibility | LEPP172027 | N/A | Against policy. The speed limit at this location is 40mph therefore automatically rules out the possibility to install a zebra crossing. The pedestrian / vehicle conflict (PV2) survey over 7 days was 0.088 x 10^8. Where the value of a PV2 is below 0.2 then a crossing point would not be justified.
Powdermill Lane j/w Leaview, Waltham Abbey - Overrun area | Overrun area to be constructed as per detailed design | Vehicles cannot get into Walton Gardens without going over the kerb and grass verge, which is causing the kerbs to break and verges to become rutted | Cllr Lea/Cllr Webster | Waltham Abbey | Traffic Management | Total scheme | LEPP162032 | 45500 | Design previously shared.
Theydon Road - Theydon Bois - Traffic calming | Request for traffic calming measures or VAS to get drivers to slow down | The apparent narrow width of the road and reports of speeding vehicles is causing concerns for residents as vehicles are mounting the kerb to pass each other | Cllr Whitbread | Theydon Bois | Traffic Management | Total scheme | LEPP172023 | N/A | The speed survey results do not indicate a speeding issue on Theydon Road, Theydon Bois, therefore doesn't meet the guidance for the installation of a Vehicle Activated Sign (VAS). The speed survey results were as follows; Location of speed survey by 85m S of Theydon Bois Golf Club posted speed limit 40mph Southbound average 35.8mph Northbound average 38.6mph
Loughton Way j/w River Road, Buckhurst Hill - Dropped kerbs | Install dropped kerbs with tactile paving and a pedestrian refuge | Pedestrians are finding it very difficult to cross at this junction to continue along the road | Cllr Metcalfe | Buckhurst Hill | Traffic Management | Implementation | LEPP162015 | N/A | The feasibility study has been completed and has not identified any suitable measures.
Fiddlers Hamlet j/w Stewards Green Road and Coopersale Street - Traffic calming | Request for traffic calming/safety measures at this junction | Concerns raised by resident that the junction of Fiddlers Hamlet/Stewards Green Road and Coopersale Street is a dangerous junction where there have been a number of reported incidents | Cllr Whitbread | Epping | Traffic Management | Feasibility | LEPP172025 | N/A | A casualty reduction scheme was implemented 8th Aug 2016, a road safety audit level 4 was completed with the only further recommendation being to remove the vegetation. This will need to be actioned and the site monitored before any further measures are considered.
Mill Street, Harlow Common, Hastingwood Road, North Weald - Traffic calming | Request to look at alleviating the congestion and reducing speeds of vehicles using these roads and provision of footway/verges for pedestrians | Concerns of congestion and speeding along these roads and lack of verges/footways for the local community living there | Parish Council | North Weald | Traffic Management | Total scheme | LEPP172031 | TBC | In validation, HLO to liaise with Parish Clerk to clarify exactly where footway/verges are required. Speed surveys completed do not indicate a speeding issue.
Fyfield Road, Ongar - Crossing | Upgrade the existing zebra crossing | The existing crossing is being frequently used by patients of the medical centre and children walking to Ongar Academy | Cllr Keska | Chipping Ongar | Traffic Management | Total scheme | LEPP172016 | TBC | This scheme is being re- validated to look at measures to improve existing zebra crossing.
Lower Forest Road - Speed limit reduction & deer warning signs | Request for speed limit change and deer warning signs | Concerns that cars are driving too fast and deer particularly in the rutting season are being hit by vehicles. Local residents would like the speed limit reduced to 40mph in line with the rest of the Forest roads and there are no warnings in either direction on the Epping to North Weald road to alert drivers to the presence of deer | Cllr Whitbread | Thornwood | Traffic Management | Total scheme | LEPP182009 | TBC | Awaiting results of speed survey.
Church Road, Buckhurst Hill - Signage | Request to look at improving signage at bend before the church and school to warn drivers to slow down | Safety concerns of speeding vehicles travelling East along Church Road towards Buckhurst Hill High Road as they approach the bend | Cllr Metcalfe | Buckhurst Hill | Traffic Management | Total scheme | LEPP172021 | N/A | Validation recommended that NEPP are engaged to discuss and progress any parking restriction scheme and that the school is also engaged with to explore softer measures such as walking buses and to establish a travel plan.
High Road, North Weald - VAS | Request for a VAS | Parish raised concerns of traffic speeding along the High Road North Weald and would like it assessed for VAS close to the end of the village where the Kings Head Garage is located | Parish Council | North Weald | Traffic Management | Total scheme | LEPP172030 | N/A | The speed survey results do not indicate a speeding issue on High Road, North Weald, therefore doesn't meet the guidance for the installation of a Vehicle Activated Sign (VAS). The speed survey results were as follows; Location of speed survey by Lamp Column 10, 50m SW of j/w Dukes Close posted speed limit 30mph South-westbound average 30.9mph North-eastbound average 29.9mph
Willow Tree Close Market Place Abridge - Parking issues | Residents are looking for a solution to this problem, especially on the entrance to the close that gets very bad | Willow Tree Close is in the market place of Abridge and sits between the busy Abridge Deli and Blue Boar pub. The area gets very busy with cars and these overflow into the close along with customers of the Deli. The problem is that cars park on both sides of the road leaving very bad access issues where rubbish trucks, vans and emergency vehicles are sometimes not able to get in to the close. Along with this being detrimental to the residents it also causes a strong safety risk which needs to be addressed | Parish Council | Lambourne | Traffic Management | Total scheme | LEPP182003 | N/A | Validation complete - Double height kerbs would be problematic due to drainage and utility issues. It should be noted that a validation was also progressed requesting bollards, but this was not progressed due to the STATS issues and the resultant remaining footway width. The previous validation recommended that waiting restrictions should be installed probably in the form of double yellow lining. This is still the recommended action so should be referred to NEPP.
Fairmead Road, High Beech - Road Closure | Request for road closure to be funded by City of London via third party team | The Conservators of Epping Forest are proposing an Experimental Traffic Order to be installed on Fairmead Road for a 6 month period with a review. This will allow an adequate period to assess the impact of closing Fairmead Road to 50m from the Crossroads junction | City of London | High Beech | Traffic Management | Total scheme | LEPP182006 | N/A | All third party schemes are assessed under the LHP validation process. This scheme has now been validated and passed to the third party team.
Bridge Hill Epping - Bridge visibility | Request to improve the traffic movement through the bridge | Outside 52 Bridge Hill, Epping, CM16 4ER is the railway bridge with bypass for vehicles, this is a very narrow bridge with blind corners and the concern is that there are many cars traversing at high speeds in both directions (the bridge only allows for one car through each way yet road users do not seem to pay attention to this) | Cllr Whitbread | Epping | Traffic Management | Total scheme | LEPP182007 | N/A | The speed survey results do not indicate a speeding issue on the approach to and from the bridge. Still being validated to ascertain if any measures can be implemented to warn vehicles of blind bend through the bridge. The speed survey results were as follows; Location of speed survey Street sign, immediately NW of j/w Sunnyside Road Posted speed limit 30mph Southeast bound average 21.9mph, Northwest bound average 20.7mph. Another site visit is required to reassess viable options.
Old Shire Lane, Honey Lane, Farthingdale Lane and Stoney Bridge Drive, Waltham Abbey - HGV movement | Request for measures to prevent HGVs accessing these local roads | Articulated trucks and lorries that seem to overflow from the lorry park near Junction 26 of the M25 motorway cause problems in the adjacent roads. These local roads, footpaths and highway hard shoulders are getting damaged by the heavy traffic. The lorries try to turn and reverse in small estate roads causing damage to the road structure and street furniture | EFDC/Cllr Gadsby | Waltham Abbey | Traffic Management | Total scheme | LEPP182008 | TBC | HGV survey completed, results being analysed to investigate the appropriate measure to resolve this issue before validation is complete.
B1393 j/w Rye Hill Road - Traffic calming | Request for traffic calming measures | Residents raising concerns regarding the speed of traffic along the B1393 near the j/w Rye Hill Road. Concerns that 50mph speed limit is a contributing factor to accidents at this junction and would like it reduced. The speed of traffic also creates a safety issue for pedestrians crossing the road. | Cllr Whitbread | Thornwood | Traffic Management | Total scheme | LEPP182011 | TBC | In validation.
A128 Brentwood Road, Ongar - Signage | Request for 30mph repeater signs to make drivers aware they are in a 30mph limit | Concerns of speeding from the Stag Public House to the mini roundabout at top of Coopers Hill and lack of speed limit signs | Town Council | Ongar | Traffic Management | Total scheme | LEPP182016 | N/A | 30mph repeater signs cannot be installed a this location. The 30mph speed limit is by virtue of street lighting. The speed survey did not indicate a speeding issue with the combined East & Westbound daily average of 30.8mph.
All roads in Loughton Conservation areas - 20mph Zones | Request to implement a 20mph speed zone incorporating all roads in conservation areas | Complaints of excessive speed on hills, lack of footways either one or both sides necessitating walking in road. This is a much used cycle route and frequently used by horses | Cllr Pond | Loughton | Traffic Management | Total scheme | LEPP182013 | TBC | In validation. HLO liaising with EFDC Conservation Officer to ensure any physical features such as roundels are acceptable in a conservation area. Will also require a number of speed surveys approximately 15 that need panel agreement to commission.
Honey Lane, Waltham Abbey - VAS | Request for a Vehicle Activated Sign (VAS) | Junction 26 of the M25 is just to the east of Honey Lane and the traffic exits the motorway at speed. The Marriot Hotel sits at the top of Honey Lane. Although Honey Lane is a main route into Waltham Abbey within a few hundred yards it enters a high density residential area, with Leverton School a short way further along | Cllr Webster/Cllr Gadsby | Waltham Abbey | Traffic Management | Total scheme | LEPP182014 | N/A | The speed survey results do not indicate a speeding issue on Honey Lane, therefore doesn't meet the guidance for the installation of a Vehicle Activated Sign (VAS). The speed survey results were as follows; Location of speed survey by Lamp Column 8, 105m East of j/w Shernbroke Avenue posted speed limit 40mph Eastbound average 35.6mph, Westbound average 35.00mph .
Parklands, Waltham Abbey - VAS | Request for a Vehicle Activated Sign (VAS) | Speeding concerns along Parklands to Paternoster Hill | Cllr Webster/Cllr Gadsby | Waltham Abbey | Traffic Management | Total scheme | LEPP182015 | N/A | The speed survey results do not indicate a speeding issue on Parklands and Paternoster Hill, and does not meet the guidance for the installation of a Vehicle Activated Sign (VAS). The speed survey results were as follows; Parklands, Waltham Abbey posted speed limit 40mph Location of speed survey no.1 by Lamp Column 40 55m NE of j/w Moremead Combined North-east & South-westbound average daily speed 38.5mph Location of speed survey no.2 by Lamp Column 25 105m E of j/w Newteswell Drive Combined East & Westbound average daily speed average 40mph Paternoster Hill, Waltham Abbey posted speed limit 30mph Location of speed survey no.3 by Lamp Column LC6, 30m W of Queens Head Public House Combined East & Westbound average daily speed average 28mph
Epping Forest - Cycling | Currently there is no complete up-to-date cycling strategy for the Epping Forest District that encompasses all cycling elements. The aim of this work is to provide a cycle strategy for Epping Forest which will identify cycle schemes and initiatives for implementation in the short, medium and long term | N/A |  | Epping Forest | Cycling | Feasibility | LEPP154001 | TBC | Cycling Action Plan now completed. Link to the plan sent to all panel members.
Church Road, Moreton - Footway | Installation of a footway for 32m outside Moreton Primary School | The lack of footway is forcing school children into the road. Other facilities including the village hall and the church require pedestrian access which is not currently available | Cllr Maggie McEwen | Moreton | Walking | Implementation | LEPP173001 | TBC | The implementation cost is around £20k, however we will need to relocate GigaClear Fibre Optics. Budget estimate request to provide relocation costs has been sent to GigaClear, until they provide this information we will not have an estimate for the total cost.
Abridge Road -Foot path | Request to ascertain if it is possible to extend the path so that it reaches the row of four houses just passed the bridge | Residents have asked if it is possible to extend an existing pathway that currently leads from Theydon Bois station along Abridge Road. This path stops just before the motorway bridge, and there are 4 dwellings just after this bridge. Residents regularly walk to the station and have to walk on the verge which can be quite difficult and dangerous, especially in bad weather | Cllr Whitbread | Theydon Bois | Walking | Total scheme | LEPP183003 | 72500 | Validation complete - recommendation to install footpath and dropped crossing point. Location of dropped crossing to be identified at design stage.
Public Bridleway no 14 from Forest Way to Woodbury Hill | Request to resurface the bridleway | Badly deteriorated surface | PROW Team | Loughton | Public Rights of Way | Total scheme | LEPP178001 | TBC | Scheme to be assessed by the PROW Team.
Footpath 3 - PROW Improvements | 1) The embankment to be shored up with concrete bag work 2) Infill with concrete and planings and compact firmly | Path is disappearing into the river. The footpath at present is uneven and difficult in places to negotiate if unsure of footings. In poor light, the issues may be intensified | PROW Team | Theydon Bois | Public Rights of Way | Total scheme | LEPP168004 | 65000
Byway 61, Willingale - PROW Improvements | 1) Clear the ditches to protect any new surface from water damage 2) Remove side overgrowth to let air and sunlight onto the byway so it dries out 3) Improve the vehicle access along the byway | Unsafe state of the byway for users as there are places with deep ruts filled with water | PROW Team | Willingale | Public Rights of Way | Total scheme | LEPP168001 | 50500
Byway 21 - PROW Improvements | Undertake improvement works to the drainage and surface to enhance the accessibility for all users of the byways | At present the lane is partly naturally surfaced. Some sections are open and exposed to the elements while the majority is enclosed by trees and hedges. The constant use by motorised vehicles has made a section of the route almost impassable for most parts of the year. The lane becomes highly waterlogged, rutted and boggy and is very difficult to negotiate and dangerous to use for all users. There have been instances of horses and four-wheel users becoming stuck | PROW Team | Fyfield | Public Rights of Way | Total scheme | LEPP168005 | 65000
Bridleway 89 - PROW Improvements | 1) Improvements to the drainage of the surface 2) Ditch clearance and cutting of grips 3) Overlay the surface with road planings and compact firmly | Boggy, undulating and uneven surface which in part has been due to damage caused by misuse which now makes the bridleway a very difficult route to follow | PROW Team | Waltham Abbey | Public Rights of Way | Total scheme | LEPP168003 | 32500 | Not all of bridleway but approximately less than 300m of total length will require extensive work.
Bridleway 66 - PROW Improvements | 1) Improvements to the drainage of the surface 2) Ditch clearance and cutting of grips 3) Overlay the surface with road planings and compact firmly | Boggy, underlating and uneven surface that makes the bridleway a very difficult route to follow | PROW Team | Waltham Abbey | Public Rights of Way | Total scheme | LEPP168002 | 45500 | Approximately 600m of total length will require extensive work. Representation received from local horse riding community for the need to attend to this bridleway.
A113 London Road, Abridge-Speeding | Request for traffic calming measures to reduce speeds | Many residents feel that traffic passes along the road at speeds over 30mph. Request for traffic calming to reduce speeds of vehicles | Lambourne Parish Council | Lambourne | Traffic Management | Total scheme | LEPP182002 | TBC | Requires speed survey
Burney Drive - Zebra crossing | Request for zebra crossing | Concerns that there is no crossing facility for the children trying to cross Burney Drive in the vicinity of the St John Fisher Catholic Primary School | District Councillor | Loughton | Walking | Total scheme | LEPP183004 | N/A | Against policy. The pedestrian / vehicle conflict (PV2) survey over 7 days was 0.071 x 10^8. Where the value of a PV2 is below 0.2 then a crossing point would not be justified.
Woodside, Thornwood Common - Traffic Management Improvements | Request for traffic calming measures | Concerns of speeding and lack of footway | County Member | Thornwood | Traffic Management | Total scheme | LEPP182019 | N/A | The speed survey results do not indicate a speeding issue on Woodside. The speed survey results were as follows; Location of speed survey by the TP, 70m W of j/w Duck Lane Posted speed limit 30mph South-eastbound average 25.6mph, North-westbound average 25.3mph
Thornwood Common - Village Signs | Request for village signs | There are no place name signs as you enter or leave Thornwood Common. It was felt that these should be introduced with a 'drive carefully though our village' sub-plate below | County Member | Thornwood | Traffic Management | Total scheme | LEPP182020 | TBC | Require locations of the signs, as already signs on the main road coming from Hastingwood roundabout
Chigwell Lane j/w Oakwood Hill - Traffic management improvements | Request for improved access to right hand filter lane junction at Chigwell Lane and Oakwood Hill and staggered junction with Langston Road, Loughton | Currently the right hand filter lane is often blocked by traffic waiting to proceed towards Chigwell resulting in drivers driving onto grassed central reservation which is now deeply rutted. Traffic flows could be increased by reducing width of central reservation. Air pollution would also be reduced if more vehicles could access this filter lane. Phasing of the traffic lights should also be considered to allow more vehicles to turn into Oakwood Hill | District Councillor | Loughton | Traffic Management | Total scheme | LEPP182021 | TBC | In validation.
Meridian Way - Zebra crossing | Request for zebra crossing | Concerns regarding lack of crossing facility | District Councillor | Waltham Abbey | Walking | Total scheme | LEPP183005 | N/A | Against policy. The speed limit at this location is 40mph therefore automatically rules out the possibility to install a zebra crossing. The pedestrian / vehicle conflict (PV2) survey over 7 days was 0.049 x 10^8. Where the value of a PV2 is below 0.2 then a crossing point would not be justified.
Hemnall Street , Epping -Traffic calming | Request for traffic calming | Concerns of vehicles speeding making it difficult for pedestrians to cross the road. Vehicles use this as a cut through to circumvent traffic on the High Street | Cllr Whitbread | Epping | Traffic Management | Total scheme | LEPP182022 | N/A | The speed survey results do not indicate a speeding issue on Hemnall Street. The speed survey results were as follows; Location of speed survey by the railings, 20m N of j/w Theydon Grove Posted speed limit 30mph South-westbound average 28.3mph, North-eastbound average 27.7mph.
Hemnall Street , Epping - Footway | Installation a footway and dropped kerbing as there is currently no footpath | There is currently no footpath and pedestrians including school children are walking in the road | Cllr Whitbread | Epping | Walking | Total Scheme | LEPP133015 | TBC | Awaiting completion of feasibility study.
Dobbs Weir, Roydon - Footway | Installation of footway between Eldon Road and Lee Valley Regional Park Authority entrance as per recommendation of feasibility study | There is currently no footway between Eldon Road and Lee Valley Regional Park Authority entrance | Cllr Jackson | Roydon | Traffic Management | Total scheme | LEPP162069 | 93500 | Installation of footway as per recommendation of feasibility study.
Forest Lane j/w New Forest Lane & Manor Road - Junction improvement | Implementation of measures identified in the feasibility for safety improvements at the junction | Safety concerns as there have been a number of collisions at this junction. | Cllr Mohindra | Chigwell | Traffic Management | Feasibility | LEPP162066 | TBC | Awaiting completion of feasibility study.
Manor Road - Signage | Request to replace missing 'Welcome to Chigwell' sign Located outside 8 Manor Road, opposite Repton Park | Resident has requested the “Welcome to Chigwell – Epping Forest” sign be replaced. Apparently there was a sign but this was knocked down several years ago and never replaced | Cllr Mohindra | Chigwell | Traffic Management | Total Scheme | LEPP182023 | TBC | Awaiting highway boundary information.
The Broadway - Central reservation | Request for measures to prevent the damage to the central reservations caused by the overrun from vehicles | The local Town Centre Partnership is asking for remedial works to the grassed area in the central reservations along The Broadway. They are keen to keep the greenery but the continual damage caused by vehicles has meant the area is more muddy than green | Cllr Mohindra | Loughton | Traffic Management | Total Scheme | LEPP152086 | TBC | In validation.
Sewardstone Road j/w Mott Street - Mini roundabout | Request for a new mini-roundabout which would ideally be placed on the junction with Mott Street and for warning signs on Sewardstone Road in both directions to slow down as they approach a new mini roundabout | Concerns raised that the traffic heading North bound on Sewardstone Road rarely respect the 30mph speed limit and often emerge from the blind corner to threaten a collision with any (slow-moving / accelerating) vehicles emerging from Mott St, turning right towards Waltham Abbey outside ‘The Plough’ | Cllr Gadsby | Waltham Abbey | Traffic Management | Total Scheme | LEPP182025 | TBC | Need to complete speed surveys.
Epping - Historic market town signs | Request to replace existing signs with (ETC LOGO) EPPING MARKET CHARTER GRANTED 1253 TWINNED WITH EPPINGEN, GERMANY | The market is a key part of Epping’s history and all evidence, including Epping Forest District Council’s Local Plan, identify preserving the market and character of this historic market town. The signage into Epping is quite poor for a town of this size and makes no mention of the important chartered market status. | Cllr Whitbread | Epping | Traffic Management | Total Scheme | LEPP182026 | TBC | HLO liaising with Town Council and County Member to clarify locations and whether signs will be funded by Town Council or via LHP.
Shernbroke Road, Haywood Court and Milhoo Court - Dropped kerbs | Request for dropped kerbs along Shernbroke Road, Haywood Court and Milhoo Court | Cllr Gadsby has met with a resident who has a health condition and needs to use a mobility scooter to take children to school at Leverton Primary in Honey Lane. Needs dropped kerbs along a number of roads along the route in order to safely negotiate pavements to school. Currently has to go in the road or take a much longer route to get children to school. | Cllr Gadsby | Waltham Abbey | Walking | Total Scheme | LEPP183006 | TBC | Awaiting highway boundary information.
Lindsey Street - Traffic calming | Request for traffic calming measures | Local residents are concerned by speeding vehicles, pedestrian safety and parking issues, From the junction with Shaftesbury Road to the end of Lindsey Street/ Bury Road. | Cllr Whitbread | Epping | Traffic Management | Total Scheme | LEPP182028 | TBC | Requires speed surveys.
Forest Drive, Theydon Bois-Feasibility | Request for a feasibility study to improve the shopping area in Theydon Bois to be delivered by Third Party Team as study would be funded by Theydon Bois Parish Council | To produce a feasibility study looking at potential ways of enhancing the shopping area in Theydon Bois. This would focus on ways to improve the overall ‘attractiveness’ or the area as well as looking at potential ways to address the parking issues in this central area of the Village. The aim being to enhance the viability of the shops and businesses in the Village. | Parish Council/Cllr Whitbread | Theydon Bois | Traffic Management | Feasibility | LEPP182029 | TBC | All third party schemes are assessed under the LHP validation process.
Sewardstone Road, on the western side of the road approximately opposite the Bakers Arms - Barrier | The request is for the installation of suitable physical barriers at either end of the path to prevent access by all vehicles | There have been a considerable number of large fly tips often containing hazardous materials, namely asbestos, on the pavement opposite the Bakers Arms. The pavement is concealed by large bushes and trees. Large vehicles are able to gain access to this area at the southern end of the line of bushes and trees by crossing the verge. Posts have previously been installed at the northern end, close to a field entrance but one has been removed which also allows vehicular access at that point. | Cllr Gadsby | Waltham Abbey | Traffic Management | Total Scheme | LEPP182030 | TBC | Awaiting highway boundary information.
B184, Beauchamp Roding - Speed limit change | Request for 40 mph speed limit (currently 60 mph) from a point north of Corn Barn Mews to a point south of The Room in the Rodings | The Parish consists of approximately 250 homes spread over a wide geographical area. The residents approached the Parish Council with their concerns over speeding and overtaking requesting for the speed limit to be reduced to 40mph. | Parish Council/Cllr McEwen | Beauchamp Roding | Traffic Management | Total Scheme | LEPP182031 | TBC | Requires speed surveys.
Manor Road, Lambourne End - Traffic calming | Parish have requested for speed survey to be completed to ascertain the extent of the speeds and request the speed limit is changed | Concerns of speeding | Parish Council/Cllr McEwen | Lambourne | Traffic Management | Total Scheme | LEPP182032 | TBC | Requires speed surveys.
Church Lane to The Rabbits bus stop- Footway | Installation of footpath to make access to The Rabbits bus stop easier for residents that live down Church Lane as per detailed design. | No footpath form Church Lane to The Rabbits bus stop from Church Lane | Cllr McEwen | Stapleford Abbotts | Walking | Implementation | LEPP163001 | 27500 | Installation of footpath as per detailed design.
Pick Hill, Waltham Abbey | To implement the recommendation of feasibility report | Vehicles are finding it very difficult to for two-way traffic to pass | Cllr Webster | Waltham Abbey | Traffic Management | Total scheme | LEPP162065 | TBC | Awaiting completion of feasibility report.
Duck Lane, Thornwood - Traffic Calming | Request for traffic calming measures. | The road is used as a cut through from Woodside to avoid the Woodside/ High Road junction. There has been increased parking problems in Duck Lane in recent years with parking in both sides. Cars using this lane as a cut through are not paying attention and travelling too fast. Local residents have wondered what could be done to address the problem. Which also impacts on Weald Hall Lane junction which is already effected by the parking issues and industrial site | Cllr Whitbread | Thornwood | Traffic Management | Total scheme | LEPP182033 | TBC | Speed survey required.
Meads Path, Loughton - Handrails | Request for handrails to assist mobility impaired pedestrians on steep part of path | There is a steep part of path on Meads Path as it exits Church Hill and Uplands, making it very difficult for mobility impaired pedestrians trying to walk along this path | Cllr Chris Pond | Loughton | Walking | Total scheme | LEPP193001 | TBC | In validation.
Staples Way and Forest Way, Loughton - Street lighting | Request to replace old concrete lamp columns with conservation style units | There are two concrete lamp columns in Staples Way and Forest Way which are both in a conservation area ,residents and Town Council would like them replaced with conservation style units | Cllr Chris Pond | Loughton | Walking | Total scheme | LEP193002 | TBC | In validation.
Epping Road, Broadley Common | Request for a VAS | Residents are concerned that many vehicles speed along this road, including a bus that then hit a brick wall | Cllr Jackson | Roydon | Traffic Management | Total scheme | LEP192001 | TBC | Requires a speed survey.
High Street jw Towpath to Roydon Marina, Roydon - Road markings | Request for road marking to assist vehicles turning right to the Marina and prevent queuing on the level crossing | Roydon Parish Council have raised concerns regarding the lack of road marking and signage when vehicles turning right to the Marina travelling from Stansted Abbots are unable to due to traffic blocking access this then means traffic backs up over the level crossing becoming stuck on the level crossing which is a safety concern | Cllr Jackson | Roydon | Traffic Management | Total scheme | LEP192002 | TBC | In validation.
Crown Hill, Upshire - Traffic calming | Request for traffic calming | Residents have raised concerns about the speeds of vehicles, particularly HGV travelling along this road | Cllr Gadsby | Upshire | Traffic Management | Total scheme | LEPP192003 | TBC | In validation.
A113, Ongar Road, Abridge - Bus stop | Request for a bus stop hardstanding opposite 121 Ongar Road | Currently the bus stop pole and flag is located on a grass verge | Cllr McEwen | Lambourne | Passenger Transport | Total scheme | LEPP195001 | TBC | In validation.
A113, Ongar Road, Abridge - Traffic management improvements | Request for the following signing and lining measures 1) Double Bend red triangle warning sign (preferably incorporating right hand turn) Church Lane RM4 1AB and 143 Ongar Road RM4 1UL 2) Double-sided raised two way reflective chevrons (preferably with crash barrier) on bend opposite 121 to 143 Ongar Rd, RM4 1UL 3) Unbroken double white lines in centre of carriageway in same location as 2 4) No parking loading or unloading red line or vertical double yellow lines in front of or on kerb outside 121 to 143 Ongar Rd, RM4 1UL 5) No parking at any time on verge or footway signage on verges and pavement at this location | Following a fatal accident on the bend outside 121 Ongar Road, RM4 1UL. Cllr McEwen and Lambourne Parish Councillor Pat Price, Charles Portou Chair of Hillmans Cottages Management Company presented a signed petition from 16 disaffected residents and key stakeholder to Cllr Bentley at surgery meeting on the 18/12/2018 that not only sought a reduction in the speed limit but also appropriate other signage and other accident prevention measures | Cllr McEwen | Lambourne | Traffic Management | Total scheme | LEPP192004 | TBC | In validation.