## 2019-20
Rochford District Highway Works Summary - 2019/20 | [6 empty] | DISTRICT | ROCHFORD
REF | Parish/Ward | Road Name | Location | Type of Work Required | Comments | Confirm Number | Date Requested | Date Completed | STATUS
ROC194001 | Great Wakering | POYNTERS LANE | LHS of Jasmine | OGRO | Ra2=1x2 Visibility splay to be cut into vegetation on verge. Possible job for RANGERS | 3309437 | 2018-12-24 10:24 | 25.4.19
ROC194002 | Rochford | CHERRY ORCHARD WAY | Adj LC J18 / 50 meters before Hall Road Roundabout | OGRO | Ra4=1x4 Rochford/Rayleigh Large White Directional Sign obscured by vegetation on the approach (cannot see sign information until approx 3 meters from sign). Cut back where necessary. Possible job for RANGERS or RDC | 3281922 | 2018-11-06 13:37 |  | long length wide cuttimg no pavement 100 meters of small trees need cutting
ROC194003 | Hockley | FOOTPATH FROM OSBORNE AVENUE TO HOCKLEY | Between 26, 12 remote footway to Os 14 | OGRO | Ra4=2x2 Weeds ,shubs and veg over growing footway needs cutting back and weed spraying . Approx 50mts JOB FOR RANGERS | 3130489 | 2017-07-04 10:15 | 5.4.19
ROC194004 | Rochford | footpath 19 Rochford | Opp 96 | PRVE | Ra4=1x4 Vegetation blocking entrance to Public Footpath 19. Job for RANGERS | 3239645 | 2018-07-03 12:19 | 5.4.19
ROC194005 | Great Wakering | NEW ROAD | Between 36 - 88 | OGRO | Ra2=1x2 Vegetation from field hedging encroaching into carriageway and clipping wing mirrors when 2 Cars pass for approx 300 meters. Possible job for RANGERS | 3290137 | 2018-11-20 12:33 |  | flail strim hedge cut
ROC194006 | Rayleigh | HIGH STREET | Os 94 (Taylor's) | OGRO | Ra3=3x1 Small Tree branch hanging down adj small trunk. Job for RANGERS | 3349622 | 2019-03-29 08:54 | 24.4.19
ROC194007 | Rawreth | OLD CHELMSFORD ROAD | Opp Moat Farm Os Witherdens Farm | OGRO | Ra4=2x2 Trees and veg over growing c/way 65mts needs cutting back. JOB FOR RANGERS | 3128112 | 2017-06-23 14:10 | 24.4.19
ROC194008 | Rayleigh | GREAT WHEATLEY ROAD | Side of Rosedale | DEB | Ra4=1x4 Cut Vegetation in 3 piles blocking footpath, approx 20 meters in total. Possible job for RANGERS | 3348207 | 2019-03-27 10:16 | 24.4.19
ROC194009 | Great Wakering | WAKERING ROAD | Approx 40 meters South of Poynters Lane Junction | OGRO | Ra4=1x4 Vegetation encroaching across bus stop for approx 10 meters. Job for RANGERS | 3311507 | 2019-01-03 14:24 | 25.4.19
ROC194010 | Rochford | SOUTHEND ROAD | Opp 153 | OGRO | Ra2=1x2 Vegetation encroaching into footway for approx 5 meters from verge. Job for RANGERS | 3290615 | 2018-11-21 09:02 | 1.4.19
ROC194011 | Rochford | SOUTHEND ROAD | Opp 163 | OGRO | Ra2=1x2 Vegetation encroaching into footway for approx 20 meters from verge. Job for RANGERS | 3290614 | 2018-11-21 08:59 | 1.4.19
ROC194012 | Rawreth | RAWRETH LANE | Opp 178 - 182 | OGRO | Ra1=1x1 Cut Vegetation left in a piles on verge. Job for RANGERS | 3330326 | 2019-02-13 13:56 | 24.4.19
ROC194013 | Rayleigh | RAWRETH LANE | Os imperial Park Industrial Estate Rawreth Lane. Opp Keep Left centre island. | OGRO | Ra2=1x2 3no large conifer trees over hanging footway and c/way ,passing lorries snapping branches and causing branches to hang down over footway. Possible job for RANGERS | 3319340 | 2019-01-16 14:21 |  | tree team needs road clossure
ROC194014 | Barling Magna | MUCKING HALL ROAD | Os Plough House | OGRO | Ra6=2x3 Bramble hedge fallen forward and protruding into the Carriageway from verge for approx 10 meters in length. Job for RANGERS | 3341710 | 2019-03-11 12:28 | 25.4.19
ROC194015 | Rochford | THE DRIVE | Between 112 and 99 | OGRO | Ra1=1x1 brambles and vegetation encroaching for approx 8 meters at end of cul de sac. Job for RANGERS | 3341894 | 2019-03-11 13:57 | 24.4.19
ROC195001 | Hawkwell | CLEMENTS HALL WAY | Opp LC CH7in hammerhead | OGRO | Ra4=1x4 Weeds and vegetation covering footway for approx 30 meters. Possible job for RANGERS or RDC weed spray. Weeds approx 1.5 meters high | 3245925 | 2018-07-19 10:34 | May
ROC195002 | Hawkwell | AVON CLOSE | Side of 30 | OGRO | Ra1=1x1 Weeds growing along edge of footpath for approx 30 meters both sides. Requires weed spray possible job for RANGERS or RDC weed spray | 3239702 | 2018-07-03 14:40 | May
ROC195003 | Rochford | OXFORD ROAD | Between 2 - 10 | OGRO | Ra1=1x1 Weeds growing along kerbline on carriageway and footway for approx 800 meters both sides. Requires weed spray possible job for RANGERS or RDC weed spray | 3239689 | 2018-07-03 13:42 | May
ROC195004 | Rochford | OAST WAY | Rear of 11-9 Middlemead | OGRO | Ra2=1x2 Tall weeds growing up along footway back edge for approx 15 meters requires removal, job for RANGERS or RDC weed spray | 3246195 | 2018-07-20 09:05 | May
ROC195005 | Rochford | SUTTON ROAD | Opp 70 | OGRO | Ra1=1x1 Vegetation growing around wooden pole and encroaching onto overhead cables. Possible job for RANGERS | 3332892 | 2019-02-20 09:31 | May
ROC195006 | Rayleigh | RAWRETH LANE | Os imperial Park Industrial Estate Rawreth Lane. Opp Keep Left centre island. | OGRO | Ra2=1x2 3no large conifer trees over hanging footway and c/way ,passing lorries snapping branches and causing branches to hang down over footway. Possible job for RANGERS | 3319340 | 2019-01-16 14:21 | May
ROC195007 | Great Wakering | POYNTERS LANE | LHS of Jasmine | OGRO | Ra2=1x2 Visibility splay to be cut into vegetation on verge. Possible job for RANGERS | 3309437 | 2018-12-24 10:24 | May
ROC195008 | Rochford | OAST WAY | Rear of 15 Middlemead | OGRO | Ra2=1x2 Tall weeds growing up along footway back edge for approx 5 meters requires removal, job for RANGERS or RDC weed spray | 3246194 | 2018-07-20 09:03 | May
ROC195009 | Great Wakering | ALEXANDRA ROAD | Between 10 - 177 both sides | OGRO | Ra1=1x1 Minor weeds growing up along kerb line, requires weed spray, approx 800 meters. Possible job for RANGERS or RDC weed spray | 3236912 | 2018-06-22 11:31 | May
ROC195010 | Rochford | CHERRY ORCHARD WAY | Adj LC J18 / 50 meters before Hall Road Roundabout | OGRO | Ra4=1x4 Rochford/Rayleigh Large White Directional Sign obscured by vegetation on the approach (cannot see sign information until approx 3 meters from sign). Cut back where necessary. Possible job for RANGERS or RDC | 3281922 | 2018-11-06 13:37 | May
ROC195011 | Rochford | THE BOULEVARD | Os 1-7 | OGRO | Ra1=1x1 Grass from verges encroaching into footway for approx 30 meters. Needs Siding. Job for RANGERS | 3341810 | 2019-03-11 14:12 | May
ROC195012 | Hockley | FOOTPATH FROM OSBORNE AVENUE TO HOCKLEY | Between 26, 12 remote footway to Os 14 | OGRO | Ra4=2x2 Weeds ,shubs and veg over growing footway needs cutting back and weed spraying . Approx 50mts JOB FOR RANGERS | 3130489 | 2017-07-04 10:15 | May
ROC195013 | Rochford | OAST WAY | Rear of 21-19 Middlemead | OGRO | Ra2=1x2 Tall weeds growing up along footway back edge for approx 10 meters requires removal, job for RANGERS or RDC weed spray | 3246193 | 2018-07-20 09:02 | May
ROC195014 | Rochford | footpath 19 Rochford | Opp 96 | PRVE | Ra4=1x4 Vegetation blocking entrance to Public Footpath 19. Job for RANGERS | 3239645 | 2018-07-03 12:19 | May
ROC195015 | Rochford | OAST WAY | Rear of 23-25 Middlemead | OGRO | Ra2=1x2 Tall weeds growing up along footway back edge requires removal, job for RANGERS or RDC weed spray | 3246192 | 2018-07-20 08:55 | May
ROC195016 | Rochford | MORNINGTON AVENUE | Os 27 | OGRO | Ra2=1x2 weeds growing along concrete dish channel for approx 40 meters. Needs siding . Job for RANGERS | 3252413 | 2018-08-08 14:15 | May
ROC195017 | Rayleigh | VERNON AVENUE | Adj LC 7 | OGRO | Ra2=1x2 Grass from verges encroaching into footway for approx 20 meters. Needs Siding job of RANGERS | 3323987 | 2019-01-28 15:32 | May
ROC195018 | Rochford | MORNINGTON AVENUE | Between 3 - 15 | OGRO | Ra2=1x2 weeds growing along concrete dish channel for approx 80 meters. Needs siding . Job for RANGERS | 3252408 | 2018-08-08 14:03 | May
ROC195019 | Canewdon | SYCAMORE WAY | Opp 1 Chestnut Path | OGRO | Ra2=2x1 Vegetation from grass verge encroaching into FW for approx 40 meters. Needs Siding. Job for RANGERS | 3106576 | 2017-04-11 10:18 | May
ROC195020 | Canewdon | SYCAMORE WAY | Opp 10 | OGRO | Ra2=1x2 Grass from verge encroaching into FW for approx 10 meters. Needs Siding. Job for RANGERS | 3106569 | 2017-04-11 13:16 | May
ROC195021 | Rochford | MORNINGTON AVENUE | Side of 90 Stambridge Road | OGRO | Ra2=1x2 weeds growing along concrete dish channel for approx 40 meters. Needs siding . Job for RANGERS | 3252407 | 2018-08-08 14:00 | May
ROC195022 | Canewdon | SYCAMORE WAY | Opp 8 Chesnut Path | OGRO | Ra2=2x1 Vegetation from grass verge encroaching into FW both sides for approx 10 meters. Needs Siding. Job for RANGERS | 3106546 | 2017-04-11 10:16 | May
ROC195023 | Canewdon | SYCAMORE WAY | Opp 8 Chesnut Path | OGRO | Ra2=2x1 Vegetation from grass verge encroaching into FW both sides for approx 20 meters. Needs Siding. Job for RANGERS | 3106544 | 2017-04-11 10:13 | May
ROC195024 | Canewdon | SYCAMORE WAY | 5 meters North of 1 Village Green | OGRO | Ra2=2x1 Vegetation from grass verge encroaching into FW both sides for approx 20 meters. Needs Siding. Job for RANGERS | 3106541 | 2017-04-11 10:06 | May
ROC195025 | Ashingdon | MOONS CLOSE | Os 8 | OGRO | Ra2=1x2 weeds growing out of footway cracked for 7 meters. Job for RANGERS | 3111179 | 2017-04-26 15:08 | May
ROC195026 | Canewdon | SYCAMORE WAY | Adj 1 Village Green | OGRO | Ra2=2x1 Vegetation from grass verge encroaching into FW both sides for approx 10 meters. Needs Siding. Job for RANGERS | 3106540 | 2017-04-11 10:04 | May
ROC195027 | Rayleigh | MILTON CLOSE | Adj LC FP8 | OGRO | Ra2=1x2 vegetation from back edge encroaching into footway for approx 100 meters. Possible job for RANGERS | 3274608 | 2018-10-19 13:09 | May
ROC195028 | Rochford | SUTTON ROAD | Between 47 to Purdeys Way | OGRO | Ra2=1x2 Brambles sticking out into footway for approx 500 meters (nettles cut back but Spikey brambles sticking out) cut back where necessary. Possible job for RANGERS | 3239644 | 2018-07-03 12:16 | May
ROC195029 | Rochford | SPENCER GARDENS | Between Oxford Road and Vaughan Close | OGRO | Ra1=1x1 Weeds growing along kerbline on carriageway and footway for approx 100 meters both sides. Requires weed spray possible job for RANGERS or RDC weed spray | 3239693 | 2018-07-03 13:49 | May
ROC195030 | Rochford | SOUTHEND ROAD | Opp 153 | OGRO | Ra2=1x2 Vegetation encroaching into footway for approx 5 meters from verge. Job for RANGERS | 3290615 | 2018-11-21 09:02 | May
ROC195031 | Rayleigh | LOUIS DRIVE WEST | Opp 105 | OGRO | Ra6=2x3 Bush from verge protruding into carriageway for 1 meter . Job for RANGERS | 3360774 | 2019-04-23 15:25 | May
ROC195032 | Rochford | SOUTHEND ROAD | Opp 163 | OGRO | Ra2=1x2 Vegetation encroaching into footway for approx 20 meters from verge. Job for RANGERS | 3290614 | 2018-11-21 08:59 | May
ROC195033 | Rochford | LEICESTER AVENUE | Side of 54 Sutton Court Drive | OGRO | Ra4=2x2 Two 10 meter sections of grass verge needs siding. Also a 10 meter section of minor brambles need removal. Job for RANGERS | 20384944 | 2017-01-27 13:45 | May
ROC195034 | Great Wakering | SOUTHEND ROAD | Opp Boonwood | OGRO | Ra2=1x2 Weeds encroaching into footway for approx 20 meters. Needs Siding. Job for RANGERS | 3249221 | 2018-07-31 08:28 | May
ROC195035 | Rochford | SUTTON ROAD | Opp 60 | OGRO | Ra1=1x1 Vegetation growing around wooden pole , street lamp head unit and encroaching onto overhead cables. Possible job for RANGERS | 3332902 | 2019-02-20 09:35 | May
ROC195036 | Rochford | ROCHFORD HALL CLOSE | Os 14 | OGRO | Ra1=1x1 Grass from verge encroaching into footway for approx 25 meters. Needs Siding. Job for RANGERS | 3344305 | 2019-03-18 15:31 | May
ROC195037 | Rochford | ROCHFORD HALL CLOSE | Between Southend Road and 3 | OGRO | Ra1=1x1 Grass from 2 verges encroaching into footway for approx 25 meters each. Needs Siding. Job for RANGERS | 3344302 | 2019-03-18 15:36 | May
ROC195038 | Great Wakering | SILCHESTER CORNER | Os 9 - 12 | OGRO | Ra4=1x4 Grass and mud from verges encroaching and growing across grass for approx 30.0x2.0 needs siding. Job for RANGERS | 3312850 | 2019-01-04 10:56 | May
ROC195039 | Rawreth | INDUSTRIAL ESTATE ROAD | Os Franklin Waste Station to junc with Rawreth Lane at various locations. | OGRO | Ra 6=2x3 Shrubs and veg over growing c/way 500mts.needs cutting back various locations where needed. JOB FOR RANGERS | 3363619 | 2019-04-30 10:29 | May
ROC195040 | Rayleigh | RONALD DRIVE | Opp 22 | OGRO | Ra4=1x4 Small blossom tree branches hanging low over footway . Job for RANGERS | 3361064 | 2019-04-24 08:42 | May
ROC195041 | Rochford | ROCHFORD GARDEN WAY | Os 129 | OGRO | Ra1=1x1 Grass from verges encroaching into footway for approx 30 meters. Needs Siding. Job for RANGERS | 3342496 | 2019-03-12 11:54 | May
ROC195042 | Hawkwell | RECTORY ROAD | Between opposite 194-210 | OGRO | Ra2=1x2 Vegeatation from back edge encroaching into the footway, needs siding for approx 100 meters. FW width 1.3 meters, veg encroaching 400mm. Job for RANGERS | 3318104 | 2019-01-14 15:07 | May
ROC195043 | Great Wakering | NEW ROAD | Between 36 - 88 | OGRO | Ra2=1x2 Vegetation from field hedging encroaching into carriageway and clipping wing mirrors when 2 Cars pass for approx 300 meters. Possible job for RANGERS | 3290137 | 2018-11-20 12:33 | May
ROC195044 | Hawkwell | PRINCESS GARDENS | Os 19 - 21 | OGRO | Ra1=1x1 Grass from verge encroaching into footway for approx 20 meters. Needs siding. Job for RANGERS | 3269327 | 2018-10-03 13:36 | May
ROC195045 | Hawkwell | PRINCESS GARDENS | Opp 53 | OGRO | Ra1=1x1 Grass from verge encroaching into footway for approx 20 meters. Needs siding. Job for RANGERS | 3269319 | 2018-10-03 14:24 | May
ROC195046 | Rayleigh | HIGH STREET | Os 94 (Taylor's) | OGRO | Ra3=3x1 Small Tree branch hanging down adj small trunk. Job for RANGERS | 3349622 | 2019-03-29 08:54 | May
ROC195047 | Canewdon | SYCAMORE WAY | Os 7 RH VX | OGRO | Ra2=1x2 Vegetation encroaching into footway for approx 8 meters. Needs Siding. Job for RANGERS | 3280221 | 2018-11-05 09:13 | May
ROC195048 | Rayleigh | DANBURY ROAD | Os 43 | OGRO | Ra2=1x2 Grass from verges encroaching into footway for approx 10 meters, needs siding job for RANGERS | 3340462 | 2019-03-07 10:35 | May
ROC195049 | Hawkwell | PRINCESS GARDENS | Side of 66 Harewood Avenue | OGRO | Ra1=1x1 Grass from verge encroaching into footway for approx 20 meters. Needs siding. Job for RANGERS | 3269316 | 2018-10-03 13:58 | May
ROC195050 | Rayleigh | HOCKLEY ROAD | Os 141a - 141 | OGRO | Ra1=1x1 Grass from verge encroaching 400mm into footway for approx 15 meters Needs Siding. Job for RANGERS. FW width 1.8 | 3346410 | 2019-03-22 10:42 | May
ROC195051 | Barling Magna | MUCKING HALL ROAD | Os Plough House | OGRO | Ra6=2x3 Bramble hedge fallen forward and protruding into the Carriageway from verge for approx 10 meters in length. Job for RANGERS | 3341710 | 2019-03-11 12:28 | May
ROC195052 | Hawkwell | PRINCESS GARDENS | Os 20 - 18 | OGRO | Ra1=1x1 Grass from verge encroaching into footway from three sections for approx 25 meters. Needs siding. Job for RANGERS | 3269315 | 2018-10-03 13:53 | May
ROC195053 | Hawkwell | PRINCESS GARDENS | Os 14 - 12 | OGRO | Ra1=1x1 Grass from verge encroaching into footway for approx 15 meters. Needs siding. Job for RANGERS | 3269314 | 2018-10-03 13:52 | May
ROC195054 | Hawkwell | PRINCESS GARDENS | Os 8 | OGRO | Ra1=1x1 Grass from verge encroaching into footway for approx 8 meters. Needs siding. Job for RANGERS | 3269312 | 2018-10-03 13:48 | May
ROC195055 | Rayleigh | HOCKLEY ROAD | Os 147 | OGRO | Ra2=1x2 Grass and mud encroaching 700mm into footway for approx 18 meters Needs Siding. Job for RANGERS. FW width 1.7 | 3346409 | 2019-03-22 10:38 | May
ROC195056 | Great Wakering | HIGH STREET | Os 333 | OGRO | Ra1=1x1 Grass from verges encroaching into footway for approx 10 meters. Needs siding job for RANGERS | 3311137 | 2019-01-02 11:44 | May
ROC195057 | Great Wakering | HIGH STREET | Os 331 | OGRO | Ra1=1x1 Grass from verges encroaching into footway for approx 15 meters. Needs siding job for RANGERS | 3311133 | 2019-01-02 11:36 | May
ROC195058 | Rayleigh | GREAT WHEATLEY ROAD | Side of Rosedale | DEB | Ra4=1x4 Cut Vegetation in 3 piles blocking footpath, approx 20 meters in total. Possible job for RANGERS | 3348207 | 2019-03-27 10:16 | May
ROC195059 | Rayleigh | GRANGE GARDENS | Junction of London Road Service Road and Grange Gardens | OGRO | Ra2=1x2 Grass encroaching into footway for approx 8 meters , Needs siding job for RANGERS | 3340225 | 2019-03-07 08:34 | May
ROC195060 | Ashingdon | GOLDEN CROSS ROAD | Side of 24 Canewedon View Road | OGRO | Ra2=1x2 Grass from verges encroaching into footway on 2 sections approx 15 meters total. Needs siding. Job for RANGERS | 3261143 | 2018-09-05 10:52 | May
ROC195061 | Ashingdon | GOLDEN CROSS ROAD | Os 2 | OGRO | Ra2=1x2 Grass from verges encroaching into footway on 2 sections approx 18 meters total. Needs siding. Job for RANGERS | 3261142 | 2018-09-05 11:24 | May
ROC195062 | Rayleigh | FERNDALE ROAD | Opp 51 | OGRO | Ra4=1x4 Brambles from hedge on verge hanging down in footway for approx 3 meters. Job for RANGERS | 3345409 | 2019-03-20 13:08 | May
ROC195063 | Rayleigh | Fpath From Albany Rd To Brocksford Ave | Side 27 remote footway Brocksford Ave to Albany Rd | OGRO | Ra1=1x1 Weeds and veg growing through footway surface at both sides for approx 40 meters. Job for RANGERS | 3352601 | 2019-04-04 12:42 | May
ROC195064 | Rawreth | OLD CHELMSFORD ROAD | Opp Moat Farm Os Witherdens Farm | OGRO | Ra4=2x2 Trees and veg over growing c/way 65mts needs cutting back. JOB FOR RANGERS | 3128112 | 2017-06-23 14:10 | May
ROC195065 | Rochford | DALYS ROAD | Os 27 - 25 | OGRO | Ra2=1x2 Grass from verge encroaching into footway for approx 30 meters. Needs siding. Job for RANGERS | 3263083 | 2018-09-11 14:40 | May
ROC195066 | Canewdon | CHESTNUT PATH | Os 1-7 | OGRO | Ra1=1x1 Grass from verges encroaching into footway for approx 40 meters. Encroaching 500mm in to FW. FW width 2 meters. Needs Siding job for RANGERS | 3358834 | 2019-04-16 13:11 | May
ROC195067 | Canewdon | CHESTNUT PATH | Os 8 - 11 | OGRO | Ra1=1x1 Grass from verges encroaching into footway for approx 40 meters. Encroaching 500mm in to FW. FW width 2 meters. Needs Siding job for RANGERS | 3358832 | 2019-04-16 13:01 | May
ROC195068 | Great Wakering | WAKERING ROAD | Approx 40 meters South of Poynters Lane Junction | OGRO | Ra4=1x4 Vegetation encroaching across bus stop for approx 10 meters. Job for RANGERS | 3311507 | 2019-01-03 14:24 | May
ROC195069 | Rawreth | RAWRETH LANE | Opp 178 - 182 | OGRO | Ra1=1x1 Cut Vegetation left in a piles on verge. Job for RANGERS | 3330326 | 2019-02-13 13:56 | May
ROC195070 | Rayleigh | LOUIS DRIVE EAST | RH junction of Louis Drive East | OGRO | Ra2=1x2 grass from verges encroaching into footway for approx 8 meters. Needs Siding. Job for RANGERS | 3361649 | 2019-04-24 15:16 | May
ROC195071 | Rayleigh | WATERY LANE | Between Lower Road and small bridge | OGRO | Ra2=1x2 Hedges either side encroaching into carriageway for approx 50 meters. Possible job for RANGERS | 3262187 | 2018-09-07 16:17 | May
ROC195072 | Rayleigh | LOUIS DRIVE EAST | Between 27 - 37 | OGRO | Ra2=1x2 grass from verges encroaching into footway for approx 50meters. Needs Siding. Job for RANGERS | 3361633 | 2019-04-24 14:45 | May
ROC195073 | Rayleigh | WARWICK GARDENS | Side of 89 Warwick Road | OGRO | Ra1=1x1 Grass from verges encroaching into footway for approx 40 meters. Needs Siding job for RANGERS | 3352587 | 2019-04-04 12:02 | May
ROC195074 | Rochford | THE DRIVE | Between 112 and 99 | OGRO | Ra1=1x1 brambles and vegetation encroaching for approx 8 meters at end of cul de sac. Job for RANGERS | 3341894 | 2019-03-11 13:57 | May
ROC195075 | Rayleigh | WARWICK GARDENS | Side of 95 Warwick Road | OGRO | Ra1=1x1 Grass from verge encroaching into footway for approx 40 meters. Needs Siding job for RANGERS | 3352586 | 2019-04-04 13:21 | May
ROC195076 | Rawreth | CHURCH ROAD | O/s st Nicholas house from opp the forge nurseries to opp footway to the church entrance | OGRO | Ra4 1x4 hedge overhanging the fw (rangers ) | 3363503 | 2019-04-30 10:09 | May
ROC195077 | Canewdon | CEDAR WALK | Opp 2 | OGRO | Ra1=1x1 Grass from verges encroaching into footway for approx 15 meters. Encroaching 500mm in to FW. FW width 1.8 meters. Needs Siding job for RANGERS | 3358925 | 2019-04-16 13:58 | May
ROC195078 | Rayleigh | ALEXANDRIA DRIVE | Side 185 on Junc with London Rd Service Rd | OGRO | Ra2=1x2 grass from verge encroaching into footway for approx 20 meters. Needs Siding. Job for RANGERS | 3361359 | 2019-04-24 12:30 | May
ROC195079 | Rochford | OXFORD ROAD | Between 2 - 10 | OGRO | Ra1=1x1 Weeds growing along kerbline on carriageway and footway for approx 800 meters both sides. Requires weed spray possible job for RANGERS or RDC weed spray | 3239689 | 2018-07-03 13:42 | 1.5.19
ROC195080 | Rochford | OAST WAY | Rear of 11-9 Middlemead | OGRO | Ra2=1x2 Tall weeds growing up along footway back edge for approx 15 meters requires removal, job for RANGERS or RDC weed spray | 3246195 | 2018-07-20 09:05 | 1.5.19
ROC195081 | Rochford | OAST WAY | Rear of 15 Middlemead | OGRO | Ra2=1x2 Tall weeds growing up along footway back edge for approx 5 meters requires removal, job for RANGERS or RDC weed spray | 3246194 | 2018-07-20 09:03 | 1.5.19
ROC195082 | Rochford | OAST WAY | Rear of 21-19 Middlemead | OGRO | Ra2=1x2 Tall weeds growing up along footway back edge for approx 10 meters requires removal, job for RANGERS or RDC weed spray | 3246193 | 2018-07-20 09:02 | 1.5.19
ROC195083 | Rochford | OAST WAY | Rear of 23-25 Middlemead | OGRO | Ra2=1x2 Tall weeds growing up along footway back edge requires removal, job for RANGERS or RDC weed spray | 3246192 | 2018-07-20 08:55 | 1.5.19
ROC195084 | Ashingdon | MOONS CLOSE | Os 8 | OGRO | Ra2=1x2 weeds growing out of footway cracked for 7 meters. Job for RANGERS | 3111179 | 2017-04-26 15:08 | 2.5.19
ROC195085 | Rayleigh | MILTON CLOSE | Adj LC FP8 | OGRO | Ra2=1x2 vegetation from back edge encroaching into footway for approx 100 meters. Possible job for RANGERS | 3274608 | 2018-10-19 13:09 | 2.5.19
ROC196001 |  | New Road | North side (footway) New Road especially from number 73 towards church. | Vegetation trimming | The vegetation is completely covering the footway in places causing lack of access to mobility scooter and pushchair users and pedestrians. |  |  | 2019-06-12
ROC196002 |  | Star Lane | West Side Star Lane | Vegetation trimming | The vegetation is completely covering the footway in places causing lack of access to mobility scooter and pushchair users and pedestrians. |  |  | 2019-06-12
ROC197001 | Great Wakering | NEW ROAD | Between 7 - 73 | Vegetation trimming | Ra4=1x4 Vegetation from verge encroaching into footway upto 1.2m . For approx 300 meters in length. Job for RANGERS | 3386841 | 2019-06-26 09:59 | 22.7.19
ROC197002 | Rayleigh | MAINE CRESCENT | Opp LC 1 | Vegetation trimming | Ra2=1x2 Vegetation from verge encroaching into footway by 1 meter for approx 15 meters. Job for RANGERS (FW width 2.0) | 3366779 | 2019-05-09 11:34 | 16.7.19
ROC197003 | Rayleigh | LONDON ROAD | Opp 134 | Vegetation trimming | Ra2=1x2 Vegetation from verge obscuring view from bus shelter and encroaching 300mm into carriageway for approx 10 meters in length. Job for RANGERS | 3378011 | 2019-06-05 12:39 | 9.7.19
ROC197004 | Rayleigh | LONDON ROAD | Opp 138 | Vegetation trimming | Ra2=1x2 Branches from hedge around bus shelter hanging down, approx 20 meters over hedge overgrown. Job for RANGERS | 3378009 | 2019-06-05 12:35 | 9.7.19
ROC197005 | Rayleigh | LONDON ROAD | Opp Pearsons Avenue | Vegetation trimming | Ra2=1x2 Vegetation obscuring visibility splay to Traffic Light Pole 2 and around LC. Splay to be cut by RANGERS job for RANGERS | 3375606 | 2019-05-30 08:59 | 9.7.19
ROC197006 | Rayleigh | LEASWAY | Side of 47 Crown Hill | Vegetation trimming | Ra2=1x2 Nettles encroaching into footway for approx 500mm for approx 25 meters in length. FW width 1.6m Job for RANGERS | 3375488 | 2019-05-29 15:06 | 23.7.19
ROC197007 | Great Wakering | WAKERING ROAD | South of Poynters Lane Junction | Vegetation trimming | Ra2=1x2 Vegetation from verge encroaching into footway for approx 500mm for a length of approx 40 meters (FW width 1.8) Job for RANGERS | 3373949 | 2019-05-23 12:23 | 22.7.19
ROC197008 | Rochford | SUTTON ROAD | Between 47 and Purdeys Way Junction | Vegetation trimming | Ra4=1x4 Vegetation encroaching into footway by 1 meter, for exactly 320 meters in length. Job for RANGERS | 3386950 | 2019-06-26 11:39 | road closure
ROC197009 | Sutton | SHOPLAND ROAD | Between Winters and Old School Cottages | Vegetation trimming | Ra4=1x4 Vegetation from verge encroaching into footway for approx 15 meters. Job for RANGERS also needs siding. ( encroaching 1.2 FW width 1.2 ) | 3367214 | 2019-05-10 09:30 | 9.7.19
ROC197010 | Rayleigh | SHAKESPEARE AVENUE | Opp 9-11 | Vegetation trimming | Ra3=3x1 Nettles and brambles overgrown and climbing property wall. For a length of approx 9 meters on verge. Job for RANGERS | 3372604 | 2019-05-21 12:29 | 9.7.19
ROC197011 | Rayleigh | HILARY CRESCENT | Os 44 | Vegetation trimming | Ra4=4x1 Small tree branch hanging down onto verge. Removal Job for RANGERS | 3365169 | 2019-05-03 10:32 | 9.7.19
ROC197012 | Canewdon | HIGH STREET | Os Fare Stage and Picasso | Vegetation trimming | Ra6=2x3 Vegetation growing up through footway from centre to back edge and weeds growing up through footway at back edge blocking footway . Encroaching 1.5m into footway (FW width 1.8lm) length of affected area 5.0m. Job for RANGERS | 3375190 | 2019-05-29 09:08 | 25.7.19
ROC197013 | Rayleigh | HIGH ROAD | Opp The side of 2 High Road | Vegetation trimming | Ra2=1x2 Vegetation encroaching into footway for approx 500mm for approx 20 meters. FW width 2.0 meters . Job for RANGERS also needs siding as well | 3383982 | 2019-06-20 08:38 | 24.7.19
ROC197014 | Rayleigh | HIGH ROAD | Between 1a and 19 Spring Gardens in alleyway | Vegetation trimming | Ra2=2x3 Nettles encroaching into footway for approx 1700mm upto for approx 35 meters. Some nettles 1.5 meters high. Job for RANGERS FW width 2.0 meters | 3383981 | 2019-06-20 08:42 | 24.7.19
ROC197015 | Ashingdon | GREENSWARD LANE | By 223 | Vegetation trimming | RA2=1×2 overgrown Vegatation impeding fw 3m Job for RANGERS | 3383885 | 2019-06-19 09:55 | 23.7.19
ROC197016 | Rayleigh | DEEPDENE AVENUE | Os 26 | Vegetation trimming | Ra1=1x1 Grass from verges encroaching into footway by 300mm for approx 5 meters . Needs siding job for RANGERS | 3383675 | 2019-06-19 11:07 | 23.7.19
ROC197017 | Rayleigh | CROWN HILL | Between 49 - 67 (Worst area 49 - 59) | Vegetation trimming | Ra3=1x3 Vegetation encroaching into footway for approx 900mm for approx 125 meters in length. FW width 1.6m Job for RANGERS | 3375495 | 2019-05-29 15:08 | 24.7.19
ROC197018 | Rayleigh | BROOK ROAD | Opp Unit 13 - 15 | Vegetation trimming | Ra3=1x3 Vegetation from verge encroaching across footway width for approx 50 meters. Job for RANGERS | 3381426 | 2019-06-13 16:16 | cars parked for work
ROC197019 | Rochford | RECTORY ROAD | LH of Magnolia Road junction | Vegetation trimming | Ra2=1x2 Small tree branches and nettles from verge obscuring view and accessibility to Traffic Light Pole 1 and cabinets for approx 30 meters. Also starting to encroach into carriageway. Job for RANGERS | 3373036 | 2019-05-22 08:57 | cars parked for work
ROC197020 | Rayleigh | BROOK ROAD | Opposite Unit 17 | Vegetation trimming | Ra3=1x3 Vegetation from verge encroaching across footway width for approx 50 meters. Job for RANGERS | 3381424 | 2019-06-13 16:12 | cars parked for work
ROC197021 | Rayleigh | BROOK ROAD | Opp Unit 17-Unit 19 | Vegetation trimming | Ra2=1x2 Vegetation encroaching into footway for approx 75 meters. Job for RANGERS | 3381422 | 2019-06-13 16:09 | cars parked for work
ROC197022 | Rayleigh | BROOK ROAD | Os 45 | Vegetation trimming | Ra3=1x3 Vegetation encroaching into footway for approx 1500mm and upto 1 meters in height for approx 15 meters. Job for RANGERS | 3381405 | 2019-06-13 15:32 | cars parked for work
ROC197023 | Rayleigh | BROOK ROAD | Os Unit 15 | Vegetation trimming | Ra2=1x2 Vegetation encroaching into footway for approx 500mm and upto 1 meters in height for approx 5 meters. Job for RANGERS | 3381379 | 2019-06-13 14:34 | cars parked for work
ROC197024 | Rayleigh | BROOK ROAD | Opp LC BR9 | Vegetation trimming | Ra2=1x2 Vegetation encroaching into footway for approx 1200mm and upto 2 meters in height for approx 18 meters, obscuring sign. Job for RANGERS | 3381375 | 2019-06-13 14:23 | cars parked for work
ROC197025 | Rayleigh | BROOK ROAD | Adj LC BR5 | Vegetation trimming | Ra1=1x1 Brambles covering one way sign on verge . Job for RANGERS | 3374277 | 2019-05-24 09:14 | cars parked for work
ROC197026 | Barling Magna | BARROW HALL ROAD | Side of 87 Little Wakering Road | Vegetation trimming | Ra2=1x2 Weeds growing up from back edge of path encroaching into footway by 500mm, for a length of 30 meters, FW width 1.0m. Job for RANGERS | 3372210 | 2019-05-20 14:21 | 22.7.19
ROC197027 | Barling Magna | BARROW HALL ROAD | Side of 87 Little Wakering Road | Vegetation trimming | Ra1=1x1 Grass from verges encroaching into footway for approx 400mm for a length of approx 30 meters, FW width 1.0. Job for RANGERS | 3372206 | 2019-05-20 14:15 | 22.7.19
ROC197028 | Rochford | ASHINGDON ROAD | ñmñnmmmjjjh1ey3 | Vegetation trimming | Ra4=1x4 Two small trees on verge, branches hanging down as low as 1.6m in height. Job for RANGERS | 3374771 | 2019-05-28 10:10 | 23.7.19
ROC197029 | Rochford | ASHINGDON ROAD | Os Suffolk Court adj LC A16A | Vegetation trimming | Ra2=1x2 Brambles and vegetation overthrowing and obscuring visibility splay for vehicles pulling out of Roche Avenue. Veg approx 15 meters in length on verge. Job for RANGERS | 3374770 | 2019-05-28 09:55 | 22.7.19
ROC197030 | Rayleigh | FOOTPATH FROM LONDON HILL TO ELM DRIVE | Between 41-45 | Vegetation trimming | Ra1=1x1 Nettles encroaching into footway for approx 500mm for approx 15 meters .FW width 1.8m. Job for RANGERS | 3375569 | 2019-05-30 08:27 | 12.7.19
ROC197031 | Rayleigh | Footpath From Nursery Close To Daws Heat | Between LC FP5 and LC FP8 | Vegetation trimming | Ra2=1x2 Stinging nettles encroaching into footway for approx 500mm upto for Approx 100 meters in length down footway. Job for RANGERS | 3378004 | 2019-06-05 12:20 | 12.7.19
ROC197032 | Rayleigh | Footpath From Weir Gardens To High Road | Side of 31a High Road in alleyway | Vegetation trimming | Ra2=1x2 Nettles encroaching into footway for approx 500mm both sides for approx 20 meters in length both sides. ( FW 1.8m) Job for RANGERS | 3374271 | 2019-05-24 08:49 | 12.7.19
ROC197033 | Rayleigh | Footpath From Weir Gardens To High Road | Rear of Gordon Roughley Court in alleyway | Vegetation trimming | Ra2=1x2 Nettles encroaching into footway for approx 500mm both sides for approx 25 meters in length both sides. ( FW 1.8m) Job for RANGERS | 3374270 | 2019-05-24 08:52 | 12.7.19
ROC197034 | Rayleigh | ALEXANDRA ROAD | Side of 64 | Vegetation trimming | Ra6=2x3 Spikey vegetation from verge encroaching into footway by 1 meter. For approx 10 meters in length. FW width 1.8m. Job for RANGERS | 3371438 | 2019-05-17 11:57 | 16.7.19
ROC197035 | Great Wakering | WHITEHALL ROAD | Side of 6 The Cedars | Vegetation trimming | Ra2=1x2 Vegetation from verge encroaching into footway for approx 800mm , length of approx 30 meters. FW width 1.8m Job for RANGERS | 3386826 | 2019-06-26 09:39 | 22.7.19
ROC619001 | Great Wakering | NEW ROAD | Between 7 - 73 | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation from verge encroaching into footway upto 1.2m . For approx 300 meters in length. Job for RANGERS | 3386841 | 2019-06-26 09:59 | 22.7.19
ROC619002 | Rayleigh | MAINE CRESCENT | Opp LC 1 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation from verge encroaching into footway by 1 meter for approx 15 meters. Job for RANGERS (FW width 2.0) | 3366779 | 2019-05-09 11:34 | 16.7.19
ROC619003 | Rayleigh | LONDON ROAD | Opp 134 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation from verge obscuring view from bus shelter and encroaching 300mm into carriageway for approx 10 meters in length. Job for RANGERS | 3378011 | 2019-06-05 12:39 | 9.7.19
ROC619004 | Rayleigh | LONDON ROAD | Opp 138 | HW: overgrown vegetation (our) | Ra2=1x2 Branches from hedge around bus shelter hanging down, approx 20 meters over hedge overgrown. Job for RANGERS | 3378009 | 2019-06-05 12:35 | 9.7.19
ROC619005 | Rayleigh | LONDON ROAD | Opp Pearsons Avenue | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation obscuring visibility splay to Traffic Light Pole 2 and around LC. Splay to be cut by RANGERS job for RANGERS | 3375606 | 2019-05-30 08:59 | 9.7.19
ROC619006 | Rayleigh | LEASWAY | Side of 47 Crown Hill | HW: overgrown vegetation (our) | Ra2=1x2 Nettles encroaching into footway for approx 500mm for approx 25 meters in length. FW width 1.6m Job for RANGERS | 3375488 | 2019-05-29 15:06 | 23.7.19
ROC619007 | Great Wakering | WAKERING ROAD | South of Poynters Lane Junction | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation from verge encroaching into footway for approx 500mm for a length of approx 40 meters (FW width 1.8) Job for RANGERS | 3373949 | 2019-05-23 12:23 | 22.7.19
ROC619008 | Rochford | SUTTON ROAD | Between 47 and Purdeys Way Junction | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation encroaching into footway by 1 meter, for exactly 320 meters in length. Job for RANGERS | 3386950 | 2019-06-26 11:39 | road closure
ROC619009 | Sutton | SHOPLAND ROAD | Between Winters and Old School Cottages | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation from verge encroaching into footway for approx 15 meters. Job for RANGERS also needs siding. ( encroaching 1.2 FW width 1.2 ) | 3367214 | 2019-05-10 09:30 | 9.7.19
ROC619010 | Rayleigh | SHAKESPEARE AVENUE | Opp 9-11 | HW: overgrown vegetation (our) | Ra3=3x1 Nettles and brambles overgrown and climbing property wall. For a length of approx 9 meters on verge. Job for RANGERS | 3372604 | 2019-05-21 12:29 | 9.7.19
ROC619011 | Rayleigh | HILARY CRESCENT | Os 44 | HW: overgrown vegetation (our) | Ra4=4x1 Small tree branch hanging down onto verge. Removal Job for RANGERS | 3365169 | 2019-05-03 10:32 | 9.7.19
ROC619012 | Canewdon | HIGH STREET | Os Fare Stage and Picasso | HW: overgrown vegetation (our) | Ra6=2x3 Vegetation growing up through footway from centre to back edge and weeds growing up through footway at back edge blocking footway . Encroaching 1.5m into footway (FW width 1.8lm) length of affected area 5.0m. Job for RANGERS | 3375190 | 2019-05-29 09:08 | 25.7.19
ROC619013 | Rayleigh | HIGH ROAD | Opp The side of 2 High Road | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation encroaching into footway for approx 500mm for approx 20 meters. FW width 2.0 meters . Job for RANGERS also needs siding as well | 3383982 | 2019-06-20 08:38 | 24.7.19
ROC619014 | Rayleigh | HIGH ROAD | Between 1a and 19 Spring Gardens in alleyway | HW: overgrown vegetation (our) | Ra2=2x3 Nettles encroaching into footway for approx 1700mm upto for approx 35 meters. Some nettles 1.5 meters high. Job for RANGERS FW width 2.0 meters | 3383981 | 2019-06-20 08:42 | 24.7.19
ROC619015 | Ashingdon | GREENSWARD LANE | By 223 | HW: overgrown vegetation (our) | RA2=1×2 overgrown Vegatation impeding fw 3m Job for RANGERS | 3383885 | 2019-06-19 09:55 | 23.7.19
ROC619016 | Rayleigh | DEEPDENE AVENUE | Os 26 | HW: overgrown vegetation (our) | Ra1=1x1 Grass from verges encroaching into footway by 300mm for approx 5 meters . Needs siding job for RANGERS | 3383675 | 2019-06-19 11:07 | 23.7.19
ROC619017 | Rayleigh | CROWN HILL | Between 49 - 67 (Worst area 49 - 59) | HW: overgrown vegetation (our) | Ra3=1x3 Vegetation encroaching into footway for approx 900mm for approx 125 meters in length. FW width 1.6m Job for RANGERS | 3375495 | 2019-05-29 15:08 | 24.7.19
ROC619018 | Rayleigh | BROOK ROAD | Opp Unit 13 - 15 | HW: overgrown vegetation (our) | Ra3=1x3 Vegetation from verge encroaching across footway width for approx 50 meters. Job for RANGERS | 3381426 | 2019-06-13 16:16 | cars parked for work
ROC619019 | Rochford | RECTORY ROAD | LH of Magnolia Road junction | HW: overgrown vegetation (our) | Ra2=1x2 Small tree branches and nettles from verge obscuring view and accessibility to Traffic Light Pole 1 and cabinets for approx 30 meters. Also starting to encroach into carriageway. Job for RANGERS | 3373036 | 2019-05-22 08:57 | cars parked for work
ROC619020 | Rayleigh | BROOK ROAD | Opposite Unit 17 | HW: overgrown vegetation (our) | Ra3=1x3 Vegetation from verge encroaching across footway width for approx 50 meters. Job for RANGERS | 3381424 | 2019-06-13 16:12 | cars parked for work
ROC619021 | Rayleigh | BROOK ROAD | Opp Unit 17-Unit 19 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation encroaching into footway for approx 75 meters. Job for RANGERS | 3381422 | 2019-06-13 16:09 | cars parked for work
ROC619022 | Rayleigh | BROOK ROAD | Os 45 | HW: overgrown vegetation (our) | Ra3=1x3 Vegetation encroaching into footway for approx 1500mm and upto 1 meters in height for approx 15 meters. Job for RANGERS | 3381405 | 2019-06-13 15:32 | cars parked for work
ROC619023 | Rayleigh | BROOK ROAD | Os Unit 15 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation encroaching into footway for approx 500mm and upto 1 meters in height for approx 5 meters. Job for RANGERS | 3381379 | 2019-06-13 14:34 | cars parked for work
ROC619024 | Rayleigh | BROOK ROAD | Opp LC BR9 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation encroaching into footway for approx 1200mm and upto 2 meters in height for approx 18 meters, obscuring sign. Job for RANGERS | 3381375 | 2019-06-13 14:23 | cars parked for work
ROC619025 | Rayleigh | BROOK ROAD | Adj LC BR5 | HW: overgrown vegetation (our) | Ra1=1x1 Brambles covering one way sign on verge . Job for RANGERS | 3374277 | 2019-05-24 09:14 | cars parked for work
ROC619026 | Barling Magna | BARROW HALL ROAD | Side of 87 Little Wakering Road | HW: overgrown vegetation (our) | Ra2=1x2 Weeds growing up from back edge of path encroaching into footway by 500mm, for a length of 30 meters, FW width 1.0m. Job for RANGERS | 3372210 | 2019-05-20 14:21 | 22.7.19
ROC619027 | Barling Magna | BARROW HALL ROAD | Side of 87 Little Wakering Road | HW: overgrown vegetation (our) | Ra1=1x1 Grass from verges encroaching into footway for approx 400mm for a length of approx 30 meters, FW width 1.0. Job for RANGERS | 3372206 | 2019-05-20 14:15 | 22.7.19
ROC619028 | Rochford | ASHINGDON ROAD | ñmñnmmmjjjh1ey3 | HW: overgrown vegetation (our) | Ra4=1x4 Two small trees on verge, branches hanging down as low as 1.6m in height. Job for RANGERS | 3374771 | 2019-05-28 10:10 | 23.7.19
ROC619029 | Rochford | ASHINGDON ROAD | Os Suffolk Court adj LC A16A | HW: overgrown vegetation (our) | Ra2=1x2 Brambles and vegetation overthrowing and obscuring visibility splay for vehicles pulling out of Roche Avenue. Veg approx 15 meters in length on verge. Job for RANGERS | 3374770 | 2019-05-28 09:55 | 22.7.19
ROC619030 | Rayleigh | FOOTPATH FROM LONDON HILL TO ELM DRIVE | Between 41-45 | HW: overgrown vegetation (our) | Ra1=1x1 Nettles encroaching into footway for approx 500mm for approx 15 meters .FW width 1.8m. Job for RANGERS | 3375569 | 2019-05-30 08:27 | 12.7.19
ROC619031 | Rayleigh | Footpath From Nursery Close To Daws Heat | Between LC FP5 and LC FP8 | HW: overgrown vegetation (our) | Ra2=1x2 Stinging nettles encroaching into footway for approx 500mm upto for Approx 100 meters in length down footway. Job for RANGERS | 3378004 | 2019-06-05 12:20 | 12.7.19
ROC619032 | Rayleigh | Footpath From Weir Gardens To High Road | Side of 31a High Road in alleyway | HW: overgrown vegetation (our) | Ra2=1x2 Nettles encroaching into footway for approx 500mm both sides for approx 20 meters in length both sides. ( FW 1.8m) Job for RANGERS | 3374271 | 2019-05-24 08:49 | 12.7.19
ROC619033 | Rayleigh | Footpath From Weir Gardens To High Road | Rear of Gordon Roughley Court in alleyway | HW: overgrown vegetation (our) | Ra2=1x2 Nettles encroaching into footway for approx 500mm both sides for approx 25 meters in length both sides. ( FW 1.8m) Job for RANGERS | 3374270 | 2019-05-24 08:52 | 12.7.19
ROC619034 | Rayleigh | ALEXANDRA ROAD | Side of 64 | HW: overgrown vegetation (our) | Ra6=2x3 Spikey vegetation from verge encroaching into footway by 1 meter. For approx 10 meters in length. FW width 1.8m. Job for RANGERS | 3371438 | 2019-05-17 11:57 | 16.7.19
ROC619035 | Great Wakering | WHITEHALL ROAD | Side of 6 The Cedars | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation from verge encroaching into footway for approx 800mm , length of approx 30 meters. FW width 1.8m Job for RANGERS | 3386826 | 2019-06-26 09:39 | 22.7.19
ROC1908002 | Hockley | SELBOURNE ROAD | Opp 9 | OGRO | Ra4=1x4 Branches from 4 small trees on verge encroaching into footway by 1.5 meters for a length of approx 20 meters Job for RANGERS | 3400512 | 2019-07-31 13:37 | 2019-08-10
ROC1909001 | Rawreth | CHURCH ROAD | Opposite The Forge Nursery | Overgrown vegetation | Ra4 = 2x2 JOB FOR RANGERS Priorty sign covered by veg | 3404843 | 2019-08-09 11:38 | 9.9.19
ROC1909002 | Rawreth | CHELMSFORD ROAD | Near Primrose Cottage | Overgrown vegetation | Ra4 = 2x2 JOB FOR RANGERS overgrown hedge 60mts | 3404719 | 2019-08-09 09:35 | 12.9.19 along entire pavement 500m
ROC1909003 | Rayleigh | CHEAPSIDE WEST | Opp 27 | Overgrown vegetation | Ra4=1x4 Vegetation encroaching into footway by approx 1.5 meter upto and for a length of approx 20 meters Job for RANGERS | 3397688 | 2019-07-25 12:07 | 5.9.19
ROC1909004 | Rayleigh | CHEAPSIDE WEST | Opp 25 | Overgrown vegetation | Ra3=1x3 Vegetation encroaching into footway by approx 1 meter upto and for a length of approx 30 meters Job for RANGERS | 3397690 | 2019-07-25 12:10 | 5.9.19
ROC1909005 | Rayleigh | BROOK ROAD | Opp Unit 13 - 15 | Overgrown vegetation | Ra3=1x3 Vegetation from verge encroaching across footway width for approx 50 meters. Job for RANGERS | 3381426 | 2019-06-13 16:16 | cars parked mon to sumday
ROC1909006 | Rayleigh | BROOK ROAD | Opposite Unit 17 | Overgrown vegetation | Ra3=1x3 Vegetation from verge encroaching across footway width for approx 50 meters. Job for RANGERS | 3381424 | 2019-06-13 16:12 | cars parked mon to sumday
ROC1909007 | Rayleigh | BROOK ROAD | Opp Unit 17-Unit 19 | Overgrown vegetation | Ra2=1x2 Vegetation encroaching into footway for approx 75 meters. Job for RANGERS | 3381422 | 2019-06-13 16:09 | cars parked mon to sumday
ROC1909008 | Rayleigh | BROOK ROAD | Os 45 | Overgrown vegetation | Ra3=1x3 Vegetation encroaching into footway for approx 1500mm and upto 1 meters in height for approx 15 meters. Job for RANGERS | 3381405 | 2019-06-13 15:32 | cars parked mon to sumday
ROC1909009 | Rayleigh | BROOK ROAD | Os Unit 15 | Overgrown vegetation | Ra2=1x2 Vegetation encroaching into footway for approx 500mm and upto 1 meters in height for approx 5 meters. Job for RANGERS | 3381379 | 2019-06-13 14:34 | cars parked mon to sumday
ROC1909010 | Rayleigh | BROOK ROAD | Opp LC BR9 | Overgrown vegetation | Ra2=1x2 Vegetation encroaching into footway for approx 1200mm and upto 2 meters in height for approx 18 meters, obscuring sign. Job for RANGERS | 3381375 |  | cars parked mon to sumday
ROC1909011 | Rayleigh | FOOTPATH FROM KING GEORGES CLOSE TO STIL | Side of 1-17 King George's Close in alleyway | Overgrown vegetation | Ra3=1x3 Vegetation from verge encroaching into footway by 1 meter for a length of approx 40 meters Job for RANGERS | 3401353 |  | 2.9.19
ROC1909012 | Rayleigh | BROOK ROAD | Adj LC BR5 | Overgrown vegetation | Ra1=1x1 Brambles covering one way sign on verge . Job for RANGERS | 3374277 |  | cars parked mon to sumday
ROC1909013 | Rochford | FOOTPATH FROM ORMONDE AVENUE TO ROCHFORD | Footpath between 21-23 | Overgrown vegetation | Ra2=1x2 Vegetation from hedging encroaching into footway by approx 700mm for a length of approx 20 meters. Job for RANGERS still needs to be cut back more | 3412501 | . 9 | 23.9.19
ROC1909014 | Rayleigh | BEDFORD CLOSE | Opp 7 | Overgrown vegetation | Ra1=1x1 growth from verge encroaching into footway for approx 500mm for a length of 30 meters. Needs siding. Job for RANGERS | ,i,0i.0iii..i.iiiiiio0 | weedk,,,,k,jk.,k,k,,k,,k, k ..
ROC1909015 | Rayleigh | footpath 68 Rayleigh |  | Overgrown vegetation | Ra3=1x3 Vegetation encroaching into footway by approx 1 meter and forna length of approx 20 meters Job for RANGERS | 3397659 | 2019-07-25 11:33
ROC1909016 | Rochford | RECTORY ROAD | LH of Magnolia Road junction | Overgrown vegetation | Ra2=1x2 Small tree branches and nettles from verge obscuring view and accessibility to Traffic Light Pole 1 and cabinets for approx 30 meters. Also starting to encroach into carriageway. Job for RANGERS | 3373036 | , | 40mph road
ROC1909017 | Rochford | ASHINGDON ROAD | Opp 12 | Overgrown vegetation | Ra6=3x2 Fallen Tree branch part blocking the footway . Possible Job for RANGERS 1.7 meters available to get passed | 3412123 | 2019-08-28 14:35 | 11.9.19
ROC1909018 | Rochford | ASHINGDON ROAD | Opp 254-260 | Overgrown vegetation | Ra2=1x2 Vegetation from hedging encroaching into footway for approx 500mm for a length of approx 50 meters Job for RANGERS | 3399064 | 2019-07-29 13:55 | 11.9.19
ROC1909019 | Rochford | ASHINGDON ROAD | Os Suffolk Court | Overgrown vegetation | Ra3=1x3 Vegetation encroaching into footway for approx 1 meter for a length of approx 15 meters Job for RANGERS | 3399062 | 2019-07-29 13:35 | 11.9.19
ROC1909020 | Rochford | ANNE BOLEYN DRIVE | Side of 74 Sutton Court Drive | Overgrown vegetation | Ra1=1x1 Grass from verges encroaching into footway for approx 700mm for approx 30 meters in length. Needs Siding job for RANGERS | 3395450 | 2019-07-19 10:00 | 25.9.19
ROC1909021 | Rayleigh | ALEXANDRA ROAD | Os 71 adj Field Entrance | Overgrown vegetation | Ra3=1x3 Vegetation from hedge at field entrance encroaching into footway by approx 500mm for a length of approx 1 meter both sides . Job for RANGERS | 3397264 | 2019-07-24 11:28 | 25.9.19
ROC1909022 | Hawkwell | ALBERT ROAD | S/o Victoria Inn ph | Overgrown vegetation | Ra4 2x2 hedge overhanging footpath 21.3x0.4 ( rangers ) | 3406294 | 2019-08-13 14:37 | 12.9.19
ROC1909023 | Rochford | Fpath Frm Ashingdon Rd 2 Rochford Gdn Wy | Side of 102 in alleyway | Overgrown vegetation | Ra2=1x2 Hedge encroaching 800mm into footway for approx 15 meters in length, leaving 1.2 meters of FW to get passed. Job for RANGERS | 3412502 | 2019-08-29 12:49 | 12.9.19
ROC1909024 | Rochford | OAST WAY | Opp 7 | Overgrown vegetation | Ra3=1x3 Large weed shrub blocking half the footway for approx 3 meters. Job for RANGERS | 3396958 | 2019-07-23 13:58 | 12.9.19
ROC1909025 | Rayleigh | MORTIMER ROAD | Between 40-52 | Overgrown vegetation | Ra3=1x3 Vegetation from verge hedging encroaching into footway by 1 meter for a length of approx 40 meters Job for RANGERS | 3405513 | 2019-08-12 12:54 | 5.9.19
ROC1909026 | Rayleigh | LOVE LANE | Junction with Crown Hill | Overgrown vegetation | Ra3=1x3 Vegetation from verge hedging encroaching into footway by 800mm for a length of approx 14 meters Job for RANGERS | 3397517 | 2019-07-25 09:18 | complete
ROC1909027 | Rayleigh | LONDON ROAD | Opp 128-130 | Overgrown vegetation | Ra3=1x3 Vegetation in ecc ditch for approx 50 meters. Job for RANGERS | 3392904 | 2019-07-11 14:30 | complete
ROC1909028 | Rayleigh | LONDON ROAD | Between 188 - 178 | Overgrown vegetation | Ra2=1x2 Hedging encroaching into footway for approx 30 meters in length. Job for RANGERS | 3391867 | 2019-07-08 14:24 | 12.9.19
ROC1909029 | Rayleigh | LONDON ROAD | Between 176 - 164 | Overgrown vegetation | Ra4=1x4 Vegetation from hedging adj play area encroaching into footway for approx 100 meters in length. Job for RANGERS | 3391871 | 2019-07-08 14:28 | 5.9.19
ROC1909030 | Rayleigh | LODGE CLOSE | Os 1 and side of 1b | Overgrown vegetation | Ra2=1x2 bush on verge encroaching into footway for approx 800mm for a length of approx 5 meters Job for RANGERS | 3390732 | 2019-07-04 14:20 | 5.9.19
ROC1909031 | Rayleigh | LODGE CLOSE | Opp 7 near LC 3 | Overgrown vegetation | Ra3=1x3 bush on verge encroaching into footway for approx 900mm for a length of approx 3 meters Job for RANGERS . One bramble is really sticking out | 3390757 | 2019-07-04 14:31 | complete
ROC1909032 | Rayleigh | LILLYVILLE WALK | Os 8 - 14 | Overgrown vegetation | Ra1=1x1 Grass from verges encroaching into footway for approx 500mm for a length of approx 60 meters Needs Siding job for RANGERS | 3390318 | 2019-07-03 15:16
ROC1909033 | Rayleigh | LANGHAM DRIVE | Rear of 43 - 53 Langham Drive (Especially behind 49) | Overgrown vegetation | Ra6=2x3 Brambles and Hedging encroaching in footpath for approx 1 meter. For a total length of approx 70 meters, worst affected area is behind 49 where some hedging has fallen forward and is overhanging the remote footway. Job for RANGERS | 3392900 | 2019-07-11 14:06 | 5.9.19
ROC1909034 | Rayleigh | KESTREL GROVE | Adj LC 1 and the junction | Overgrown vegetation | Ra2=1x2 Hedges from verge encroaching into footway for approx 500mm for a length of approx 10 meters. Job for RANGERS | 3392894 | 2019-07-11 13:54 | 5.9.19
ROC1909035 | Rayleigh | KENNEDY CLOSE | 10 meters East of LC 1 | Overgrown vegetation | Ra2=1x2 Vegetation from verge encroaching into footway for approx 800mm for a length of approx 15 meters. Job for RANGERS | 3390402 | 2019-07-03 15:48 | complete
ROC1909036 | Rayleigh | HULLBRIDGE ROAD | 50 meters North of Ferndale Road junction | Overgrown vegetation | Ra2=1x2 Stinging nettles encroaching into footway for approx 500mm for approx 50 meters in length. FW width 1.8m Job for RANGERS | 3397642 | 2019-07-25 11:16 | complete
ROC1909037 | Rayleigh | HULLBRIDGE ROAD | Between Army Cadets / LC HB20 - Opp Lubbards Farm | Overgrown vegetation | Ra3=1x3 Nettles encroaching into footway for approx 700mm and branches overhanging footway. For a length of approx 60 meters Job for RANGERS | 3397639 | 2019-07-25 11:12 | 20.9.19
ROC1909038 | Rayleigh | HOCKLEY ROAD | Opp 62 | Overgrown vegetation | Ra2=1x2 Vegetation from raised verge overhanging footway for approx 50 meters in length job for RANGERS | 3394940 | 2019-07-17 13:50 | 23.9.19
ROC1909039 | Rochford | HILARY CLOSE | Between 9-14 | Overgrown vegetation | Ra3=1x3 Brambles encroaching into footway by 1 meter for a length of approx 9 meters Job for RANGERS | 3402574 | 2019-08-06 12:39 | 9.9.19
ROC1909040 | Rayleigh | HIGH ROAD | Side of 1a in alleyway | Overgrown vegetation | Ra2=1x2 Vegetation from verge growing over footway DBM by 1 meter for a length of approx 30 meters Needs Siding job for RANGERS | 3401199 | 2019-08-02 08:19
ROC1909041 | Rochford | HALL ROAD | Opp St Andrews Road | Overgrown vegetation | Ra2=1x2 Vegetation encroaching into footway for approx 500mm for approx 500mm for a length of approx 75 meters Job for RANGERS | 3391682 | 2019-07-08 11:54 | complete
ROC1909042 | Rochford | HALL ROAD | Going North of 2 Potash Bungalows | Overgrown vegetation | Ra4=1x4 Nettles encroaching into footway by 1.5 meters upto for Approx 75 meters. Job for RANGERS | 3403987 | 2019-08-08 09:23 | 2.9.19
ROC1909043 | Rayleigh | FERNDALE ROAD | Opp 53 | Overgrown vegetation | Ra4=1x4 Vegetation from overhanging footway 1.5 meters and encroaching into footway by 1.5 meters for a length of approx 20 meters around verge area. Job for RANGERS | 3405512 | 2019-08-12 12:47 | 5.9.19
ROC1909044 | Rayleigh | FERNDALE ROAD | LHS of 1 adj Dog Bin | Overgrown vegetation | Ra2=1x2 Brambles encroaching into footway by 500mm for a length of approx 2 meters Job for RANGERS | 3405508 | 2019-08-12 12:42 | 5.9.19
ROC1909045 | Rayleigh | EASTWOOD ROAD | Os 41-43 | Overgrown vegetation | Ra1=1x1 Vegetation from centre getting high obscuring visibility. Job for RANGERS | 3397556 | 2019-07-25 10:06 | 12.9.19
ROC1909046 | Rayleigh | EASTWOOD ROAD | Opp 629 | Overgrown vegetation | Ra1=1x1 Grass from verges encroaching into footway for approx 500mm for a length of approx 60 meters Needs Siding job for RANGERS | 3390644 | 2019-07-04 13:07
ROC1909047 | Rayleigh | VICTORIA ROAD | Opp 65 | Overgrown vegetation | Ra3=1x3 Vegetation from verge hedge encroaching into footway by approx 800mm for a length of approx 70 meters . Job for RANGERS | 3397255 | 2019-07-24 11:12 | 2.9,19
ROC1909048 | Rayleigh | VICTORIA AVENUE | Opp 85 | Overgrown vegetation | Ra3=1x3 Vegetation from verge hedging encroaching into footway by approx 1 meter for a length of approx 30 meters, also ivy encroaching along footway back edge which needs siding. Job for RANGERS | 3397510 | 2019-07-25 08:57
ROC1909049 | Rochford | EAST STREET | Os 2 | Overgrown vegetation | Ra4=2x2 Bush encroaching into footway by 1 meter and obscuring sign. Job for RANGERS | 3412160 | 2019-08-28 15:20 | 9.9.19
ROC1909050 | Sutton | SUTTON ROAD | 10 meters South of All Saints Church | Overgrown vegetation | Ra2=1x2 Vegetation from verge encroaching into footway for 700mm for a length of approx 50 meters. Job for RANGERS | 3392072 | 2019-07-09 10:40 | 40mph road
ROC1909051 | Sutton | SUTTON ROAD | Between Sutton Manor and All Saints Church | Overgrown vegetation | Ra2=1x2 Vegetation encroaching into footway for approx 800mm for a length of approx 180 meters. Job for RANGERS | 3391709 | 2019-07-08 12:03 | 40 mph road
ROC1909052 | Rayleigh | DAWS HEATH ROAD | Opp 47 | Overgrown vegetation | Ra1=1x1 Vegetation encroaching into footway by 300mm (FW width 1.8m) for a length of approx 40 meters. Job for RANGERS | 3412776 | 2019-08-30 10:44 | 11.9.19
ROC1909053 | Sutton | SUTTON ROAD | Between Church and Shopland Road junction | Overgrown vegetation | Ra3=1x3 Vegetation from verge encroaching into footway for approx 900mm for a length of approx 50 meters Job for RANGERS | 3392062 | 2019-07-09 10:38 | 40mph road
ROC1909054 | Rayleigh | STATION ROAD | Opp 50 | Overgrown vegetation | Ra6=2x3 Small budlia branches overhanging footway for approx 3 meters. Job for RANGERS | 3393077 | 2019-07-12 08:28 | complete
ROC1909055 | Rayleigh | CROWN HILL | Opp 44b | Overgrown vegetation | Ra4=1x4 Vegetation from verge hedging encroaching into footway by 1.5 meters for a length of approx 20 meters affecting visibility splay of Love Lane job for RANGERS | 3397520 | 2019-07-25 09:20 | 6.9.19
ROC1909056 | Rayleigh | STATION ROAD | Opp 12 | Overgrown vegetation | Ra2=1x2 Vegetation from verge encroaching into footway for approx 500mm for a length of 15 meters . Job for RANGERS | 3393076 | 2019-07-12 08:32 | 6.9.19
ROC1909057 | Rayleigh | STATION ROAD | Opp 50 (the trinity) | Overgrown vegetation | Ra2=1x2 Vegetation from verge encroaching into footway for approx 500mm for a length of 10 meters . Job for RANGERS | 3393075 | 2019-07-12 08:29 | 6.9.19
ROC1909058 | Rayleigh | CROWN HILL | Opp 42 | Overgrown vegetation | Ra2=1x2 Vegetation from raised verge overhanging footway for approx 50 meters . Job for RANGERS | 3393080 | 2019-07-12 08:23 | 6.9.19
ROC1909059 | Stambridge | STAMBRIDGE ROAD | Between Rectory Cottage to Moonraker | Overgrown vegetation | Ra3=1x3 Vegetation encroaching into footway by approx 1.2 meter upto and for a length of approx 200 meters Job for RANGERS | 3397724 | 2019-07-25 13:47 | 11.9.19
ROC1909060 | Rayleigh | SOUTH VIEW CLOSE | Side and Rear of 244 Eastwood Road | Overgrown vegetation | Ra3=1x3 Bush from verge encroaching into by 1 meter for a length of approx 4 meters Job for RANGERS | 3406235 | 2019-08-13 12:22 | 6.9.19
ROC1909061 | Rayleigh | CROWN HILL | Opp 42a | Overgrown vegetation | Ra6=2x3 Small branches overhanging footway for approx 5 meters. Job for RANGERS | 3393079 | 2019-07-12 08:25 | 6.9.19
ROC1909062 | Rayleigh | SOUTH VIEW CLOSE | Adj LC 1 | Overgrown vegetation | Ra3=1x3 Bush from verge encroaching into by 1 meter for a length of approx 4 meters Job for RANGERS | 3406233 | 2019-08-13 12:33 | 9.9.19
ROC1909063 | Rayleigh | SIR WALTER RALEIGH DRIVE | Opp 17 -35 | Overgrown vegetation | Ra4=1x4 Vegetation from verge encroaching into carriageway for approx 1.2 meters. For a length of approx 35 meters. Job for RANGERS | 3392883 | 2019-07-11 13:42 | 6.9.19
ROC1909064 | Rayleigh | SHAKESPEARE AVENUE | Side of 12 Shakespeare Avenue | Overgrown vegetation | Ra4=1x4 Brambles from verge encroaching into footway for approx 8 meters. Job for RANGERS | 3412884 | 2019-08-30 13:28 | 9.9.19
ROC1909065 | Rochford | ROCHEHALL WAY | Os Marlborough Depot | Overgrown vegetation | Ra3=1x3 Vegetation and Brambles encroaching into footway for approx 1.5 meters for a length of approx 40 meters Job for RANGERS | 3411514 | 2019-08-27 13:32 | cars and lorries parked
ROC1909066 | Rayleigh | RAYLEIGH AVENUE | Junction of Royal Court | Overgrown vegetation | Ra2=1x2 Brambles encroaching into footway and around dog waste bin by approx 1 meter for a length of approx 5 meters Job for RANGERS | 3400813 | 2019-08-01 09:18 | 9.9.19
ROC1909067 | Rayleigh | POPLAR ROAD |  | Overgrown vegetation | Ra1=1x1 Grass from verges encroaching into footway for approx 500mm for a length of approx 20 meters Needs Siding job for RANGERS | 3390062 | 2019-07-03 13:05 | 25.9.19
ROC1909068 | Rayleigh | POPLAR ROAD | Os 11a | Overgrown vegetation | Ra1=1x1 Grass from verges encroaching into footway for approx 500mm for a length of approx 20 meters Needs Siding job for RANGERS | 3390057 | 2019-07-03 12:50 | 25.9.19
ROC1909069 | Rayleigh | CLYDE CRESCENT | Os 67 | Overgrown vegetation | Ra1=1x1 Grass from verges encroaching into footway for approx 500mm for approx 6 meters in length on 2 verges. Needs Siding job for RANGERS | 3394231 | 2019-07-16 10:56 | 25.9.19
ROC1910001 | Ashingdon | Ashingdon Road | From the Ashingdon Primary Academy heading south/east down Ashingdon Hill | Vegetation cutting | Overgrown vegetation encroaching onto the footway | NA | 2019-10-07 | 15.10.19
ROC1910002 | Rayleigh | VICTORIA AVENUE | Opp 85 | Vegetation | Ra3=1x3 Vegetation from verge hedging encroaching into footway by approx 1 meter for a length of approx 30 meters, also ivy encroaching along footway back edge which needs siding. Job for RANGERS | 3397510 | 2019-07-25 08:57 | 10.10.19
ROC1910003 | Hawkwell | BELCHAMPS WAY | From jct to l/c2 s/o church hall grounds | Vegetation | Ra4 2x2 cut Back overhanging hedge 40.6x0.5 ( rangers ) | 3420814 | 2019-09-23 11:04 | 11.10.19
ROC1910004 | Rayleigh | BEDFORD CLOSE | Opp 7 | Vegetation | Ra1=1x1 growth from verge encroaching into footway for approx 500mm for a length of 30 meters. Needs siding. Job for RANGERS | 3408744 | 2019-08-19 10:19 | 11.10.19
ROC1910005 | Ashingdon | ASHINGDON ROAD | Opposite 563a to 591 | Vegetation | Ra 4=2×2, vegetation encroaching onto fway, 200m in length, Rangers? | 3421094 | 2019-09-24 09:05 | 15.10.19
ROC1910006 | Ashingdon | ASHINGDON ROAD | O/s621 | Vegetation | Ra3 1x3 cut back tree brambles hangover f/w ( rangers ) | 3421320 | 2019-09-24 15:10 | 15.10.19
ROC1910007 | Rayleigh | THE APPROACH | Opp 24 - 14 | Vegetation | Ra2=1x2 weeds grown upto 1.5 meters through the footway for an approx length of 70 meters Job for RANGERS | 3415842 | 2019-09-06 16:06 | 7.10.19
ROC1910008 | Ashingdon | FAMBRIDGE ROAD | From school car park entrance to opposite property Royston | Vegetation | Ra 4=2×2, Highway verge partially blocking fway, 200m in length, Rangers? | 3421139 | 2019-09-24 10:35 | 15.10.19
ROC1910009 | Rayleigh | footpath 68 Rayleigh |  | Vegetation | Ra3=1x3 Vegetation encroaching into footway by approx 1 meter and forna length of approx 20 meters Job for RANGERS | 3397659 | 2019-07-25 11:33 | 7.10.19
ROC1910010 | Rayleigh | MORTIMER ROAD | Os 36-38 | Vegetation | Ra1=1x1 hedging on verge encroaching into footway by 500mm for a length of approx 8 meters Job for RANGERS | 3417126 | 2019-09-11 14:46 | 7.10.19
ROC1910011 | Hullbridge | MALYONS LANE | Opp greenacers | Vegetation | Ra4 2x2 hedge overhanging footpath 5.4x0.9 ( rangers ) | 3421162 | 2019-09-24 11:05 | 10.10.19
ROC1910012 | Rayleigh | LODGE CLOSE | Fence of 26/27 | Vegetation | Ra1=1x1 Ivy growing up fence from verge for approx 14 meters. Needs removal. Job for RANGERS | 3417009 | 2019-09-11 11:33 | 7.10.19
ROC1910013 | Rayleigh | LILLYVILLE WALK | Os 8 - 14 | Vegetation | Ra1=1x1 Grass from verges encroaching into footway for approx 500mm for a length of approx 60 meters Needs Siding job for RANGERS | 3390318 | 2019-07-03 15:16 | 25.9.19
ROC1910014 | Rayleigh | HIGH ROAD | Side of 1a in alleyway | Vegetation | Ra2=1x2 Vegetation from verge growing over footway DBM by 1 meter for a length of approx 30 meters Needs Siding job for RANGERS | 3401199 | 2019-08-02 08:19 | 25.9.19
ROC1910015 | Rayleigh | EASTWOOD ROAD | Opp Wyvale Garden Centre | Vegetation | Ra4=1x4 Vegetation from verge encroaching into footway by 1.5 meters for a length of approx 40 meters Job for RANGERS | 3417020 | 2019-09-11 11:49 | 7.10.19
ROC1910016 | Rayleigh | EASTWOOD ROAD | Opp 629 | Vegetation | Ra1=1x1 Grass from verges encroaching into footway for approx 500mm for a length of approx 60 meters Needs Siding job for RANGERS | 3390644 | 2019-07-04 13:07 | 25.9.19
ROC1910017 | Rayleigh | DOWNHALL PARK WAY | Adj LC 34 | Vegetation | Ra1=1x1 Vegetation from verge encroaching into footway by 400mm for an approx length of 10 meters. Job for RANGERS | 3416820 | 2019-09-11 08:26 | 10.10.19
ROC1910018 | Rawreth | CHURCH ROAD | By l/c 1A | Vegetation | Ra 4 2x2 overhanging hedge 150.0x0.3 ( rangers ) | 3422594 | 2019-09-27 12:04 | 15.10.19
ROC1910019 | Rayleigh | CHEAPSIDE EAST | Os 9 - 25 | Vegetation | Ra2=1x2 grass from verge encroaching into footway for approx 500mm for a length of approx 10 meters on 10 small verges outside properties needs siding. Job for RANGERS | 3415410 | 2019-09-06 11:39 | 9.10.19
ROC1910020 | Hockley | BROADLANDS ROAD | Opposite 58-60 | Vegetation | Ra 4=2×2, vegetation partially blocking fway, 15m in length, Rangers? | 3421223 | 2019-09-24 12:49 | 11.10.19
ROC1910021 | Hockley | BRANKSOME AVENUE | O/s1 | Vegetation | Ra2 1x2 tree overhanging f/w needs trimming back (rangers ) | 3421102 | 2019-09-24 09:26 | 11.10.19
ROC1910022 | Rayleigh | BRAMFIELD ROAD EAST | Os 28 | Vegetation | Ra2=1x2 hedge our side of Brick wall encroaching 1 meter into footway for approx 4 meters in length job for RANGERS | 3414402 | 2019-09-04 14:44 | 11.10.19
ROC1911001 | Rayleigh | MILTON CLOSE | Side of 1 | HW: overgrown vegetation (our) | Ra2=1x2 Bush on verge encroaching into footway for approx 1 meter for a length of approx 3 meters job for RANGERS | 3433751 | 2019-10-28 09:21 | 8.11.19
ROC1911002 | Rayleigh | HIGH ROAD | Alleyway between 1a - 19 | HW: overgrown vegetation (our) | Ra1=1x1 nettles growing and encroaching into footway by 800mm for a length of approx 30 meters both sides. Job for RANGERS | 3426333 | 2019-10-08 08:17 | 8.11.19
ROC1911003 | Rayleigh | EASTWOOD ROAD | Opp Wyvale Garden Centre | HW: overgrown vegetation (our) | RESOLVED Ra4=1x4 Vegetation from verge encroaching into footway by 1.5 meters for a length of approx 40 meters Job for RANGERS | 3430118 | 2019-10-17 09:39 | 19.11.19
ROC1911004 | Rayleigh | THAMES CLOSE | Opp 8 | HW: overgrown vegetation (our) | Ra4=2x2 Hedges on verge blocking half the footway. Encroaching into footway by 1 meters in a L shape footway 6 meters Job for RANGERS | 3429272 | 2019-10-15 14:53 | 18.11.19
ROC1911005 | Sutton | SUTTON ROAD | 40 meters North of Sutton Church Hall | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation from verge encroaching into footway by 1.5 meters for a length of approx 70 meters Job for RANGERS | 3436076 | 2019-10-31 15:23 | 18.11.19
ROC1911006 | Rayleigh | DOBSONS CLOSE | Side of 141 Daws Heath Road | HW: overgrown vegetation (our) | Ra3=1x3 Hedge from verge encroaching into footway by 1.2 meters for a length of approx 2 meters Job for RANGERS | 3434534 | 2019-10-29 09:26 | 11.11.19
ROC1911007 | Rayleigh | DOBSONS CLOSE | Side of 141 Daws Heath Road | HW: overgrown vegetation (our) | Ra1=1x1 Hedges from verge encroaching into carriageway by 250mm for a length of approx 10 meters job for RANGERS | 3434542 | 2019-10-29 09:34 | 11.11.19
ROC1911008 | Rayleigh | PHILBRICK CRESCENT EAST | Os 5 | HW: overgrown vegetation (our) | Ra4=1x4 Basal growth from tree encroaching into footway by 800mm for a length of approx 2 meters . Job for RANGERS | 3432400 | 2019-10-23 09:35 | 11.11.19
ROC1911009 | Rochford | SOUTHEND ROAD | Opp 2 Warners Bridge Chase on Southend Road | HW: overgrown vegetation (our) | Ra1=1x1 Vegetation encroaching into footway by 400mm for an approx length 30 meters Job for RANGERS | 3435384 | 2019-10-30 12:03 | 13.11.19
ROC1911010 | Rayleigh | PHILBRICK CRESCENT EAST | Os 23 | HW: overgrown vegetation (our) | Ra2=1x2 Basal growth from tree encroaching into footway by 800mm for a length of approx 1 . Job for RANGERS | 3432396 | 2019-10-23 09:31 | 11.11.19
ROC1911011 | Rayleigh | PHILBRICK CRESCENT EAST | Os 25 | HW: overgrown vegetation (our) | Ra3=1x3 Basal growth from tree encroaching into footway by 800mm for a length of approx 2 meters . Job for RANGERS | 3432395 | 2019-10-23 09:30 | 11.11.19
ROC1911012 | Rayleigh | PHILBRICK CRESCENT EAST | Os 35 | HW: overgrown vegetation (our) | Ra2=1x2 Basal growth from tree encroaching into footway by 800mm for a length of approx 1 . Job for RANGERS | 3432389 | 2019-10-23 09:25 | 11.11.19
ROC1911013 | Canewdon | SCOTTS HALL ROAD | Os 7 RH VX | HW: overgrown vegetation (our) | Ra4=1x4 Spikey hedge obscuring access to water box. And encroaching into footway 1.6 meters for a length of approx 3 meters job for RANGERS | 3429817 | 2019-10-16 14:03 | 18.11.19
ROC1911014 | Rayleigh | KENILWORTH GARDENS | Os 6-8 | HW: overgrown vegetation (our) | Ra3=1x3 Weeds around tree base encroaching into footway by 1 meter and 2 meters high upto. For approx 2 meters in length job for RANGERS | 3431676 | 2019-10-22 11:12 | 11.11.19
ROC1911015 | Rayleigh | KEATS WALK ACCESS ROAD | Side of 12 Shakespeare Avenue | HW: overgrown vegetation (our) | Ra2=1x2 Brambles hanging down in to foot Way for approx 7 meters in length job for RANGERS | 3427396 | 2019-10-09 15:33 | 18.11.19
ROC1911016 | Rochford | CHERRY ORCHARD WAY | Adj LC J24 | HW: overgrown vegetation (our) | Ra2=1x2 bushes from verge encroaching into footway by 1 meter for a length of approx 10 meters Job for RANGERS | 3429933 | 2019-10-16 11:39 | 8.11.19
ROC1911017 | Rochford | CHERRY ORCHARD WAY | Opp LC J15 adj bus layby | HW: overgrown vegetation (our) | Ra3=1x3 bushes from verge encroaching into footway by 1.5 meter for a length of approx 10 meters Job for RANGERS | 3429932 | 2019-10-16 11:41 | 8.11.19
ROC1912001 | Rochford | CHERRY ORCHARD LANE | Between LC G12 - LC G6 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation encroaching into footway by 800mm both sides for a length of approx 120 meters Job for RANGERS | 3435246 | 2019-10-30 10:00 | 4.12.19
ROC1912002 | Rochford | ASHINGDON ROAD | Opposite wood view next to bus stop | HW: overgrown vegetation (our) | Ra2 = 2x1 JOB FOR RANGERS overgrown vegetation | 3445592 | 2019-11-27 12:31 | 11.12.19
ROC1912003 | Rochford | MILTON CLOSE | Side of 1 | HW: overgrown vegetation (our) | Ra2=1x2 Bush on verge encroaching into footway for approx 1 meter for a length of approx 3 meters job for RANGERS | 3433751 | 2019-10-28 09:21 | 4.12.19
ROC1912004 | Rochford | HAWKWELL ROAD | Jnt with whitehart lane | HW: overgrown vegetation (our) | Ra4=2x2 JOB FOR RANGERS overgrown bush 2mts covering 80% Of footway | 3446578 | 2019-11-29 12:03 | 12.12.1
ROC1912005 | Rochford | CHURCH ROAD | Opposite Braemar to church | HW: overgrown vegetation (our) | Ra2 = 2x1 JOB FOR RANGERS 100mts over hanging veg into road | 3445026 | 2019-11-26 10:32 | 12.12.19
ROC2001001 | Rayleigh | LITTLE WHEATLEY CHASE | Opp 9-17 | HW: overgrown vegetation (our) | Ra2=1x2 Mud and vegetation encroaching into footway by 700mm for a length of approx 30 meters. Needs siding job for RANGERS | 3455870 | 2020-01-08 14:00 | Unable possible road closure
ROC2001002 | Rayleigh | DOWNHALL PARK WAY | Side 97 Opp 77 | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation from verge encroaching by 800mm (FW width 0.4m) for a length of approx 20 meters Job for RANGERS | 3450476 | 2019-12-12 13:05 |  | 13.1.20
ROC2001003 | Sutton | SUTTON ROAD | 40 meters North of Sutton Church Hall | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation from verge encroaching into footway by 1.5 meters for a length of approx 70 meters Job for RANGERS | 3436076 | 2019-10-31 15:23 |  | 20.1.20
ROC2001004 | Canewdon | SCOTTS HALL ROAD | Os 7 RH VX | HW: overgrown vegetation (our) | Ra4=1x4 Spikey hedge obscuring access to water box. And encroaching into footway 1.6 meters for a length of approx 3 meters job for RANGERS | 3429817 | 2019-10-16 14:03 |  | 20.1.20
ROC2001005 | Rayleigh | REGENT CLOSE | Opp 15-16 | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation from verge encroaching into footway by approx 1.8m for 10 meters in L shape. JOB FOR RANGERS | 3450550 | 2019-12-12 15:58 |  | 13.1.20
ROC2001006 | Rayleigh | REGENT CLOSE | Opp 11-14 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation from verge encroaching by 500mm for a length of approx 40 meters Job for RANGERS | 3450542 | 2019-12-12 15:44 |  | 13.1.20
ROC2001007 | Rayleigh | KEATS WALK ACCESS ROAD | Side of 12 Shakespeare Avenue | HW: overgrown vegetation (our) | Ra2=1x2 Brambles hanging down in to foot Way for approx 7 meters in length job for RANGERS | 3427396 | 2019-10-09 15:33 |  | 17.1.20
ROC2001008 | Rochford | DALYS ROAD | Opp 18 | HW: overgrown vegetation (our) | Ra2=1x2 Brambles encroaching into footway by approx 800mm for a length of approx 5 meters Job for RANGERS | 3447667 | 2019-12-04 09:17 |  | 14.1.20
ROC2001009 | Rochford | CHERRY ORCHARD WAY | Adj LC J24 | HW: overgrown vegetation (our) | Ra2=1x2 bushes from verge encroaching into footway by 1 meter for a length of approx 10 meters Job for RANGERS | 3429933 | 2019-10-16 11:39 |  | 15.1.20
ROC2001010 | Sutton | SUTTON ROAD | Os Sutton Bridge Farm | HW: overgrown vegetation (our) | Ra2=1x2 Verge encroaching into footway by 600mm for a length of approx 40 meters. Needs siding job for RANGERS | 3453149 | 2019-12-23 09:20 |  | Unable possible road closure
ROC2001011 | Rochford | CHERRY ORCHARD WAY | Opp LC J15 adj bus layby | HW: overgrown vegetation (our) | Ra3=1x3 bushes from verge encroaching into footway by 1.5 meter for a length of approx 10 meters Job for RANGERS | 3429932 | 2019-10-16 11:41 | 15.1.20
ROC2001012 | Rochford | SOUTHEND ROAD | Opp 2 Warners Bridge Chase on Southend Road | HW: overgrown vegetation (our) | Ra1=1x1 Vegetation encroaching into footway by 400mm for an approx length 30 meters Job for RANGERS | 3435384 | 2019-10-30 12:03 | 21.1.20
ROC2001013 | Rayleigh | RAWRETH LANE | Os 159 | HW: overgrown vegetation (our) | Ra2=1x2 Verge encroaching into footway by 600mm for a length of approx 10 meters. Needs siding job for RANGERS | 3453535 | 2019-12-24 09:45 | 29.1.20
ROC2001014 | Rayleigh | RAWRETH LANE | Os 159 | HW: overgrown vegetation (our) | Ra4=2x2 Hedge from verge encroaching by 500mm for a length of approx 10 meters, Brambles hanging into footway. Job for RANGERS | 3453537 | 2019-12-24 09:48 | 29.1.20
ROC2001015 | Rayleigh | BARDFIELD WAY | Adj LC 1 | HW: overgrown vegetation (our) | Ra2=1x2 Mud and vegetation encroaching into footway by 700mm for a length of approx 16 meters. Needs siding job for RANGERS | 3455838 | 2020-01-08 13:29 | 29.1.20
ROC2001016 | Rayleigh | DOBSONS CLOSE | Side of 141 Daws Heath Road | HW: overgrown vegetation (our) | Ra3=1x3 Hedge from verge encroaching into footway by 1.2 meters for a length of approx 2 meters Job for RANGERS | 3434534 | 2019-10-29 09:26 | 14.1.20
ROC2001017 | Rochford | SOUTHEND ROAD | Between 68 and 28 | HW: overgrown vegetation (our) | Ra2=1x2 Mud and vegetation debris built up along the back of footway making it narrow. NEEDS SIDING JOB FOR RANGERS encroaching by 600mm upto for a length of approx 65 meters | 3447275 | 2019-12-03 11:38 | Unable possible road closure
ROC2001018 | Rayleigh | LABURNUM WAY | Os 3 | HW: overgrown vegetation (our) | Ra3=1x3 Hedging on verge and around street name plate encroaching into footway by 900mm for a length of approx 10 meters. Job for RANGERS | 3447017 | 2019-12-02 14:41 | 15.1.20
ROC2001019 | Rayleigh | DOBSONS CLOSE | Side of 141 Daws Heath Road | HW: overgrown vegetation (our) | Ra1=1x1 Hedges from verge encroaching into carriageway by 250mm for a length of approx 10 meters job for RANGERS | 3434542 | 2019-10-29 09:34 | 15.1.20
ROC2001020 | Great Wakering | WAKERING ROAD | Os 223-225 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation from verge encroaching into footway by 800mm for approx 12 meters JOB FOR RANGERS | 3447371 | 2019-12-03 14:02 | 27.1.20
ROC2001021 | Rayleigh | VERNON AVENUE | Os 33 | HW: overgrown vegetation (our) | Ra1=1x1 Grass from verges encroaching into footway by 500mm for approx 10 meters needs siding job for RANGERS | 3456288 | 2020-01-10 10:37 | 29.1.20
ROC2001022 | Rayleigh | THAMES CLOSE | Opp 8 | HW: overgrown vegetation (our) | Ra4=2x2 Hedges on verge blocking half the footway. Encroaching into footway by 1 meters in a L shape footway 6 meters Job for RANGERS | 3429272 | 2019-10-15 14:53 | 27.1.20
ROC2001023 | Rayleigh | PHILBRICK CRESCENT EAST | Os 5 | HW: overgrown vegetation (our) | Ra4=1x4 Basal growth from tree encroaching into footway by 800mm for a length of approx 2 meters . Job for RANGERS | 3432400 | 2019-10-23 09:35 | 22.1.20
ROC2001024 | Rayleigh | PHILBRICK CRESCENT EAST | Os 23 | HW: overgrown vegetation (our) | Ra2=1x2 Basal growth from tree encroaching into footway by 800mm for a length of approx 1 . Job for RANGERS | 3432396 | 2019-10-23 09:31 | 22.1.20
ROC2001025 | Rayleigh | PHILBRICK CRESCENT EAST | Os 25 | HW: overgrown vegetation (our) | Ra3=1x3 Basal growth from tree encroaching into footway by 800mm for a length of approx 2 meters . Job for RANGERS | 3432395 | 2019-10-23 09:30 | 22.1.20
ROC2001026 | Rayleigh | PHILBRICK CRESCENT EAST | Os 35 | HW: overgrown vegetation (our) | Ra2=1x2 Basal growth from tree encroaching into footway by 800mm for a length of approx 1 . Job for RANGERS | 3432389 | 2019-10-23 09:25 | 21.1.20
ROC2001027 | Sutton | SUTTON ROAD | Os Sutton Bridge Farm | HW: overgrown vegetation (our) | Ra2=1x2 vegetation from verge encroaching into footway by 400mm for an approx length of 40 meters Job for RANGERS | 3453148 | 2019-12-23 09:13 | 24.1.20
ROC2001028 | Rayleigh | LEASWAY | Remote footway 31 Crown Hill access from LC FP4 to LC FP2 | HW: overgrown vegetation (our) | Ra6=2x3 Trees ,shrubs, bramble and veg over hanging footway head height, causing obstruction to pedestrians . 59mts JOB FOR RANGERS | 3452867 | 2019-12-20 09:25 | 24.1.20
ROC2001029 | Rayleigh | KENILWORTH GARDENS | Os 6-8 | HW: overgrown vegetation (our) | Ra3=1x3 Weeds around tree base encroaching into footway by 1 meter and 2 meters high upto. For approx 2 meters in length job for RANGERS | 3431676 | 2019-10-22 11:12 | 19.1.20
ROC2001030 | Rayleigh | LITTLE WHEATLEY CHASE | Opp 3-9 | HW: overgrown vegetation (our) | Ra2=1x2 Mud and vegetation encroaching into footway by 700mm for a length of approx 30 meters. Needs siding job for RANGERS | 3455873 | 2020-01-08 14:05 | 31.1.20
ROC2002001 | Rayleigh | RECTORY GARTH | Opp 15-18 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation from verge encroaching into footway by 600mm for a length of approx 30 meters. Job for RANGERS | 3458246 | 2020-01-16 11:35 | 12.2.20
ROC2002002 | Great Wakering | WAKERING ROAD | Os 223-225 | HW: overgrown vegetation (our) | Ra1=1x1 Vegetation from verge encroaching into footway by 500mm for approx 12 meters needs back efge siding JOB FOR RANGERS | 3460037 | 2020-01-22 10:50 | 28.2.20
ROC2002003 | Great Wakering | WAKERING ROAD | Between 225-271 | HW: overgrown vegetation (our) | Ra3=1x3 Vegetation weeds and debris encroaching into FW from verge by 700mm (FW width 1.1m) for a length of approx 200m needs siding JOB FOR RANGERS | 3460035 | 2020-01-22 10:46 | 28.2.20
ROC2002004 | Great Wakering | STAIRS ROAD | 50 meters North of 181 | HW: overgrown vegetation (our) | Ra1=1x1 Vegetation branches from verge encroaching into carriageway by 200mm for a length of approx 20 meters Job for RANGERS | 3460046 | 2020-01-22 11:07 | 18.2.20
ROC2002005 | Rayleigh | ELM DRIVE | Os 7 | HW: overgrown vegetation (our) | Ra2=1x2 Grass from verges encroaching into footway by 900mm for approx 15 meters needs siding job for RANGERS | 3456717 | 2020-01-13 08:56 | 21.2.2.20
ROC2002006 | Rayleigh | LONDON ROAD | RH junction of Louis Drive East | HW: overgrown vegetation (our) | Ra1=1x1 Vegetation from hedge on verge encroaching 1 meter in visibility splay for approx 20 meters job for RANGERS | 3462051 | 2020-01-28 15:06 | 21.2.20
ROC2002007 | Rayleigh | DRAKES WAY | Opp Side of 11 | HW: overgrown vegetation (our) | Ra2=1x2 Small branches from verge encroaching into footway by 1 meter for a length of approx 30 meters Job for RANGERS | 3462253 | 2020-01-29 09:52 | 27.2.20
ROC2002008 | Rayleigh | DRAKES WAY | Opp 1-6 | HW: overgrown vegetation (our) | Ra2=1x2 Laurel hedge encroaching into footway by 700mm for a length of approx 50 meters Job for RANGERS | 3462241 | 2020-01-29 09:43 | 27.2.20
ROC2003001 | Rochford | DALYS ROAD | Opp 18 | HW: overgrown vegetation (our) | Ra2=1x2 Brambles encroaching into footway by approx 800mm for a length of approx 5 meters Job for RANGERS | 3447667 | 2019-12-04 09:17 | 3.3.20
ROC2003002 | Rayleigh | HERON GARDENS | Adj 51 | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation encroaching into footway by 1.7 meters and footway covered with moss for approx 12 meters Job for RANGERS | 3466223 | 2020-02-12 15:18 | 3.3.20
ROC2003003 | Rayleigh | LEASWAY | Remote footway 31 Crown Hill access from LC FP4 to LC FP2 | HW: overgrown vegetation (our) | Ra6=2x3 Trees ,shrubs, bramble and veg over hanging footway head height, causing obstruction to pedestrians . 59mts JOB FOR RANGERS | 3452867 | 2019-12-20 09:25 | 3.3.20
ROC2003004 | Rayleigh | LITTLE WHEATLEY CHASE | Opp 9-17 | HW: overgrown vegetation (our) | Ra2=1x2 Mud and vegetation encroaching into footway by 700mm for a length of approx 30 meters. Needs siding job for RANGERS | 3455870 | 2020-01-08 14:00 | 10.3.20
ROC2003005 | Rayleigh | LITTLE WHEATLEY CHASE | Opp 3-9 | HW: overgrown vegetation (our) | Ra2=1x2 Mud and vegetation encroaching into footway by 700mm for a length of approx 30 meters. Needs siding job for RANGERS | 3455873 | 2020-01-08 14:05 | 10.3.20
ROC2003006 | Rayleigh | REGENT CLOSE | Opp 11-14 | HW: overgrown vegetation (our) | Ra2=1x2 Vegetation from verge encroaching by 500mm for a length of approx 40 meters Job for RANGERS | 3450542 | 2019-12-12 15:44 | 4.3.20
ROC2003007 | Rayleigh | REGENT CLOSE | Opp 15-16 | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation from verge encroaching into footway by approx 1.8m for 10 meters in L shape. JOB FOR RANGERS | 3450550 | 2019-12-12 15:58 | 4.3.20
ROC2003008 | Rochford | SOUTHEND ROAD | Between 68 and 28 | HW: overgrown vegetation (our) | Ra2=1x2 Mud and vegetation debris built up along the back of footway making it narrow. NEEDS SIDING JOB FOR RANGERS encroaching by 600mm upto for a length of approx 65 meters | 3447275 | 2019-12-03 11:38 | 7.3.20
ROC2003009 | Sutton | SUTTON ROAD | Os Sutton Bridge Farm | HW: overgrown vegetation (our) | Ra2=1x2 vegetation from verge encroaching into footway by 400mm for an approx length of 40 meters Job for RANGERS | 3453148 | 2019-12-23 09:13 |  | 9.3.20
ROC2003010 | Sutton | SUTTON ROAD | Os Sutton Bridge Farm | HW: overgrown vegetation (our) | Ra2=1x2 Verge encroaching into footway by 600mm for a length of approx 40 meters. Needs siding job for RANGERS | 3453149 | 2019-12-23 09:20 |  | 9.3.20
ROC2003011 | Rayleigh | VERNON AVENUE | Os 33 | HW: overgrown vegetation (our) | Ra1=1x1 Grass from verges encroaching into footway by 500mm for approx 10 meters needs siding job for RANGERS | 3456288 | 2020-01-10 10:37 | 4.3.20
ROC2003012 | Rayleigh | FOOTPATH FROM UPPER LAMBRICKS TO LOWER L | Opp Sandy Lodge | HW: overgrown vegetation (our) | Ra4=1x4 small branches and vegetation hanging down in remote footway for approx 10 meters Job for RANGERS | 3465930 | 2020-02-12 10:13 | 3.3.20
ROC2003013 | Rayleigh | DOWNHALL PARK WAY | Side 97 Opp 77 | HW: overgrown vegetation (our) | Ra4=1x4 Vegetation from verge encroaching by 800mm (FW width 0.4m) for a length of approx 20 meters Job for RANGERS | 3450476 | 2019-12-12 13:05 | 5.3.20
ROC2003014 | Rayleigh | NORMAN CRESCENT | Junc Side 50 to Os 1 | HW: overgrown vegetation (our) | Ra3=1x3 Moss covering of footway, Approximately 26mts . Job for RANGERS | 3466345 | 2020-02-13 08:55
ROC2003015 | Rayleigh | NORMAN CRESCENT | On centre island | HW: overgrown vegetation (our) | Ra3=1x3 Moss covering full circle footway, Approximately 92mts job for RANGERS | 3466348 | 2020-02-13 08:59
ROC2003016 | Rayleigh | RAWRETH LANE | Os 159 | HW: overgrown vegetation (our) | Ra4=2x2 Hedge from verge encroaching by 500mm for a length of approx 10 meters, Brambles hanging into footway. Job for RANGERS | 3453537 | 2019-12-24 09:48 | 5.3.20
ROC2003017 | Rayleigh | RAWRETH LANE | Os 159 | HW: overgrown vegetation (our) | Ra2=1x2 Verge encroaching into footway by 600mm for a length of approx 10 meters. Needs siding job for RANGERS | 3453535 | 2019-12-24 09:45 | 6.3.20
ROC2003018 | Rayleigh | LABURNUM WAY | Os 3 | HW: overgrown vegetation (our) | Ra3=1x3 Hedging on verge and around street name plate encroaching into footway by 900mm for a length of approx 10 meters. Job for RANGERS | 3447017 | 2019-12-02 14:41 | 5.3.20
ROC2003019 | Rayleigh | BARDFIELD WAY | Adj LC 1 | HW: overgrown vegetation (our) | Ra2=1x2 Mud and vegetation encroaching into footway by 700mm for a length of approx 16 meters. Needs siding job for RANGERS | 3455838 | 2020-01-08 13:29 | 4.3.20