## Sheet1
Tendring Potential Schemes List - November 2018
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
Church Road, Brightlingsea - Zebra crossing | Concerns raised by the Colne Community College in regards to speed of traffic and for students crossing the road. | Students and pedestrians have reported issues crossing the road. | Cllr Goggin | Brightlingsea | Traffic Management | Design | LTEN152118 | 6000 | Validation - Design and consultation of zebra crossing for first year only (PV2 score = 0.217 x 10>8). College investigating relocation of pedestrian entrance. Scheme cannot progress until this has been completed.
Bateman Road, Red Barn Road, Brightlingsea - Pedestrian Refuge | Concerns raised by the Colne Community College in regards to speed of traffic and for students crossing the road. | Students and pedestrians have reported issues crossing the road. | Cllr Goggin | Brightlingsea | Traffic Management | Design | LTEN152119 | 7000 | Validation - Build out kerb line to narrow the width of carriageway, improving visibility for pedestrians.
The Street, Little Clacton, outside No 170 | Residents have raised a request for the replacement of an ageing bus shelter. | Replacement of an ageing bus shelter. | Little Clacton Parish Council | Little Clacton | Passenger Transport | Total scheme | LTEN165028 | 7000 | Replacement metal bus shelter.
Harwich Road, Little Oakley - TMI | Residents are growing increasingly concerned around the personal injury collisions on the corner of Foulton Hall on both approaches. | Speeding, lack of signage. | Little Oakley Parish Council | Little Oakley | Traffic Management | Total scheme | LTEN162023 | 5000 | Validation recommends - Speeds do not meet the intervention level for further investigation at this time. Design and implementation of package of works: • Remove redundant 30mph terminal sign from lamp column at start of Seaview Avenue • Replace large ‘bend ahead’ warning sign on existing posts opposite junction with Seaview Avenue • Replace knocked down & damaged yellow backed single chevron sign adjacent to Foulton Hall access • Cut back vegetation along same stretch of verge obscuring the single chevrons.
Mill Street, Robinsons Road, Brightlingsea - TMI | HGV's and large commercial vehicles are becoming stuck causing congestion. | HGV struggling to turn on corners of narrow roads, causing damage to residents properties . | Cllr Goggin | Brightlingsea | Traffic Management |  | LTEN162031 | TBC | In validation.
Williamsburg Avenue, Harwich - No Through Road signage | Large commercial vehicles and HGV's have been found to regularly park along Williamsburg Avenue which is a no through road. | Congestion caused by parked HGV's. | Cllr Henderson | Harwich | Traffic Management | Total scheme | LTEN162033 | 4000 | Validation - NEPP have implemented a 24hr clearway TRO. Recommended to erect a larger No through road sign with post on a clearer side of the verge which can been seen high up in HGV cabs.
Plough Road, Colles Brook Road, South Heath Road, Great Bentley - TMI | Vehicles have been reported to be travelling too fast for the current road conditions, drivers have reported lack of signage. | Speeding and lack of signage identified. | Great Bentley Parish Council | Great Bentley | Traffic Management |  | LTEN162040 | TBC | Awaiting speed and volume survey information.
Heath Road, Cansey Lane, Bradfield | Removal of old brick shelter and implementing a new wooden shelter. | Shelter deterioration. | Bradfield Parish Council | Bradfield | Passenger Transport | Total scheme | LTEN165032 | 10500 | New wooden shelter.
Heath Road, The Village Maid, Bradfield | Removal of old brick shelter and implementing a new wooden shelter. | Shelter deterioration. | Bradfield Parish Council | Bradfield | Passenger Transport | Total scheme | LTEN165033 | 10500 | New wooden shelter.
Clacton Road, Elmstead Market - Bollards | Vehicles are approaching the outside of Budgens at speed, across the kerb line without checking to see if the route is clear. | Lack of awareness from drivers | Elmstead Parish Council | Elmstead | Traffic Management | Total scheme | LTEN162036 | 5000 | Validation recommends - Design and implementation of five bollards.
Colchester Road, Great Bentley | Bus stop located on a grass verge, need for a hard standing area for passengers to stand and wait. | Lack of formal bus stop and hardstand. | Passenger Transport Team | Great Bentley | Passenger Transport | Design | LTEN165048 | 3000 | Provide area of hardstand with bus stop infrastructure.
Church Road, Brightlingsea | Request from the Town Council for the north side of Church Road at the Maltings Road Stop. This stop will cover Maltings Estate/Colne School serving passengers travelling to the town centre. | Lack of shelter identified. | Passenger Transport Team | Brightlingsea | Passenger Transport | Total scheme | LTEN165049 | 6500 | Formalise bus stop with flag, pole and shelter with a seat.
Cox's Hill, Lawford | Following development built at Cox's Hill - Shelter with infrastructure required | Lack of passenger transport infrastructure. | Passenger Transport Team | Lawford | Passenger Transport | Design | LTEN165050 | 4000 | To design and prepare locations for the implementation of two stops.
Long Road, Lawford | Residents are requesting a pedestrian crossing point to aid residents to access Lawford Primary School. | Request for a zebra crossing. | Lawford Parish Council | Lawford | Walking | Design | LTEN173001 | 6500 | Validation recommends - Criteria for a crossing point has been reached. Design, target cost and legal order within first year.
Hastings Avenue, Clacton | An alternative location for a dropped kerb and tactile paving has been requested. | Lack of dropped kerbs identified. | Cllr Honeywood | Un-parished | Walking |  | LTEN173003 | TBC | Awaiting speed and volume survey information.
Church Road, Thorrington - TMI | Vehicles using this route as a cut through with pedestrians in sections of the road due to a lack of footpath. | Perceived speeding identified. | Cllr Goggin | Thorrington | Traffic Management | Total Scheme | LTEN172005 | 3000 | Validation recommends - Replacement of faded terminal signage at the northern end of the road and the installation of a new carriageway roundel at the start of the 30mph limit at this end.
Church Road jw Well St, Spring Chase & Ladysmith Av, Brightlingsea - TMI | Complaints from residents requesting traffic calming or a mini roundabout on the jw Well Street, Spring Chase and Ladysmith Avenue. | Residents complaining over speeding and difficulty crossing the road. | Brightlingsea Town Council | Brightlingsea | Traffic Management | Feasibility | LTEN172007 | 5000 | Validation completed - Recommended to progress to feasibility study.
Rail Station to Marine Parade, Clacton - Cycle Route | Following ECC's cycling strategy, improvements to the NCR150 and links to the station have been requested. | Lack of cycle route identified. | Cllr Sargeant | Un-parished | Cycling |  | LTEN174001 | TBC | In validation.
Kings Avenue, Holland-on-sea | Complaints received from residents in regards to a lack of tactile pavement at dropped kerbs by the shopping parade. | Lack of tactile paving identified. | Cllr Sargeant | Un-parished | Walking | Total scheme | LTEN173004 | 6000 | Validation - Design and implementation of dropped crossing and tactile paving.
Wellington Road jw Church Street, Harwich - TMI | Concerns raised by local residents regarding visibility issues, lack of give way signs and faded road markings. | Lack of visibility from Wellington Road into Church Street. | Cllr Henderson | Harwich Peninsula | Traffic Management | Total scheme | LTEN172010 | 10000 | Validation recommends - Design and implementation to change the working priority at the junction giving Church Street the priority.
The Esplanade, Holland-on-Sea | Mobility scooter users and parents with pushchairs are being forced onto the grass verges due to parked vehicles. | Parking on footway. | Cllr Sargeant | Un-parished | Walking |  | LTEN173005 | TBC | County Member checking highway boundary with Tendring DC.
Holland Road, Clacton-on-Sea - TMI | Severe corrosion has caused damage to the pole and electrics. Wiring has become compromised. | Faulty school crossing wig wag sign. | Cllr Sargeant | Un-parished | Traffic Management |  | LTEN172014 | TBC | In validation.
Golf Green Road, Jaywick - TMI | Residents have complained about vehicle crashes and near misses caused by speeding vehicles. | Speeding issues reported. | Cllr Honeywood | Un-parished | Traffic Management |  | LTEN172015 | TBC | 180m S of j/w Jasmine Way. 30mph speed limit. Southbound av: 28.7mph Northbound av: 29.2mph The results show that there is good compliance against the posted 30mph. Speeds do not meet the intervention level for further investigation at this time.
The Street, Kirby-le-Soken - TMI | Residents have complained that two cars cannot pass on a section of road. Request for priority vehicle signage. | Two cars are unable to pass due to narrow carriageway width. | Cllr Platt | Frinton & Walton | Traffic Management | Feasibility | LTEN172016 | 5000 | Validation recommended - Progress a Feasibility Study to investigate the cost of potentially extending the electric main with Priority working signage at either end of the approach.
Cloes Lane, Clacton - TMI | Residents have reported issues crossing the road in a safe location due to reported speeding vehicles. | Lack of formal crossing point. | Cllr Wood | Un-parished | Traffic Management | Design | LTEN173006 | 6000 | Validation recommends - Detailed design, target costing and TRO advertising within the first financial year. 30mph speed limit CDPV2 = 0.920 x 10^8 Southbound av: 28.5mph Northbound av: 28.6mph.
Pork Lane, Frinton & Walton - TMI | Residents reported issues with speeding and large commercial vehicles using the route. | Speeding, HGV usage. | Cllr Platt | Frinton & Walton | Traffic Management | Total scheme | LTEN172018 | 3000 | Validation recommends - Unsuitable for HGV signage to be placed at either end of Pork Lane to deter unfamiliar large vehicles from using the route.
Golden Lane, Thorpe-le-Soken - TMI | Request received to investigate speeding, HGV usage and verge protection for ditch. | Speeding issues reported. | Cllr Erskine | Thorpe-Le-Soken | Traffic Management |  | LTEN172022 | TBC | Current speed limit: 30mph Southwest bound: 33.2mph Northeast bound: 31.5mph 2nd Speed and Volume survey - Southwest bound - 31.2mph Northwest bound - 29.9mph Now in Validation
Parkeston Road, Harwich - Crossing point | Spring Meadow Primary School, parents and local councillors are concerned over pedestrian safety and the speed of vehicles using this route. | Safety crossing the road, vehicle speeds. | Cllr Henderson | Harwich Town Council | Traffic Management | Feasibility | LTEN173007 | 4000 | Validation completed - Recommendation to complete feasibility study due to a number of potential issues that will need fully investigating.
Valley Road , Clacton-on-Sea - Crossing point | Implementation of zebra crossing following completion of detailed design. | Difficulty crossing the road | Cllr Sargeant | Un-parished | Traffic Management | Implementation | LTEN163007 | TBC | Implementation of zebra crossing following completed design. Awaiting target costing information.
Bromley Road, Slough Lane, Ardleigh - TMI | Residents have called for investigation into a weight limit restriction. | HGV's & large commercial vehicles using route. | Cllr Guglielmi | Ardleigh | Traffic Management | Design | LTEN172024 | 5000 | Validation recommends - Scheme to review all of the existing TRO’s for weight/height restrictions within the parish of Ardleigh and adjoining areas. To include target cost.
Entrance to Weeley on B1033 Colchester Rd, Thorpe Rd, Weeley - Gateway feature | Implementation of recommended solutions following completed detailed design. | Speeding issues reported. | Cllr Erskine | Weeley | Traffic Management | Total scheme | LTEN152124 | TBC | Implementation of recommended solutions following completed detailed design.
High Street, Mistley - Stop infrastructure | Post Office, High Street, Mistley – although there is a timetable adjacent to the Post Office, the bus stop yellow road sign has almost completely faded on the road and there are no bus stop signs on either side of the road. (ID 29007011 / 29007Y11) | Lack of formalised stops on either side of road. | Cllr Guglielmi | Mistley | Passenger Transport | Total scheme | LTEN175002 | 5500 | Bus Stop protection marking and bus stop infrastructure on both sides.
Harwich Road, Mistley - Stop infrastructure | Rigby Avenue, Harwich Road, Mistley - both bus stop signs are old and need replacing. (ID IM63 / IM63b) | Deteriorating infrastructure. | Cllr Guglielmi | Mistley | Passenger Transport | Total scheme | LTEN175003 | 3000 | Replacement bus infrastructure includes 2 poles, 2 flags and 2 timetables.
Harwich Road, Mistley - Stop infrastructure | Chapel Cut, Harwich Road, Mistley – both bus stop signs are old and need replacing and neither has a timetable (ID296007010 / 29007009) | Deteriorating infrastructure. | Cllr Guglielmi | Mistley | Passenger Transport | Total scheme | LTEN175004 | 3000 | Replacement bus infrastructure includes 2 poles, 2 flags and 2 timetables.
Long Road, Manningtree | A long stay care complex is located close by but the nearest bus stop is located over 400m away. | Lack of formal bus stop and hardstand. | Passenger Transport Team | Lawford | Passenger Transport | Total scheme | LTEN175005 | 3000 | Implementation of bus stop infrastructure for two stops, one on either side of the road.
New Road, Mistley | A request for improved bus stop infrastructure close to the Church and Mistley Place Park Tearooms. | Lack of marked bus stops. | Mistley Parish Council | Mistley | Passenger Transport | Total scheme | LTEN175006 | 4000 | formalise bus stops with poles, flags and timetables.
New Road jw The Park, Mistley | A request for improved bus stop infrastructure close to the junction with The Park. | Lack of marked bus stops. | Mistley Parish Council | Mistley | Passenger Transport | Total scheme | LTEN175007 | 5000 | North bound stop: Pole, flag and 23m yellow cage. Southbound stop: 23m yellow cage.
Frating Road, Harwich Road, Great Bromley | The Parish Council has received funding for the implementation of two VAS. The request must first be validated to ascertain if the criteria can be met. | Speeding issues reported | Great Bromley Parish Council | Great Bromley | Traffic Management |  | LTEN172032 | TBC | In validation.
Ruaton Drive, Stambridge Road, Clacton-on-Sea | Vehicles have been seen using a footway to cut through between two local roads. | Vehicles using footway as a cut through. | Cllr Wood | Clacton-on-Sea | Traffic Management | Total scheme | LTEN172033 | 3300 | Validation recommends - Design and installation of a bollard at either end of the alley to prevent vehicles passing through. Bollards to match those which are installed on shared footway/cycleway nearby.
Wellesley Road, Clacton-on-Sea | Busy PR1 route with perceived high speeds at points of the day where traffic flows are lower. | Speeding issues reported | Cllr Sargeant | Non parished | Traffic Management |  | LTEN172035 | N/A | 65m south of j/w Berkeley Road/Wellesley Road. Speed limit = 30mph Southbound: 30.3mph The results show that there is good compliance against the posted 30mph. Recommendation not to progress further with this request.
The Walls, Mistley | Residents experience difficulty crossing the road to and from the bus stops, shops and to access the river front. | Lack of crossing point identified. | Cllr Guglielmi | Mistley | Walking |  | LTEN173008 | TBC | 25m w of jw Kiln Lane. Speed limit = 30mph. Eastbound av: 28.6mph Westbound av: 29.1mph CDPV2 score = 0.0044 x 10^8. The score does not meet the minimum requirements to progress further investigation for a crossing point at this location.
Suffolk Street, Frinton | Vehicles of unsuitable size using road and becoming stuck and having to reverse out. | Vehicles becoming stuck | Cllr Platt | Frinton & Walton | Traffic Management |  | LTEN172037 | TBC | Adj No.21, 40m NW of jw B1034 The Parade. Speed Limit = 30mph Eastbound av: 9.2mph Westbound av: 12.6mph Survey results fed into validation request.
B1027 jw Clacton Road, St. Osyth | The Parish have raised concerns as to the increase of traffic waiting at the junction. | Congestion | St. Osyth Parish Council | St. Osyth | Traffic Management |  | LTEN182005 | TBC | In validation - Speed and volume survey information to feed into validation request.
A137 Harwich Road, Lawford | HGV usage of laybys in the evening is causing environmental issues. | Parked HGV's causing environmental issues. | Cllr Gulielmi | Lawford Parish Council | Traffic Management |  | LTEN182009 | TBC | In validation.
School Lane, Lawford | HGV's are using the route as a rat run between Wignall Street and Grange Road. | HGV becoming stuck and cannot reverse. | Cllr Gulielmi | Lawford Parish Council | Traffic Management |  | LTEN182002 | TBC | In validation.
Rectory Road, Little Bentley | Near misses and speeding issues have been reported to the Parish Council. Request to extend speed limit. | Speeding issues reported. | Little Bentley Parish Council | Little Bentley Parish Council | Traffic Management |  | LTEN182003 | TBC | Awaiting speed and volume survey information.
Ravens Green Road, Little Bentley | Lack of signage, lining and speeding vehicles has been raised to the Parish Council. | Speeding issues reported. | Little Bentley Parish Council | Little Bentley Parish Council | Traffic Management |  | LTEN182004 | TBC | Awaiting speed and volume survey information.
Alresford Road, Elmstead | Local residents are calling for investigation into a speed limit reduction to cover the row of houses on the eastern side of Alresford Road between The Chase and Sunnymean Farm. | Speeding issues reported. | Cllr Guglielmi | Elmstead | Traffic Management |  | LTEN182015 | TBC | Speed and volume survey information relayed back to Cllr Guglielmi.
St. Osyth Road, Clacton-on-Sea | Residents of St. Osyth Road have complained to the County Member and the MP regarding vehicle speeds and noise. | Speeding issues reported. | Cllr Wood | Un-parished | Traffic Management |  | LTEN182006 | TBC | Speed and volume survey received, no evidence of speeding issues. Emailed Cllr Wood on the data.
London Road, Little Clacton | Local residents of Little Clacton have requested a crossing point close to No. 11. | Lack of crossing point identified. | Cllr Erskine | Little Clacton | Walking |  | LTEN183001 | TBC | Awaiting pedestrian, vehicle conflict survey information.
Constable Avenue, Clacton-on-Sea | Local residents of Little Clacton have requested a crossing point close to No. 248. | Lack of crossing point identified. | Cllr Wood | Un-parished | Walking |  | LTEN183002 | TBC | Survey information fed back to Cllr Erskine.
Wix Road, Ramsey & Parkeston | Large commercial vehicles and HGV's have been found using an unsuitable local route. | HGV's using unsuitable local route. | Cllr Erskine | Ramsey & Parkeston | Traffic Management |  | LTEN182008 | TBC | Awaiting speed and volume survey information.
Frinton Road, Clacton-on-Sea | The owner of Little Holland Hall has contacted the County Member to request an elderly persons crossing sign either side of the Care Home. | Lack of elderly persons signage. | Cllr Sargeant | Un-parished | Traffic Management |  | LTEN182010 | TBC | In validation.
Luff Way, Walton-on-the-Naze | The County Member has requested investigation for yellow lineage and dropped kerbing outside of a care home to safe passage to cross the road. | Lack of dropped kerbing/parking restrictions. | Cllr Platt | Frinton & Walton | Walking |  | LTEN183003 | TBC | In validation
East Street, Harwich | HGV's are using East Street to make deliveries but are using areas of the footway to turn, damaging properties. | Large commercial vehicles endangering pedestrians and property. | Cllr Henderson | Harwich Town Council | Walking |  | LTEN183004 | TBC | In validation.
Kings Parade, Holland-on-Sea | Local residents are requesting investigation into a crossing point to the seafront. | Lack of crossing point identified. | Cllr Sargeant | Un-parished | Walking |  | LTEN183005 | TBC | In Validation.
Brook Street, High Street, Manningtree | Local residents of Brook Street and the High Street have complained to the County Member regarding vehicle speeds. | Speeding issues reported. | Cllr Guglielmi | Manningtree Town Council | Traffic Management | Surveys | LTEN182011 | TBC | Awaiting speed and volume survey information.
Bentley Road, Little Bromley | Request from the Parish Council to investigate lowering the limit in line with the rest of the village. | Speeding issues reported. | Cllr Guglielmi | Little Bromley | Traffic Management |  | LTEN182012 | TBC | Awaiting speed and volume survey information.
Plough Road, Aingers Green | Complaints received from local residents in regards to perceived speeding and HGV's using an unsuitable route. | Speeding, HGV usage. | Cllr Goggin | Great Bentley | Traffic Management |  | LTEN182013 | TBC | Data received, no evidence to percieved speeding issues. HGV usage 9%. Emailed Cllr Goggin with results.
Queen Street, Great Oakely | Residents of Queen Street have requested investigation into a narrow street where vehicles are becoming stuck and damaging properties. | Commercial vehicles damaging properties. | Cllr Erskine | Great Oakely | Traffic Management |  | LTEN182014 | TBC | In validation.
Colchester Road, Great Bromley | Residents complaints regarding speed of vehicles travelling along Colchester Road. Request to extend 40mph limit cover additional properties. | Speeding issues. | Great Bromley Parish Council | Great Bromley | Traffic Management |  | LTEN182016 | 200 | Awaiting speed and volume survey information.
Colchester Road, Elmstead | Local residents have complained to the parish council regarding perceived speeding issues and pedestrians experiencing issues crossing the road. | Speeding issues and difficulty crossing the road. | Elmstead Parish Council | Elmstead | Walking |  | LTEN183006 |  | Speed and Volume Survey Data and PV2 Received, needs to be sent for validation.
Frinton Road, Holland-on-Sea | Cllr Sargeant has requested that parking areas are reviewed outside the shops on Frinton Road. | Parking and visibility issues. | Cllr Sargeant | Un-parished | Traffic Management |  | LTEN182017 |  | Emailed Cllr Sargeant explaining that this is a NEPP issue, and the shop frontings are not publicly maintainable highway.
Heckfords Road, Great Bentley | Great Bentley Parish Council have raised the provision of introducing a no right turn on to the A133. | Visibility issues | Great Bentley Parish Council | Great Bentley | Traffic Management |  | LTEN182018 |  | Awaiting collision data from RSE team.
Great Bentley Road, Frating | Local residents have requested that the timings of the fixed signals are to be changed, due to perceived congestion. | Congestion | Cllr Goggin | Frating | Traffic Management |  | LTEN182019 | 2000 | In validation.
Thorrington Road, Great Bentley | Local residents have requested that Stop Signs are implemented rather than give way, due to a number of collisions being reported. | Vehicles failing to acknowledge road signs. | Great Bentley Parish Council | Thorrington | Traffic Management |  | LTEN182020 |  | In validation.
B1027 Flag Hill, St. Osyth | Elderly local residents are experiencing difficulty crossing the road to reach the bus stop due to the current speed limti of the road. | Elderly residents crossing road. | Cllr Goggin | St. Osyth | Traffic Management |  | LTEN182021
St John's Road, Clacton-on-Sea | Cllr Sargeant has requested that investigations are made into placing a crossing point as elderly residents are having difficulites crossing the road. | Difficulty crossing the road | Cllr Sargeant | Un-parished | Traffic Management | Surveys | LTEN182023
Marine Parade East j/w Beach Road, Clacton-on-Sea | Vehicles are entering Beach Road from Marine Parade East from the exit. | Vehicles entering the wrong side of the junction. | Cllr Honeywood | Non parished | Traffic Management |  | LTEN182024
Heath Road/The Street, Bradfield | Local residents have raised concerns regarding speeding speeding issues along Heath Road and The Street | Speeding issues reported | Bradfield Parish Council | Bradfield | Traffic Management | Surveys | LTEN182025 |  | Awaiting speed and volume survey information