## Sheet1
Tendring Local Highway Panel - Potential Schemes List - September 2019
Scheme name | Description | Problem | Requested by | Parish | Scheme Category | Scheme stage | Cost Code | Budget | Comments
Church Road, Brightlingsea - Zebra crossing | Concerns raised by the Colne Community College in regards to speed of traffic and for students crossing the road. | Students and pedestrians have reported issues crossing the road. | Cllr Goggin | Brightlingsea | Traffic Management | Design | LTEN152118 | TBC | Validation - Design and consultation of zebra crossing for first year only (PV2 score = 0.217 x 10^8). College investigating relocation of pedestrian entrance. Scheme cannot progress until this has been completed.
The Street, Little Clacton, outside No 170 - Replacement shelter | Residents have raised a request for the replacement of an ageing bus shelter. | Replacement of an ageing bus shelter. | Little Clacton Parish Council | Little Clacton | Passenger Transport | Total scheme | LTEN165028 | TBC
Mill Street, Robinsons Road, Brightlingsea - Traffic management improvements | HGV's and large commercial vehicles are becoming stuck causing congestion. | HGV struggling to turn on corners of narrow roads, causing damage to residents properties. | Cllr Goggin | Brightlingsea | Traffic Management | Total scheme | LTEN162031 | N/A | Validation recommends not to proceed with this request. Brightlingsea Town Council to liaise with the developments within the town which is contributing to the HGV movements.
Heath Road, Cansey Lane, Bradfield - Replacement shelter | Removal of old brick shelter and implementing a new wooden shelter. | Shelter deterioration. | Bradfield Parish Council | Bradfield | Passenger Transport | Total scheme | LTEN165032 | TBC
Heath Road, The Village Maid, Bradfield - Replacement shelter | Removal of old brick shelter and implementing a new wooden shelter. | Shelter deterioration. | Bradfield Parish Council | Bradfield | Passenger Transport | Total scheme | LTEN165033 | TBC
Church Road, Brightlingsea - New shelter | Request from the Town Council for the north side of Church Road at the Maltings Road Stop. This stop will cover Maltings Estate/Colne School serving passengers travelling to the town centre. | Lack of shelter identified. | Passenger Transport Team | Brightlingsea | Passenger Transport | Total scheme | LTEN165049 | TBC
Cox's Hill, Lawford - New shelters | Following development built at Cox's Hill - Shelter with infrastructure required. | Lack of passenger transport infrastructure. | Passenger Transport Team | Lawford | Passenger Transport | Total scheme | LTEN165050 | TBC
Chapel Lane, Thorrington - One way street | Implementation of recommended solutions following completed feasibility study. | Congestion along Chapel Lane. | Thorrington Parish Council | Thorrington | Traffic Management | Total scheme | LTEN162008 | TBC | The CMA has been signed by the Cabinet Member recommending not to proceed with the design of the one way system.
Suffolk Street, Walton-on-the-Naze - Width restriction | Vehicles of unsuitable size using road and becoming stuck and having to reverse out. | Vehicles becoming stuck. | Cllr Platt | Frinton and Walton | Traffic Management | Total scheme | LTEN172037 | 5000 | Site meeting held on 17/05/2019, which concluded to investigate the design and implementation of a width restriction.
Rectory Road, Little Bentley - Traffic management improvements | Near misses and speeding concerns have been reported to the Parish Council. Request to extend speed limit. | Speeding issues reported. | Little Bentley Parish Council | Little Bentley Parish Council | Traffic Management | Validation | LTEN182003 | TBC | Awaiting reply from Parish on where to undertake speed and volume survey.
Ravens Green Road, Little Bentley - Traffic management improvements | Lack of signage, lining and speeding concerns have been raised to the Parish Council. | Speeding issues reported. | Little Bentley Parish Council | Little Bentley Parish Council | Traffic Management | Validation | LTEN182004 | TBC | Awaiting reply from Parish on where to undertake speed and volume survey.
Alresford Road, Elmstead - Speed limit | Local residents are calling for investigation into a speed limit reduction to cover the row of houses on the eastern side of Alresford Road between The Chase and Sunnymead Farm. | Speeding issues reported. | Elmstead Parish Council | Elmstead | Traffic Management | Total scheme | LTEN182015 | TBC | Speed and volume survey information relayed back to Cllr Guglielmi. Awaiting confirmation of S106 contributions.
London Road, Little Clacton - Zebra crossing | Local residents of Little Clacton have requested a crossing point close to No. 11. | Lack of crossing point identified. | Cllr Erskine | Little Clacton | Walking | Total scheme | LTEN183001 | N/A | 85th percentile speeds recorded (35.1mph southbound, 35.5mph northbound) a CMA is being prepared for Cabinet Member approval.
Colchester Road, Elmstead - Crossing point | Local residents have complained to the Parish Council regarding perceived speeding issues and pedestrians experiencing issues crossing the road. | Speeding issues and difficulty crossing the road. | Elmstead Parish Council | Elmstead | Walking | Total scheme | LTEN183006 | TBC | Awaiting confirmation of S106 contributions.
Frinton Road, Holland-on-Sea - Signage | Cllr Sargeant has requested that parking arrangements are reviewed outside the shops on Frinton Road. | Parking and visibility issues. | Cllr Sargeant | Unparished | Traffic Management | Total scheme | LTEN182017 | 2000 | Validation recommends - Design and implementation of a sign to denote the free car park on Ipswich Road.
Heckfords Road, Great Bentley - No right turn | Great Bentley Parish Council have raised the provision of introducing a no right turn on to the A133. | Visibility issues. | Great Bentley Parish Council | Great Bentley | Traffic Management | Total scheme | LTEN182018 | N/A | Validation recommends not to proceed with this request, as installing a no right turn facility at this location is likely to push traffic down routes which are thought to be less suitable.
B1027 Flag Hill, St. Osyth - Signing improvements | Elderly local residents are experiencing difficulty crossing the road to reach the bus stop due to the current speed limit of the road. | Elderly residents crossing road. | Cllr Goggin | St. Osyth | Traffic Management | Total scheme | LTEN182021 | TBC | A speed reduction from 60mph to 40mph is outside policy but a CMA could be written to seek Cabinet Member's view given the existing speed limits in the area and the significant development along this stretch of road.
Frinton Road, Holland-on-Sea j/w Primrose Road - Pedestrian crossing | Cllr Sargeant has requested urgent investigation following recent near misses at the junction with Primrose Road. | Difficulty crossing the road. | Cllr Sargeant | Holland-on-Sea | Traffic Management | Total scheme | LTEN182026 | N/A | Highways Surgery was held on 30th April 2019 which concluded that it was not possible to install a crossing point at this location.
Sladbury's Lane, Clacton-on-Sea (Old House) - Bend improvements | Request to investigate protection of the properties on the bend. | Safety Issues. | Cllr Erskine | Unparished | Traffic Management | Total scheme | LTEN182027 | 81000 | Validation identified a package of 3 potential solutions to the issues raised. Option 1 - Carriageway resurfacing at £81,000 for design and implementation. Option 2 - Road marking refreshments at £2,000 for design and implementation. Option 3 - Replacement signage works at £6,000.
Seafields Road, Holland-on-Sea - Verge protection | The County Member has requested investigation on this route due to the verges being destroyed by inconsiderate parking. | It has been reported that vehicles are parking inconsiderately which is forcing service vehicles onto the verges. | Cllr Sargeant | Unparished | Traffic Management | Total scheme | LTEN182028 | 8000 | Validation recommends - Convert the verge area into concrete to allow vehicles to overrun should they need to.
Weeley Heath Gateway Signage, Weeley - Gateway | Request to investigate installing gateway features in Weeley Heath. | Gateway features have been requested to identify the village of Weeley Heath. | Cllr Erskine | Weeley | Traffic Management | Total scheme | LTEN182030 | 9500 | Validation recommends to proceed with the design and implementation of 3 gateway features, similar to the ones identifying Little Clacton village.
Tendring Road, Thorpe-le-Soken - Speed reduction | Request to investigate changing the speed limit in line with the B1033 from 60mph to 40mph. | Speeding issues have been raised. Speed limit reduction in line with a recent development. | Cllr Erskine | Thorpe-le-Soken | Traffic Management | Total Scheme | LTEN182031 | 6500 | Validation recommends - Proceed to design, advertising and implementation within one year.
Thorrington Road, Great Bentley - New footway | Feasibility Study into new footway link for Brook Farm to Great Bentley. | Footpath connection missing between the village sign on Thorrington Road up to Brook Farm. | Great Bentley Parish Council | Great Bentley | Walking | Total scheme | LTEN163002 | N/A | Feasibility study concluded that it is not recommended to proceed due to the few people that would benefit from a footway being installed.
Various locations around Manningtree - Signage review | Signage review to look into the untidy/unnecessary and outdated signage around the town of Manningtree. | Confusing/unnecessary signage around the entire town of Manningtree. | Cllr Guglielmi | Lawford | Traffic Management | Total scheme | LTEN162009 | 5000 | A package of signage improvements identified in the study. Report distributed to Cllr Guglielmi. Parish have agreed to present the ideas to the Panel following the completed feasibility study.
Main Road, Harwich - 20's Plenty | Request for 20's Plenty signage to be placed outside All Saints Primary School. | Request for 20's Plenty. | Cllr Henderson | Harwich | Traffic Management | Total scheme | LTEN182032 | 3000 | Validation recommends to proceed with the design and implementation of two "20's Plenty" signs. Exact locations to be identified at design stage.
Eastern Road, Brightlingsea - 20's Plenty | Request for 20's Plenty signage to be placed outside Brightlingsea Primary School. | Request for 20's Plenty. | Cllr Goggin | Brightlingsea | Traffic Management | Total scheme | LTEN182033 | N/A | Validation recommends no further action, as it is not thought that the signage would be seen at this location.
Chase Lane, Harwich - 20's Plenty | Request for 20's Plenty signage to be placed outside Chase Lane Primary School. | Request for 20's Plenty. | Cllr Henderson | Harwich | Traffic Management | Total scheme | LTEN182034 | N/A | Validation recommends - No further action as the school does not front the carriageway. Information fed back to Cllr Henderson.
Walton Road, Clacton-on-Sea - 20's Plenty | Request for 20's Plenty signage to be placed outside Clacton County High School. | Request for 20's Plenty. | Cllr Sargeant | Unparished | Traffic Management | Total scheme | LTEN182035 | 3000 | Validation recommends not to install 20's Plenty signage, however the faded existing signage could be replaced, and 'New Road Layout' signage could be removed.
Plough Road, Great Bentley - 20's Plenty | Request for 20's Plenty signage to be placed outside Great Bentley Primary School. | Request for 20's Plenty. | Cllr Goggin | Great Bentley | Traffic Management | Total scheme | LTEN182036 | N/A | Validation recommends not to proceed with this request, due to a level crossing and a high amount of signage being present.
Hall Lane, Harwich - 20's Plenty | Request for 20's Plenty signage to be placed outside Harwich and Dovercourt High School. | Request for 20's Plenty. | Cllr Henderson | Harwich | Traffic Management | Total scheme | LTEN182037 | 3000 | Validation recommends to proceed with the design and implementation of 20's Plenty signage. Exact locations to be identified at the design stage.
Barrack Lane, Harwich - 20's Plenty | Request for 20's Plenty signage to be placed outside Harwich Community Primary School. | Request for 20's Plenty. | Cllr Henderson | Harwich | Traffic Management | Total scheme | LTEN182038 | 3000 | Validation recommends to proceed with the design and implementation of 20's Plenty signage. Exact locations to be identified at the design stage.
Holland Road, Clacton-on-Sea - 20's Plenty | Request for 20's Plenty signage to be placed outside Holland Park Primary School. | Request for 20's Plenty. | Cllr Sargeant | Unparished | Traffic Management | Total scheme | LTEN182039 | N/A | Validation recommends not to proceed with this request, due to a large amount of signage being present as well as a school crossing patrol.
Pound Farm Drive, Harwich - 20's Plenty | Request for 20's Plenty signage to be placed outside Spring Meadow Primary School. | Request for 20's Plenty. | Cllr Henderson | Harwich | Traffic Management | Total scheme | LTEN182040 | N/A | Validation recommends not to proceed with this request, due to a large amount of vehicle parking and narrow road widths.
The Drive, Harwich - 20's Plenty | Request for 20's Plenty signage to be placed outside St Josephs Catholic School. | Request for 20's Plenty. | Cllr Henderson | Harwich | Traffic Management | Validation | LTEN182041 | TBC | In validation. Speed and volume survey required to assess suitability.
St Osyth Road East, Clacton-on-Sea - 20's Plenty | Request for 20's Plenty signage to be placed outside Engaines Primary School. | Request for 20's Plenty. | Cllr Erskine | Little Clacton | Traffic Management | Total scheme | LTEN182042 | N/A | Validation recommends not to proceed with the request due to the narrow width of the footway.
Beaumont Road, Great Oakley - 20's Plenty | Request for 20's Plenty signage to be placed outside All Saints (Great Oakley) Primary School. | Request for 20's Plenty. | Cllr Erskine | Great Oakley | Traffic Management | Total scheme | LTEN182043 | N/A | Validation recommends - 20's Plenty signage is thought to confuse drivers as there are too many speed limit changes in the area. Advised not to proceed with this request. Information fed back to Cllr Erskine.
Oakleigh Close, Weeley - 20's Plenty | Request for 20's Plenty signage to be placed outside St Andrews Primary School. | Request for 20's Plenty. | Cllr Erskine | Weeley | Traffic Management | Total scheme | LTEN182044 | N/A | Validation recommends - 20's Plenty would not meet the criteria at this location due to a lot of vehicles parking along the carriageway. Information sent to Cllr Erskine.
Mayes Lane, Ramsey - 20's Plenty | Request for 20's Plenty signage to be placed outside Two Village Primary School. | Request for 20's Plenty. | Cllr Erskine | Little Oakley | Traffic Management | Total scheme | LTEN182045 | N/A | Validation recommends - 20's Plenty signage would not meet the criteria stated within the Highways Practice Notice as the school does not front the carriageway. Information fed back to Cllr Erskine.
Alton Park Road, Clacton-on-Sea - 20's Plenty | Request for 20's Plenty signage to be placed outside Alton Park Primary School. | Request for 20's Plenty. | Cllr Honeywood | Unparished | Traffic Management | Total scheme | LTEN182046 | 3000 | Validation recommends to proceed with the design and implementation of 20's Plenty signage. Exact locations to be identified at the design stage.
Heath Road, Bradfield - 20's Plenty | Request for 20's Plenty signage to be placed outside Bradfield Primary School. | Request for 20's Plenty. | Cllr Guglielmi | Bradfield | Traffic Management | Total scheme | LTEN182047 | N/A | Validation recommends not to proceed with the request due to the lack of capacity to install signage at this location.
Fifth Avenue, Frinton-on-Sea - 20's Plenty | Request for 20's Plenty signage to be placed outside Frinton on Sea Primary School. | Request for 20's Plenty. | Cllr Platt | Frinton and Walton | Traffic Management | Total scheme | LTEN182048 | N/A | Informal consultation has received objections to the scheme, therefore it is not recommended to proceed with the request.
Elm Tree Avenue, Walton-on-the-Naze - 20's Plenty | Request for 20's Plenty signage to be placed outside Hamford Primary Academy. | Request for 20's Plenty. | Cllr Platt | Frinton & Walton | Traffic Management | Total scheme | LTEN182049 | N/A | Validation recommends not to proceed with the request due to extensive features within the school already being present. Information shared with Cllr Platt.
Colchester Road, Lawford - 20's Plenty | Request for 20's Plenty signage to be placed outside Highfields Primary School and Manningtree High. | Request for 20's Plenty. | Cllr Guglielmi | Lawford | Traffic Management | Total scheme | LTEN182050 | 3000 | Validation recommends to proceed with the design and implementation of two "20's Plenty" signs. Exact locations to be identified at design stage.
Halstead Road, Kirby Cross - 20's Plenty | Request for 20's Plenty signage to be placed outside Kirby Primary Academy. | Request for 20's Plenty. | Cllr Platt | Frinton and Walton | Traffic Management | Total scheme | LTEN182051 | 3000 | Validation recommends to proceed with the design and implementation of two "20's Plenty" signs. Exact locations to be identified at design stage.
Long Road, Lawford - 20's Plenty | Request for 20's Plenty signage to be placed outside Lawford Primary School. | Request for 20's Plenty. | Cllr Guglielmi | Lawford | Traffic Management | Total scheme | LTEN182052 | N/A | Validation recommends not to proceed with the request, due to a possible zebra crossing being installed at this location.
School Road, Elmstead - 20's Plenty | Request for 20's Plenty signage to be placed outside Market Fields School. | Request for 20's Plenty. | Cllr Guglielmi | Elmstead | Traffic Management | Total scheme | LTEN182053 | TBC | Validation recommends to proceed with the design and implementation of two "20's Plenty" signs. Exact locations to be identified at design stage.
Cloes Lane, Clacton-on-Sea - 20's Plenty | Request for 20's Plenty signage to be placed outside St Clares Primary School. | Request for 20's Plenty. | Cllr Wood | Unparished | Traffic Management | Total scheme | LTEN182054 | N/A | Validation recommends not to proceed with the request due amount of existing signage highlighting other hazards.
Brook Street, Great Bromley - Signing and lining | Request for 20's Plenty signage to be placed outside St Georges Primary School. | Request for 20's Plenty. | Cllr Guglielmi | Great Bromley | Traffic Management | Total scheme | LTEN182055 | 5000 | Validation recommends not to install 20's Plenty signage, however the faded existing signage could be replaced and the lining could be refreshed.
Norman Close, St Osyth - 20's Plenty | Request for 20's Plenty signage to be placed outside St Osyth Primary School. | Request for 20's Plenty. | Cllr Goggin | St Osyth | Traffic Management | Total scheme | LTEN182056 | 2000 | Validation recommends to design and implement one 20's Plenty sign, due to cul-de-sac nature. Exact locations to be identified at design stage.
Hadleigh Road, Frinton-on-Sea - 20's Plenty | Request for 20's Plenty signage to be placed outside St Philomenas Catholic School. | Request for 20's Plenty. | Cllr Platt | Frinton and Walton | Traffic Management | Total scheme | LTEN182057 | 3000 | This scheme has been proposed to be cancelled by Cllr Platt.
School Road, Tendring - 20's Plenty | Request for 20's Plenty signage to be placed outside Tendring Primary School. | Request for 20's Plenty. | Cllr Guglielmi | Tendring | Traffic Management | Validation | LTEN182058 | N/A | Validation recommends not to proceed with the request due to the number of features that currently exist on site.
Standley Road, Walton-on-the-Naze - 20's Plenty | Request for 20's Plenty signage to be placed outside Walton on the Naze Primary School. | Request for 20's Plenty. | Cllr Platt | Frinton and Walton | Traffic Management | Total scheme | LTEN182059 | 3000 | Validation recommends to design and implement two 20's Plenty signs. Exact locations to be identified at the design stage.
Colchester Road, Wix - 20's Plenty | Request for 20's Plenty signage to be placed outside Wix and Wrabness Primary School. | Request for 20's Plenty. | Cllr Guglielmi | Wix | Traffic Management | Total scheme | LTEN182060 | 3500 | Validation recommends to remove 2 of the existing school signs and replace with 20's Plenty signage.
Bridge over Holland Brook, Church Road, Little Bentley - Priority working signage | The bridge over Holland Brook on Church Road in Little Bentley is too narrow to allow for two larger vehicles to pass simultaneously. | Congestion/accidents have been witnessed on the bridge. | Cllr Guglielmi | Little Bentley | Traffic Management | Total Scheme | LTEN142079 | 5000 | Design and implementation of signage improvements following a feasibility study.
The Street, Ramsey - HGV signage | Request to investigate placing "unsuitable for HGVs" signage in order to further deter vehicles from using the route. | HGVs getting stuck along the route. | Cllr Erskine | Ramsey and Parkeston | Traffic Management | Validation | LTEN182061 | TBC | In validation.
Clacton Road, Weeley Heath - Repeater signage | Request for 30mph repeaters and roundels to be installed to remind drivers of the speed limit. | Speeding vehicles. | Cllr Erskine | Weeley | Traffic Management | Total scheme | LTEN182062 | 6500 | Validation recommends to review the TRO, street lighting and repeater signage, as well as design and implement roundels and vegetation clearance.
Little Clacton Road, Great Holland - Repeater signage | Request for 30mph repeaters and roundels to be installed to remind drivers of the speed limit. | Speeding vehicles. | Cllr Platt | Frinton and Walton | Traffic Management | Total scheme | LTEN182063 | 6500 | Validation recommends to review the repeater signage and street lighting, as well as design and implement any measures which are identified.
St Osyth Road, Little Clacton - VAS | Residents have raised concerns over the speed of vehicles approaching Meadow View Park. | Speeding vehicles. | Cllr Erskine | Little Clacton | Traffic Management | Total scheme | LTEN182064 | 10000 | Speed and volume survey results - Southbound 36.3mph. Northbound 32.8mph. Validation recommends to proceed with the intention of design and implementation in one year.
B1035 Heath Road, Tendring - Speed reduction | Residents have raised concerns over the speed of the route, asking for a reduction to 30mph to be considered. | Safety issues have been raised to the parish. | Cllr Guglielmi | Tendring | Traffic Management | Total scheme | LTEN182065 | N/A | Speed and volume survey results - Southbound 36.9mph. Northbound 37.5mph. Survey data shows good compliance within the posted 40mph limit.
B1035 Thorpe Road, Tendring - Speed reduction | Residents have raised concerns over the speed of the route, asking for a reduction to 30mph to be considered. | Safety issues have been raised to the parish. | Cllr Guglielmi | Tendring | Traffic Management | Total scheme | LTEN182066 | N/A | Speed and volume survey result - Eastbound 41.6mph. Southbound 42.9mph. Information fed back to Tendring Parish Council and Cllr Guglielmi.
Old Ipswich Road, Ardleigh - Speed reduction | Residents have raised concerns over speeding vehicles and HGV usage. | Speeding vehicles. | Cllr Guglielmi | Ardleigh | Traffic Management | Validation | LTEN182067 | TBC | In validation.
Beaumont-cum-Moze - Signage review | Request for a signage review of the area. | Missing signage | Cllr Erskine | Beaumont-cum-Moze | Traffic Management | Total scheme | LTEN192001 | 4000 | Validation recommends to proceed to detailed design to identify any remedial works that are required.
St Osyth Road, Little Clacton | Speed and volume survey. | Speeding vehicles. | Cllr Erskine | Little Clacton | Surveys | Surveys
B1035 Heath Road, Tendring | Speed and volume survey. | Speed and volume survey required to investigate a speed reduction. | Parish Council | Tendring | Surveys | Surveys
B1035 Thorpe Road, Tendring | Speed and volume survey. | Speed and volume survey required to investigate a speed reduction. | Parish Council | Tendring | Surveys | Surveys
Old Ipswich Road, Ardleigh | Speed and volume survey. | Speed and volume survey required to measure HGV usage. | Parish Council | Ardleigh | Surveys | Surveys
Low Road, Harwich | Speed and volume survey. | Speeding vehicles. | Cllr Henderson | Harwich | Surveys | Surveys
Steam Mill Road, Bradfield | Bradfield Parish Council have raised speeding concerns along the route. | Speeding vehicles. | Bradfield Parish Council | Bradfield | Traffic Management | Total scheme | LTEN192003 | N/A | Speed and volume survey results - Eastbound 29.6mph. Westbound 29.9mph. Information shows good compliance within the posted speed limit. Results shared with Bradfield Parish Council and Cllr Guglielmi.
Steam Mill Road, Bradfield | Speed and volume survey. | Speeding vehicles. | Bradfield Parish Council | Bradfield | Surveys | Surveys
Grange Road, Lawford - New Footway | Request from the Parish Council to provide a new footway between School Lane and Bromley Road. | Lack of footway. | Cllr Guglielmi | Lawford | Walking | Implementation | LTEN163009 | 77500 | Implementation of a new footway linking School Lane and Bromley Road following completed design.
The Avenue, Red Barn Lane, Stone's Green Road, Great Oakley - Horse warning signage | Request from the County Member requesting horse warning signage. | Lack of signage. | Cllr Erskine | Great Oakley | Traffic Management | Validation | LTEN192004 | TBC | In validation.
Colchester Road, Ardleigh | VAS Repair | VAS reported as not working correctly. | Cllr Guglielmi | Ardleigh | VAS | Surveys
Main Road, Harwich - 20's Plenty | Request for 20's Plenty signage to be placed outside Mayflower Primary School. | Request for 20's Plenty. | Cllr Henderson | Harwich | Traffic Management | Validation | LTEN192005 | N/A | Validation recommends not to proceed with the request for 20's Plenty due to parked cars block visibility of the sign. Advisory 20 when lights flash not recommended due to existing patrol flashing signs present.
Station Road, Clacton-on-Sea - Bus cage | Request to investigate the possibility of extending the bus cage. | Buses having difficulty pulling away from the bus stop. | Passenger Transport Team | Unparished | Passenger Transport | Total scheme | LTEN195001 | 3000 | Validation recommends to extend the yellow bus cage to allow buses to pull out without driving onto the other side of the carriageway. The Panel will need to be aware that this will result in the loss of a parking space.
Kirby Road, Walton-on-the-Naze - Signing and lining | Request to investigate providing additional lining and signing. | Vehicles losing control. | Cllr Platt | Frinton and Walton | Traffic Management | Validation | LTEN192006 | TBC | Speed and volume survey demonstrates good compliance within the posted 30mph speed limit. In validation to investigate the possibility of painting roundels on the carriageway and undertaking a review of signage on the bend.
B1414 Oakley Road, Harwich | VAS Repair | VAS needs replacing. | Cllr Erskine | Ramsey | VAS | Surveys
B1032 Kirby Road, Great Holland | Cllr Platt has requested that a speed and volume survey is undertaken due to reported speeding issues. | Speeding vehicles. | Cllr Platt | Frinton and Walton | Traffic Management | Validation | LTEN192007 | TBC | Speed and volume survey information results shared with Cllr Platt. Now in validation to investigate lowering the speed limit from 40mph to 30mph.
B1032 Kirby Road, Great Holland | Cllr Platt has requested that a speed and volume survey is undertaken due to reported speeding issues. | Speeding vehicles. | Cllr Platt | Frinton and Walton | Surveys | Surveys
Pork Lane, Frinton and Walton | Cllr Platt has requested that a speed and volume survey is undertaken to assess suitability for a speed reduction. | Speed reduction requested. | Cllr Platt | Frinton and Walton | Traffic Management | Total scheme | LTEN192008 | N/A | Speed and volume survey results: Northbound - 26.5mph. Soundbound - 26.1mph. The location does not meet guidance for a 20mph due to the length of road. Information shared with Cllr Platt. This is to be delivered under LTEN172018.
Pork Lane, Frinton and Walton | Cllr Platt has requested that a speed and volume survey is undertaken to assess suitability for a speed reduction. | Speed reduction requested. | Cllr Platt | Frinton and Walton | Surveys | Surveys
Straight Road, Bradfield - Speed reduction | Cllr Guglielmi has requested a speed and volume survey is undertaken to assess suitability for a speed reduction. | Speed reduction requested. | Cllr Guglielmi | Bradfield | Traffic Management | Total scheme | LTEN192009 | N/A | Speed and volume results - Northbound 39.5mph. Southbound 38.0mph, therefore demonstating good compliance with the posted 40mph speed limit. Information relayed to Cllr Guglielmi and Bradfield PC.
Straight Road, Bradfield - Speed reduction | Cllr Guglielmi has requested a speed and volume survey is undertaken to assess suitability for a speed reduction. | Speed reduction requested. | Cllr Guglielmi | Bradfield | Surveys | Surveys
Bar Corner, St Osyth - Junction improvements | St Osyth Parish Council have raised concerns over the safety of the crossroads. | Safety concerns. | St Osyth Parish Council | St Osyth | Traffic Management | Validation | LTEN192010 | TBC | Meeting held wish Parish to agree a way forward. Parish to now investigate the possibility of funding a feasibility study.
Footpath 5, St Osyth - Surface improvements | Resurfacing of a Public Right of Way. | A popular walking route alongside Mill Dam Lake, which provides a circular route back into the village, is currently unsurfaced passed the boat-hire, and can be very muddy and slippery, especially in winter. | PROW team | St Osyth | Public Rights of Way | Total scheme | LTEN198001 | 16500 | To level the path, reverting the bank where needed, and to lay and roll road planings, to be held in place with timber edgings.
Clacton Road, Mistley | Bradfield Parish Council have raised concerns regarding the junction with Steam Mill Road. | Visibility issues. | Bradfield Parish Council | Bradfield | Traffic Management | Validation | LTEN192011 | TBC | In validation.
Cockaynes Lane, Alresford | Request for a 20mph zone to be investigated. | Pedestrians struggling to walk along the route. | Alresford Parish Council | Alresford | Traffic Management | Validation | LTEN192012 | TBC | Awaiting speed and volume survey information.
B1027 St Osyth Road, Alresford | Alresford Parish Council have requested investigation into a speed reduction from 40mph to 30mph | Vehicles travelling at excessive speeds. | Alresford Parish Council | Alresford | Traffic Management | Validation | LTEN192013 | TBC | Awaiting speed and volume survey information.
Wivenhoe Road, Alresford | Alresford Parish Council have requested investigation into traffic calming measures. | Increase in pedestrians and HGV usage. | Alresford Parish Council | Alresford | Traffic Management | Validation | LTEN192014 | TBC | Awaiting speed and volume survey information.
Wivenhoe Road, Alresford | Speed and volume survey. |  | Alresford Parish Council | Alresford | Surveys | Surveys |  | 200
Skelmersdale Road, Clacton-on-Sea | Investigation into traffic calming measures. | Speeding vehicles. | Cllr Sargeant | Unparished | Traffic Management | Validation | LTEN192015 | TBC | Awaiting speed and volume survey information.
Skelmersdale Road, Clacton-on-Sea | Speed and volume survey. |  | Cllr Sargeant | Unparished | Surveys | Surveys |  | 200
The Drive, Harwich | Speed and volume survey. |  | HLO | Harwich | Surveys | Surveys |  | 200
Chapel Lane, Crockleford Heath | Cllr Guglielmi has requested a speed and volume survey is undertaken to assess suitability for a speed reduction. | Speeding vehicles and safety. | Cllr Guglielmi | Ardleigh | Traffic Management | Validation | LTEN192016 | TBC | Awaiting speed and volume survey information.
Chapel Lane, Crockleford Heath | Speed and volume survey. |  | Cllr Guglielmi | Ardleigh | Surveys | Surveys |  | 200
Burrs Road, Clacton-on-Sea | Cllr Erskine has requested a speed and volume survey is undertaken due to percieved speeding issues. | Speeding vehicles. | Cllr Erskine | Unparished | Traffic Management | Validation | LTEN192017 | TBC | Awaiting speed and volume survey information.
Burrs Road, Clacton-on-Sea | Speed and volume survey. |  | Cllr Erskine | Unparished | Surveys | Surveys |  | 200
Plough Road, Great Bentley - Lining Improvements | Great Bentley Parish Council have raised concerns over inconsiderate parking at the junction with Station Road. | Inconsiderate parking. | Great Bentley Parish Council | Great Bentley | Traffic Management | Validation | LTEN192018 | TBC | Awaiting highway boundary information.
Parkeston Road, Harwich - Zebra Crossing | Investigation into a possible Zebra Crossing. | Safety crossing the road and vehicle speeds. | Cllr Henderson | Harwich Town Council | Traffic Management | Design | LTEN173007 | 9500 | Feasibility study has recommended to proceed to design and legal advertising. This will cost the Panel £9,500.
A133 Main Road, Frating - Crossing Improvements | Frating Parish Council have requested investigation into the possibility of installing dropped kerbing near Frating park. | Safety crossing the road and vehicle speeds. | Cllr Guglielmi | Frating | Walking | Validation | LTEN193001 | TBC | In validation.